# **Development Monitoring and Evaluation Office**

# **NITI Aayog**

Selection of Technical Consultant

Request for Proposals

for

Consultancy for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector

May 2019

Government of India

**Contents**

|  |  |  |
| --- | --- | --- |
| **S. No.** | **Contents**  | **Page No.** |
|  | Request for Proposal | 1 |
|  | Disclaimer | 2 |
|  | Glossary | 4 |
|  |  |  |
|  | **Invitation for Proposals** | 6 |
| 1 | **Introduction** | 7 |
| 2 | **Instructions to Applicants** | 12 |
| A. General | 12 |
| B. Documents | 23 |
| C. Preparation and Submission of Proposal | 25 |
| D. Evaluation Process | 31 |
| E. Appointment of Consultant | 33 |
| 3 | **Criteria for Evaluation** | 36 |
| 4 | **Fraud and corrupt practices** | 40 |
| 5 | **Pre-Proposal Conference** | 42 |
| 6 | **Miscellaneous** | 43 |
|  |  |  |
|  | **Schedules** | 44 |
| 1 | **Terms of Reference** | 45 |
| 2 | **Form of Agreement** | 64 |
| Annex-1: Terms of Reference | 91 |
| Annex-2: Deployment of Personnel | 92 |
| Annex-3: Estimate of Personnel Costs | 93 |
| Annex-4: Approved Sub-Consultant(s) | 94 |
| Annex-5: Cost of Services | 95 |
| Annex-6: Payment Schedule | 96 |
| Annex-7: Bank Guarantee for Performance Security | 97 |
|  |  |
| 3 | **Guidance Note on Conflict of Interest** | 99 |
|  |  |  |
|  | **Appendices** | 101 |
| 1 | **Appendix-I: Technical Proposal** | 102 |
|  | Form 1: Letter of Proposal | 100 |
|  | Form 2: Particulars of the Applicant | 105 |
|  | Form 3: Statement of Legal Capacity | 108 |
|  | Form 4: Power of Attorney  | 109 |
|  | Form 5: Financial Capacity of Applicant | 111 |
|  | Form 6: Particulars of Key Personnel | 112 |
|  | Form 7: Proposed Methodology and Work Plan | 114 |
|  | Form 8: Abstract of Eligible Assignments of the Applicant | 115 |
|  | Form 9: Abstract of Eligible Assignments of Key Personnel | 116 |
|  | Form 10: Eligible Assignments of Applicant | 117 |
|  | Form 11: Eligible Assignments of Key Personnel | 118 |
|  | Form 12: Curriculum Vitae (CV) of Professional Personnel | 119 |
|  | Form 13: Deployment of Personnel | 121 |
|  | Form 14: Survey and Field Investigations | 122 |
|  | Form 15: Proposal for Sub-Consultant(s) | 123 |
|
| 2 | **Appendix-II: Financial Proposal** | 124 |
|  | Form 1: Covering Letter | 124 |
|  | Form 2: Financial Proposal | 125 |
|  | Form 3: Estimate of Personnel Costs | 128 |
|  |  |  |
| 3 | **Appendix-III: List of Bid-specific provisions** | 129 |
|
| 4 | **Appendix-IV: References** | 130 |

No. I-19015/01/2019-DMEO

Government of India

NITI Aayog

Development Monitoring and Evaluation Office

Sansad Marg, New Delhi -110001

**Request for Proposal (RFP)**

May 6th, 2019

**Notice: Request for Proposal (RFP) for Consultancy for Evaluation of Centrally Sponsored Schemes under Package 5 - Rural Development Sector.**

The Development Monitoring and Evaluation Office (DMEO), National Institution for Transforming India (NITI) Aayog, Government of India, intends to engage Consultants to conduct evaluation of Centrally Sponsored Schemes (CSS) under **Package 5 - Rural Development Sector**, details of which have been provided in the RFP document.

DMEO, NITI Aayog invites proposals for Package 5 - Rural Development Sector, from national/ international firms/ organisations/ institutions, which have requisite experience in this field as detailed in the RFP. The salient features of the study, eligibility criteria and instructions on how to bid and other details are available in the RFP document uploaded on the websites http://niti.gov.in/tenders. Important Information & tentative dates are given in section 1 of the RFP.

Interested applicants are requested to submit their response to the RFP in a sealed envelope through Speed Post/ Registered Post or deliver by hand super scribing “**RFP for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector”**on top of the envelope to the following address on or before June 4th, 2019, 1100 hrs.

The submission must be addressed to:

Shri O.P. Thakur

Senior Research Officer

Development Monitoring & Evaluation Office (DMEO)

C-022 5th floor, NITI Aayog, Sansad Marg

New Delhi, 110001

Email: dmeoeval-niti@gov.in

**Disclaimer**

The information contained in this Request for Proposals document (“**RFP**”) or subsequently provided to Applicants, whether verbally or in documentary or any other form by or on behalf of the Authority or any of its employees or advisers, is provided to Applicants on the terms and conditions set out in this RFP and such other terms and conditions subject to which such information is provided.

This RFP is not an agreement and is neither an offer nor invitation by the Authority to the prospective Applicants or any other person. The purpose of this RFP is to provide interested parties with information that may be useful to them in the formulation of their Proposals pursuant to this RFP. This RFP includes statements, which reflect various assumptions and assessments arrived at by the Authority in relation to the Consultancy. Such assumptions, assessments and statements do not purport to contain all the information that each Applicant may require. This RFP may not be appropriate for all persons, and it is not possible for the Authority, its employees or advisers to consider the objectives, technical expertise and particular needs of each party who reads or uses this RFP. The assumptions, assessments, statements and information contained in this RFP, may not be complete, accurate, adequate or correct. Each Applicant should, therefore, conduct its own investigations and analysis and should check the accuracy, adequacy, correctness, reliability and completeness of the assumptions, assessments and information contained in this RFP and obtain independent advice from appropriate sources.

Information provided in this RFP to the Applicants is on a wide range of matters, some of which depends upon interpretation of law. The information given is not an exhaustive account of statutory requirements and should not be regarded as a complete or authoritative statement of law. The Authority accepts no responsibility for the accuracy or otherwise for any interpretation or opinion on the law expressed herein.

The Authority, its employees and advisers make no representation or warranty and shall have no liability to any person including any Applicant under any law, statute, rules or regulations or tort, principles of restitution or unjust enrichment or otherwise for any loss, damages, cost or expense which may arise from or be incurred or suffered on account of anything contained in this RFP or otherwise, including the accuracy, adequacy, correctness, reliability or completeness of the RFP and any assessment, assumption, statement or information contained therein or deemed to form part of this RFP or arising in any way in this Selection Process.

The Authority also accepts no liability of any nature whether resulting from negligence or otherwise, howsoever caused, arising from reliance of any Applicant upon the statements contained in this RFP.

The Authority may in its absolute discretion, but without being under any obligation to do so, update, amend or supplement the information, assessment or assumption contained in this RFP.

The issue of this RFP does not imply that the Authority is bound to select an Applicant or to appoint the Selected Applicant, as the case may be, for the Consultancy and the Authority reserves the right to reject all or any of the Proposals without assigning any reasons whatsoever.

The Applicant shall bear all its costs associated with or relating to the preparation and submission of its Proposal including but not limited to preparation, copying, postage, delivery fees, expenses associated with any demonstrations or presentations which may be required by the Authority or any other costs incurred in connection with or relating to its Proposal. All such costs and expenses will remain with the Applicant and the Authority shall not be liable in any manner whatsoever for the same or for any other costs or other expenses incurred by an Applicant in preparation or submission of the Proposal, regardless of the conduct or outcome of the Selection Process.

**Glossary**

**Additional Costs** As in Item H of Form-2 of Appendix-II

**Agreement** As defined in Schedule-2

**Agreement Value** As defined in Clause 6.1.2 of Schedule-2

**Applicable Laws** As defined in Schedule-2

**Applicant** As defined in Clause 2.1.1

**Associate** As defined in Clause 2.3.3

**Authorised Representative** As defined in Clause 2.13.3

**Authority** As defined in Clause 1.1.1

**Bid Security** As defined in Clause 2.20.1

**Conditions of Eligibility** As defined in Clause 2.2.1

**Conflict of Interest** As defined in Clause 2.3.1

**Consultancy** As defined in Clause 1.2

**Consultancy Team** As defined in Clause 2.1.4

**Consultant** As defined in Clause 1.2

**CV** Curriculum Vitae

**Deliverables** As defined in Paragraph 8 of Schedule-1

**Documents** As defined in Clause 2.12

**Effective Date** As defined in Clause 2.1 of Schedule-2

**Eligible Assignments** As defined in Clause 3.1.4

**Final Evaluation Report** As specified in Paragraph 10 of Schedule-1

**Financial Proposal** As defined in Clause 2.15.1

**Form of Agreement** Form of Agreement as in Schedule-2

**INR, Re, Rs.** Indian Rupee(s)

**Inception Report** As specified in Paragraph 8 of Schedule-1

**Key Date or KD** As defined in Paragraph 9 of Schedule-1

 **Key Personnel** As defined in Clause 2.1.4

##### **Lead Member**  As defined in Clause 2.1.1

**LOA** Letter of Award

**Member** As defined in Clause 2.3.3 (a)

**Official Website** As defined in Clause 1.11.2

**Personnel** As defined in Clause 1.1.1(n) of Schedule-2

**Professional Personnel** As defined in Clause 2.14.6

**Prohibited Practices**  As defined in Clause 4.1

**Project** As defined in Clause 1.1.6

**Project Manager** As defined in Clause 4.6 of Schedule-2

**Proposal** As defined in Clause 1.2

**Proposal Due Date or PDD** As defined in Clauses 1.5 and 1.8

**Resident Personnel** As defined in Clause 1.1.1(o) of Schedule-2

**RFP** As defined in Disclaimer

##### **Selected Applicant** As defined in Clause1.6

##### **Selection Process** As defined in Clause 1.6

##### **Services** As defined in Clause 1.1.1(q) of Schedule-2

**Sole Firm** As defined in Clause 2.1.1

**Statement of Expenses** As defined in Note 13, Form-2 of Appendix-II

**Statutory Auditor** An Auditor appointed under Applicable Laws

**Sub-Consultant** As defined in Clause 1.1.1(r) of Schedule-2

**Support Personnel** As defined in Clause 2.14.6

**Team Leader** As defined in Clause 2.1.4

**Technical Proposal** As defined in Clause 2.14.1

**TOR** As defined in Clause 1.1.6

**US$** United States Dollar

**WG** As defined in Paragraph 12 of the TOR

The words and expressions beginning with capital letters and defined in this document shall, unless repugnant to the context, have the meaning ascribed thereto herein.

**Invitation for Proposals**

**1. INTRODUCTION**[[1]](#footnote-1)$

* 1. Background
		1. The Development Monitoring and Evaluation Office (DMEO) (the “Authority”) was constituted in September 2015 by merging of the erstwhile Programme Evaluation Office (PEO) and the Independent Evaluation Office (IEO). DMEO is an attached Office of NITI Aayog to fulfil the mandates of monitoring and evaluation assigned to NITI Aayog.
		2. To ensure efficient and effective use of public resources, the Government of India has made evaluation of the Centrally Sponsored Schemes (CSS) and Central Sector schemes mandatory before the schemes come up for fresh appraisal. The Government also has adopted output-outcome monitoring framework to strengthen monitoring and evaluation of the schemes. After the Five-Year Plans were done away with at the end of 12thFive Year Plan, in order to rationalize the available resources based on the recommendations of the Finance Commission for the achievement of the National Development Agenda, the Government had made the approval of the schemes co-terminus with the Finance Commission cycle.
		3. The 14thFinance Commission cycle will end in March 2020, and the 15thFinance Commission will begin thereafter. The Government has assigned DMEO, NITI Aayog the responsibility to conduct independent third-party evaluation of all the CSS in a time bound manner so that the findings of the evaluation are made available to appropriate authorities for determining the rationalization of the schemes.
		4. Proliferation of the number of CSS has led to a number of concerns. Based on the recommendation of the Sub-Group of Chief Ministers on the rationalization of CSS, and consultations with various Ministries/Departments and other stakeholders, the Government of India in 2016 rationalized the CSS under the 28 umbrella CSSto achieve the overarching National Development Agenda. The National Development Agenda consists of the following: (i) poverty elimination – livelihoods, jobs and skill development; (ii) drinking water and Swachh Bharat mission; (iii) rural connectivity: electricity, access roads and communication; (iv) agriculture including animal husbandry, fisheries, integrated watershed management and irrigation; (v) education including mid-day meal; (vi) health, nutrition, women and child; (vii) housing for all: rural and urban; (viii) urban transformation; (ix) law and order, justice delivery system; and (x) others, which may include: wildlife conservation and greening.
		5. The evaluation of the CSS under the 28 umbrella CSS will be conducted through 10 sector evaluation studies listed below. DMEO invites proposal for selection of technical consultants (the Consultants) to conduct evaluation of the following 10 sectors.

|  |  |  |
| --- | --- | --- |
| **Name of the package** | **Ministries/Departments involved** | **Name of Umbrella Centrally Sponsored Scheme** |
| Agriculture, Animal Husbandry and Fisheries | * Ministry of Agriculture and Farmers’ Welfare
 | * + Blue Revolution (fisheries)
	+ Green Revolution (agriculture)
	+ White Revolution (animal husbandry)
 |
| Women and Child | * Ministry of Women and Child
 | * + Integrated Child Development Services
	+ Mission for Empowerment and Protection of Women
 |
| Human Resource Development | * Ministry of Human Resource Development
 | * + National Education Mission
	+ National Programme of Mid-day Meal in Schools
	+ Umbrella Programme for Development of Minorities
 |
| Urban Transformation | * Ministry of Housing and Urban Affairs
 | * + Pradhan Mantri Awas Yojana (Urban)\*
	+ Deendayal Antyodaya Yojana-National Urban Livelihood Mission\*
	+ Swachh Bharat Mission (Urban)
	+ Urban Rejuvenation Mission (AMRUT and Smart Cities )
 |
| Rural Development | * Ministry of Rural Development
 | * + Mahatma Gandhi National Rural Employment Guarantee Program
	+ National Rural Livelihood Mission (Ajeevika)
	+ National Social Assistance Programme
	+ Pradhan Mantri Awas Yojana (Gramin)\*
	+ Pradhan Mantri Gram Sadak Yojana
	+ Shyama Prasad Mukherjee Rurban Mission
 |
| Drinking Water and Sanitation | * Ministry of Drinking Water and Sanitation
 | * + Swachh Bharat Mission (Rural)\*
	+ National Rural Drinking Water Mission
 |
| Health | * Ministry of Health and Family Welfare
* Ministry of AYUSH
 | * + National Health Mission
	+ National Health Protection Scheme (erstwhile RSSY)
 |
| Jobs and Skills | * Ministry of Labour and Employment
* Ministry of Skill Development and Entrepreneurship
 | * + Jobs and Skills Development
 |
| Water Resource, Environment and Forest\*\* | * Ministry of Water Resource River Development and Ganga Rejuvenation
* Ministry of Environment Forest and Climate Change
 | * + Pradhan Mantri Krishi Sinchai Yojana\*\*
	+ Environment, Forestry and Wildlife
 |
| Social Inclusion, Law and Order & Justice Delivery | * Ministry of Home Affairs
* Ministry of Law and Justice
* Ministry of Minority Affairs
* Ministry of Social Justice and Empowerment
 | * + Umbrella Programme for Development of Scheduled Castes
	+ Umbrella Programme for Development of backward classes, differently abled and other vulnerable groups
	+ Umbrella Programme for Development of scheduled tribes
	+ Umbrella Programme for Development of minorities
	+ Modernization of Police Forces
	+ Infrastructure Facilities for Judiciary
	+ Border Area Development Program
 |

\*Umbrella CSS split between two ministries that are evaluated under different ministries (SBM, Awas Yojana, Livelihood)

\*\* Pradhan Mantri Krishi Sinchai Yojana umbrella CSS although under three ministries (Water Resources, Rural Development and Agriculture) all components under the umbrella CSS will be evaluated by under package 9.

* + 1. In pursuance of the above, the Authority has decided to carry out the process for selection of a Technical Consultant for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector(the “**Project**”)in accordance with the Terms of Reference specified at Schedule-1 (the “**TOR**”).
	1. Request for Proposals
		1. The Authority invites proposals (the “**Proposals**”) for selection of a Technical Consultant (the “**Consultant**”) who shall conduct an evaluation study of the concerned sector, including an assessment of the performance of the sector, the coverage and performance of the identified UmbrellaCSS in the sector, and the performance of the schemes under theUmbrella CSS, in accordance with the TOR (collectively the “**Consultancy**”).

The Authority intends to select the Consultant through an open competitive bidding process in accordance with the procedure set out herein.

* 1. Due diligence by Applicants

Applicants are encouraged to inform themselves fully about the assignment and the local conditions before submitting the Proposal by paying a visit to the Authority, sending written queries to the Authority, and attending a Pre-Proposal Conference on the date and time specified in Clause 1.10.

* 1. Availability of RFP Document

The document can be downloaded from the Official Website of the Authority (www.niti.gov.in/tenders/).

* 1. Validity of the Proposal

The Proposal shall be valid for a period of not less than 90 days from the Proposal Due Date (the “**PDD**”).

* 1. Brief description of the Selection Process

The Authority has adopted a two-stage selection process (collectively the “**Selection Process**”) for evaluating the Proposals comprising technical and financial bids to be submitted in two separate sealed envelopes. In the first stage, a technical evaluation will be carried out as specified in Clause 3.1. Based on this technical evaluation, a list of short-listed applicants shall be prepared as specified in Clause 3.2. In the second stage, a financial evaluation will be carried out as specified in Clause 3.3. Proposals will finally be ranked according to their combined technical and financial scores as specified in Clause 3.4. The first ranked Applicant shall be selected for negotiation (the “**Selected Applicant**”) while the second ranked Applicant will be kept in reserve.

* 1. Currency conversion rate and payment
		1. For the purposes of technical evaluation of Applicants, Rs. 69 (Rupees sixty-nine) per US$ shall be considered as the applicable currency conversion rate. In case of any other currency, the same shall first be converted to US$ as on the date 60 (sixty) days prior to the Proposal Due Date, and the amount so derived in US$ shall be converted into INR at the aforesaid rate. The conversion rate of such currencies shall be the daily representative exchange rates published by the International Monetary Fund for the relevant date.
		2. All payments to the Consultant shall be made in INR in accordance with the provisions of this RFP. The Consultant may convert INR into any foreign currency as per Applicable Laws and the exchange risk, if any, shall be borne by the Consultant.
	2. Schedule of Selection Process

The Authority would endeavour to adhere to the following schedule:

|  |  |  |
| --- | --- | --- |
|  | **Event Description** | **Date** |
| 1. | Last date for receiving queries/clarifications | [20 days prior to PDD] |
| 2. | Pre-Proposal Conference | [16 days prior to PDD] |
| 3. | Authority response to queries  | [11 days prior to PDD] |
| 4. | Proposal Due Date or PDD | 4th June 2019 |
| 5. | Opening of Proposals | On Proposal Due Date |
| 6. | Letter of Award (LOA) | [Within 15 days of PDD] |
| 7. | Signing of Agreement  | Within 10 days of LOA  |
| 8. | Validity of Applications | 90 days of Proposal Due Date |

* 1. Pre-Proposal Queries

Prospective Applicants may address their queries to the nodal officer specified below: Shri O.P. Thakur

Senior Research Officer

Development Monitoring & Evaluation Office (DMEO)

C-022, 5th Floor, NITI Aayog, Sansad Marg

New Delhi, 110001

Email: dmeoeval-niti@gov.in

Phone: 011 - 23045133

* 1. Pre-Proposal Conference

The date, time and venue of Pre-Proposal Conference shall be:

Date: 20thMay 2019

Time: 10:00 hrs

Venue: To be communicated on the NITI Aayog website

Further details regarding the Pre-proposal will be updated on the official website of the Authority.

* 1. Communications
		1. All communications including the submission of Proposal should be addressed to:

Applicants may register for the same on or before 18th May 2019 by submitting the following details of their representatives attending the pre-proposal conference at the email address mentioned in clause 1.11: Name, Designation, Company, Mobile number, Email Address, Sectors/Packages of interest.

O.P. Thakur

Senior Research Officer

Development Monitoring & Evaluation Office (DMEO)
C-022, 5th floor, NITI Aayog, Sansad Marg
New Delhi, 110001

Phone: 011 - 23045133

Email: dmeoeval-niti@gov.in

* + 1. The Official Website of the Authority is:

<http://www.>[niti.gov.in](http://www.niti.gov.in)

Note: Please open [www.niti.gov.in/tenders](http://www.niti.gov.in/tenders/smart)/ to access all the posted and uploaded documents related to this RFP.

* + 1. All communications, including the envelopes, should contain the following information, to be marked at the top in bold letters:

**RFP for Consultancy for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector2.INSTRUCTIONS TO APPLICANTS**

**A. GENERAL**

* 1. Scope of Proposal
		1. Detailed description of the objectives, scope of services, Deliverables and other requirements relating to this Consultancy are specified in this RFP. In case an applicant firm possesses the requisite experience and capabilities required for undertaking the Consultancy, it may participate in the Selection Process either individually (the “**Sole Firm**”) or as lead member of a consortium of firms (the “**Lead Member**”) in response to this invitation. The term applicant (the “**Applicant**”) means the Sole Firm or the Lead Member, as the case may be. The manner in which the Proposal is required to be submitted, evaluated and accepted is explained in this RFP.
		2. Applicants are advised that the selection of Consultant shall be on the basis of an evaluation by the Authority through the Selection Process specified in this RFP. Applicants shall be deemed to have understood and agreed that no explanation or justification for any aspect of the Selection Process will be given and that the Authority’s decisions are without any right of appeal whatsoever.
		3. The Applicant shall submit its Proposal in the form and manner specified in this Part-2 of the RFP. The Technical Proposal shall be submitted in the form at Appendix-I and the Financial Proposal shall be submitted in the form at Appendix-II. Upon selection, the Applicant shall be required to enter into an agreement with the Authority in the form specified at Schedule-2.
		4. Key Personnel

The Consultant shall form a multi-disciplinary team (the “**Consultancy Team**”) for undertaking this assignment.The Consultancy Team shall consist of the following key personnel (the “**Key Personnel**”). The key personnel will comprise of core team and non-core team who shall discharge their respective responsibilities as specified below:

|  |  |
| --- | --- |
| **Key Personnel** | **Responsibilities** |
| **Core Team (**Expected to be deployed full time over the entire duration of the assignment and to be scored as a part of the bid evaluation**)** |
| Team Leader (the “**Team Leader**”) | S/He will lead, co-ordinate and supervise the multidisciplinary team for preparation of the Evaluation Study, and act as a focal point to the Authority throughout the duration of the Consultancy for the specific sector. S/He will be responsible for:* Overall execution of the consultancy assignment.
* Accountable leadership providing guidance, problem solving support and leading discussions with senior stakeholders
* Ensure all deliverables and milestones are satisfactorily delivered
* Provide insights from experience in Social sector projects, PSU/Govt. work, large scale projects.
 |
| Deputy Team Leader | S/He will assist the Team lead in leading, co-ordinating and supervising the multidisciplinary team for preparation of the Evaluation Study.S/He will be responsible for:* Leading day-to-day management of the team
* Project management of the project as per agreed activities, timelines and deliverables
* Communication related activities
* Defining the detailed work plan, and managing the team of consultants against the work plan
* Drive discussions with senior officials in the Govt at Centre and State level
* Working with the client project team and stakeholders
* Sending periodic updates, and highlighting challenges in project execution
 |
| Monitoring and Evaluation Expert | S/He will be responsible for:* Designing the overall study approach to synthesize sectoral analysis and the CSS scheme-wise analysis.
* Organizing and overseeing the use of qualitative and quantitative evaluation techniques
* Designing a meta-analysis plan based on the secondary data (including NITI Aayog’s Output-Outcome Monitoring data).
* Designing primary data collection tools like discussion guides for focus group discussions, agenda for in-depth interviews and household-level survey questionnaires and prepare a data analysis plan.
* Ensuring data quality of the primary data collected and the use of latest analytical tools for qualitative and quantitative data analysis
 |
| Economist | S/He will be responsible for * Providing economic perspectives on all aspects of the project, including poverty alleviation,
* Providing analysis, insights and inputs focussing on the cross-sectional themes of direct/indirect employment generation, impact on and role of private sector, community and civil society in the scheme.
 |
| Rural Development Sector Lead | S/he will be responsible for providing subject matter/sector/domain expertise of the proposed Project including:* The Alignment of the Sector with the mapped SDGs and National Priorities.
* Providing for Designing the KII, FGDs, other tools etc.
* Providing analysis plan, meta-analysis, questionnaire and discussion guide design, analysis of secondary and primary data, mid-term and final evaluation report review, sector-specific synthesis and recommendations, etc. among others.
 |
| **Non-core Team (Expected to be deployed based on approach and methodology adopted for the assignment and requirements of the client, but not to be evaluated as a part of the bid)** |
| Finance Specialist | S/He will provide:* Financial analysis and support throughout the project.
* Analysis, insights and inputs focussing on the cross-sectional theme of Public expenditure tracking.

S/He will spend at least 30 (thirty) days on the Project.  |
| Statistician | S/He will be responsible for providing basic statistical rigour in developing methodology including sampling, questionnaires, data analysis from primary and secondary sources.S/He shall spend at least 30 (thirty) days on the Project. |
| Public Institution Specialist | S/He will be responsible for * Providing expertise on dealing with government stakeholders across the system, from village level upwards, institutional arrangements, fund flows etc.
* Providing analysis, insights and inputs focussing on the cross-sectional themes of accountability and transparency,reforms and regulations, human resource, capacity building etc.

S/He shall spend at least 40 (forty) days on the Project.  |
| Gender and Social Inclusion Specialist | S/He will be responsible for:* Providing expertise on assessing the integration of gender and social inclusion concerns, i.e., gender mainstreaming, attitudes towards gender etc, in the programmes, particularly in terms of equity.
* Providing analysis, insights and inputs focussing on the cross-sectional themes of gender mainstreaming, inclusion of SC, ST, OBC, Minorities, Person with disabilities etc.

S/He shall spend at least 20 (twenty) days on the Project. |
| Environment, Climate Change & Sustainability Specialist | S/He will be responsible for providing:* Expertise on assessing the integration of environmental sustainability and climate change in the programmes.
* Analysis, insights and inputs focussing on the cross-sectional themes of Climate change and sustainability

S/He shall spend at least 20 (twenty) days on the Project.  |
| Information Technology Specialist | S/He will be responsible for:* Providing database support, standardization etc.
* Reviewing and asessing application of IT for project implementation, M&E etc.
* Ensuring IT-based primary data collection, surveys etc.
* Providing analysis, insights and inputs focussing on the cross-sectional themes of use of IT/Technology in driving efficiency.

S/He shall spend at least 20 (twenty) days on the Project.  |
| Safeguards Specialist | S/He will be responsible for:* Assessing environmental and social risks in the schemes under the sector
* Recommending minimization and mitigation measures to address adverse project impacts/negative externalities on people and the environment.

S/He shall spend at least 10(ten) days on the Project.  |
| Livelihood Expert | S/he will be responsible for:* Providing subject matter/sector/domain expertise of the proposed Project
* Providing analysis plan, meta-analysis, questionnaire and discussion guide design, analysis of secondary and primary data, mid-term and final evaluation report review, horticulture specific synthesis and recommendations, etc. among others.

S/he shall spend at least 30 (thirty) days on the Project. |
| Rural Infrastructure Expert | S/he will be responsible for:* Providing subject matter/sector/domain expertise of the proposed Project
* Providing analysis plan, meta-analysis, questionnaire and discussion guide design, analysis of secondary and primary data, mid-term and final evaluation report review, horticulture specific synthesis and recommendations, etc. among others.

S/he shall spend at least 30 (thirty) days on the Project. |

* 1. Conditions of Eligibility of Applicants
		1. Applicants must read carefully the minimum conditions of eligibility (the “**Conditions of Eligibility**”) provided herein.Proposals of only those Applicants who satisfy the Conditions of Eligibility will be considered for evaluation.
		2. To be eligible for evaluation of its Proposal, the Applicant shall fulfil the following:
1. **Technical Capacity**: The Applicant should be a Private/ Public limited company or partnership firm or expert institution with operations in India. Individuals are not eligible to participate in this RFP.The Applicant shall have, over the past 5 (five) years preceding the PDD, undertaken a minimum of 3 (three) Eligible General Assignments and 1 (one) Eligible Specific Assignments as specified in Clause 3.1.4.The Applicant (Bidder) should not have been blacklisted by the Central Government, any State Government, a Statutory Authority, or a Public-Sector Undertaking, from participating in any consulting assignment
2. **Financial Capacity**: The Applicant shall have received a minimum income of Rs. 50 (fifty) crores per annum from professional fees during each of the 3 (three) financial years preceding the Proposal Due Date. For the purpose of evaluation, Applicants having comparatively larger revenues from professional fees shall be given added weightage. For the avoidance of doubt, professional fees hereunder refers to fees received by the Applicant for providing advisory or consultancy services to its clients.
3. **Availability of Key Personnel:** The Applicant shall offer and make available all Key Personnel meeting the requirements specified in Sub-clause (D) below.
4. **Conditions of Eligibility for Key Personnel:** Each of the Key Personnel must fulfil the Conditions of Eligibility specified below:

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Personnel** | **Educational Qualification** | **Length of Professional Experience** | **Experience on Eligible Assignments** |
| **Core Team (**Expected to be deployed full time over the entire duration of the assignment and to be scored as a part of the bid evaluation**)** |
| **Team Leader** | Postgraduate degree in Education,International Development, Economics, Public Policy, Political Science, Statistics, Sociology or related fields. Ph.D. and Project Management certification preferred | 15 years | S/he should have led the team for 2 (two) Eligible General Assignments and 1 (one) Eligible Specific Assignment. S/he should have an experience of minimum 5 years in sector |
| **Deputy Team Leader** | MBA or Postgraduate Diploma in Management or equivalent | 12 years | S/He should have participated in at least 2 (two) Eligible General Assignments and been deputy leader of 1 (one) Eligible Specific Assignment. |
| **Monitoring and Evaluation Expert** | Postgraduate degree in International Development, Economics, Econometrics, Political Science, Statistics or related field. Diploma/training courses in M&E or Evaluations research preferred. | 10 years | S/He should have undertaken M&E advisory and analysis for at least 1 (one) Eligible General Assignments and 2 (two) Eligible Specific Assignment. |
| **Economist** | Postgraduate degree, preferably PhD, in Economics, Econometrics or related fields. | 10 years | S/He should have undertaken economic advisory and analysis for at least 2 (two) Eligible General Assignments and 1 (one) Eligible Specific Assignment.Experience in population studies, demographics will be preferred |
| **Rural Development Sector Lead** | Postgraduate degree in Rural Development, Rural Management, Development studies or related fields | 10 | S/He should have undertaken Subject Matter advisory and analysis for 2 (two) Eligible General Assignments and 1 Eligible Specific Assignment. |
| **Non-core Team (To be deployed based on approach and methodology adopted for the assignment and requirements of the client, but will not be evaluated as a part of the bid)** |
| **Finance Specialist** | Postgraduate degree in Finance, Economics, Development Economics, Public Finance or Bachelors with CA/ ICWA or related fields | 10 years | S/He should have undertaken financial analysis for 2 (two) Eligible General Assignments |
| **Statistician** | Postgraduate degree in Statistics, Economics, Econometrics, Mathematics or related fields | 10 years | S/He should have undertaken statistical analysis and advisory for 2 (two) Eligible General Assignments and 1(one) Eligible Specific Assignment. S/he must have experience in designing and running household surveys. |
| **Public Institution Specialist** | Postgraduate degree in Public Policy, Governance, Public Administration or related fields or Post graduate degree in any discipline with at least 5 years of experience in Public Administration/Public Policy | 7 years | S/He should have undertaken policy analysis /public administration advisory for 2 (two) Eligible General Assignments. |
| **Gender and Social Inclusion Specialist** | Postgraduate degree in social sciences, preferably Gender Studies, Social Inclusion etc. or related fields | 7 years | S/He should have undertaken gender mainstreaming/social inclusion advisory and analysis for 2 (two) Eligible General Assignments |
| **Environment, Climate Change & Sustainability Specialist** | Postgraduate degree in Sustainability, Sustainable Development, Enviromental Sciences, Environmental Engineering, Environmental Planning or related fields | 7 years | S/He should have undertaken sustainability advisory and analysis for 2 (two) Eligible General Assignments |
| **Information Technology Specialist** | B.Tech/ B.E. or equivalent in Information Technology, Computer ApplicationsOR Masters in Computer Applications or related fields | 7 years | S/He should have undertaken technological support for 2 (two) Eligible General Assignments |
| **Safeguards Specialist** | Postgraduate in Anthropology, Sociology, Applied Social Science or other related fields. | 7 years | S/He should have undertaken safeguards/risk advisory and analysis for 2 (two) Eligible General Assignments |
| **Livelihoods Expert** | Postgraduate degree in Rural Development, Rural Management, Development studies, or related fields | 10 years | S/He should have undertaken Subject Matter advisory and analysis for 2 (two) Eligible General Assignments |
| **Rural Infrastructure Expert** | BE/BTech in Civil Engineering. MTech/ME preferred. | 10 years | S/He should have undertaken Subject Matter advisory and analysis for 2 (two) Eligible General Assignments. S/he must have experience in rural asset creation, including roads, housing, etc.  |

* + 1. The Applicant shall enclose with its Proposal, certificate(s) from its Statutory Auditors[[2]](#footnote-2)$ stating its total revenues from professional fees during each of the 3 (three) financial years preceding the PDD and the fee received in respect of each of the Eligible Assignments specified in the Proposal. In the event that the Applicant does not have a statutory auditor, it shall provide the requisite certificate(s) from the firm of Chartered Accountants that ordinarily audits the annual accounts of the Applicant.
		2. The Applicant should submit a Power of Attorney as per the format at Form-4 of Appendix-I; provided, however, that such Power of Attorney would not be required if the Application is signed by a partner of the Applicant, in case the Applicant is a partnership firm or limited liability partnership.
		3. Any entity which has been barred by the Central Government, any State Government, a statutory authority or a public sector undertaking, as the case may be, from participating in any project, and the bar subsists as on the date of Proposal, would not be eligible to submit a Proposal either by itself or through its Associate.
		4. An Applicant or its Associate should have, during the last three years, neither failed to perform on any agreement, as evidenced by imposition of a penalty by an arbitral or judicial authority or a judicial pronouncement or arbitration award against the Applicant or its Associate, nor been expelled from any project or agreement nor have had any agreement terminated for breach by such Applicant or its Associate.
		5. While submitting a Proposal, the Applicant should attach clearly marked and referenced continuation sheets in the event that the space provided in the specified forms in the Appendices is insufficient. Alternatively, Applicants may format the specified forms making due provision for incorporation of the requested information.
	1. Conflict of Interest
		1. An Applicant shall not have a conflict of interest that may affect the Selection Process or the Consultancy (the “**Conflict of Interest**”). Any Applicant found to have a Conflict of Interest shall be disqualified. In the event of disqualification, the Authority shall forfeit and appropriate the Bid Security as mutually agreed genuine pre-estimated compensation and damages payable to the Authority for, *inter alia*, the time, cost and effort of the Authority including consideration of such Applicant’s Proposal, without prejudice to any other right or remedy that may be available to the Authority hereunder or otherwise.
		2. The Authority requires that the Consultant provides professional, objective, and impartial advice and at all times hold the Authority’s interests paramount, avoid conflicts with other assignments or its own interests, and act without any consideration for future work. The Consultant shall not accept or engage in any assignment that would be in conflict with its prior or current obligations to other clients, or that may place it in a position of not being able to carry out the assignment in the best interests of the Authority.
		3. Some guiding principles for identifying and addressing Conflicts of Interest have been illustrated in the Guidance Note at Schedule-3. Without limiting the generality of the above, an Applicant shall be deemed to have a Conflict of Interest affecting the Selection Process, if:

(a) the Applicant, its consortium member (the “**Member**”) or Associate (or any constituent thereof) and any other Applicant, its consortium member or Associate (or any constituent thereof) have common controlling shareholders or other ownership interest; provided that this disqualification shall not apply in cases where the direct or indirect shareholding or ownership interest of an Applicant, its Member or Associate (or any shareholder thereof having a shareholding of more than 5% (five per cent) of the paid up and subscribed share capital of such Applicant, Member or Associate, as the case may be) in the other Applicant, its consortium member or Associate is less than 5 per cent of the subscribed and paid up equity share capital thereof; provided further that this disqualification shall not apply to any ownership by a bank, insurance company, pension fund or a public financial institution referred to in sub-section (72) of section 2 of the Companies Act, 2013. For the purposes of this Clause 2.3.3(a), indirect shareholding held through one or more intermediate persons shall be computed as follows: (aa) where any intermediary is controlled by a person through management control or otherwise, the entire shareholding held by such controlled intermediary in any other person (the “**Subject Person**”) shall be taken into account for computing the shareholding of such controlling person in the Subject Person; and (bb) subject always to sub-clause (aa) above, where a person does not exercise control over an intermediary, which has shareholding in the Subject Person, the computation of indirect shareholding of such person in the Subject Person shall be undertaken on a proportionate basis; provided, however, that no such shareholding shall be reckoned under this sub-clause (bb) if the shareholding of such person in the intermediary is less than 26% (twenty six per cent) of the subscribed and paid up equity shareholding of such intermediary; or

(b) a constituent of such Applicant is also a constituent of another Applicant; or

(c) such Applicant or its Associate receives or has received any direct or indirect subsidy or grant from any other Applicant or its Associate; or

(d) such Applicant has the same legal representative for purposes of this Application as any other Applicant; or

(e) such Applicant has a relationship with another Applicant, directly or through common third parties, that puts them in a position to have access to each other’s information about, or to influence the Application of either or each of the other Applicant; or

(f) there is a conflict among this and other consulting assignments of the Applicant (including its personnel and Sub-Consultant) and any subsidiaries or entities controlled by such Applicant or having common controlling shareholders. The duties of the Consultant will depend on the circumstances of each case. While providing consultancy services to the Authority for this particular assignment, the Consultant shall not take up any assignment that by its nature will result in conflict with the present assignment; or

(g) a firm which has been engaged by the Authority to provide goods or works or services for a project, and its Associates, will be disqualified from providing consulting services for the same project save and except as provided in Clause 2.3.4; conversely, a firm hired to provide consulting services for the preparation or implementation of a project, and its Members or Associates, will be disqualified from subsequently providing goods or works or services related to the same project; or

(h) the Applicant, its Member or Associate (or any constituent thereof), and the bidder or Concessionaire, if any, for the Project, its contractor(s) or sub-contractor(s) (or any constituent thereof) have common controlling shareholders or other ownership interest; provided that this disqualification shall not apply in cases where the direct or indirect shareholding or ownership interest of an Applicant, its Member or Associate (or any shareholder thereof having a shareholding of more than 5% (five per cent) of the paid up and subscribed share capital of such Applicant, Member or Associate, as the case may be,) in the bidder or Concessionaire, if any, or its contractor(s) or sub-contractor(s) is less than 5% (five per cent) of the paid up and subscribed share capital of such Concessionaire or its contractor(s) or sub-contractor(s); provided further that this disqualification shall not apply to ownership by a bank, insurance company, pension fund or a Public Financial Institution referred to in sub-section (72) of section 2 of the Companies Act, 2013. For the purposes of this sub-clause (h), indirect shareholding shall be computed in accordance with the provisions of sub-clause (a) above.

For purposes of this RFP, Associate means, in relation to the Applicant, a person who controls, is controlled by, or is under the common control with such Applicant (the “**Associate**”). As used in this definition, the expression “control” means, with respect to a person which is a company or corporation, the ownership, directly or indirectly, of more than 50% (fifty per cent) of the voting shares of such person, and with respect to a person which is not a company or corporation, the power to direct the management and policies of such person by operation of law or by contract.

* + 1. An Applicant eventually appointed to provide Consultancy for this Project, and its Associates, shall be disqualified from subsequently providing goods or works or services related to the construction and operation of the same Project and any breach of this obligation shall be construed as Conflict of Interest; provided that the restriction herein shall not apply after a period of 5 (five) years from the completion of this assignment or to consulting assignments granted by banks/ lenders at any time; provided further that this restriction shall not apply to consultancy/ advisory services performed for the Authority in continuation of this Consultancy or to any subsequent consultancy/ advisory services performed for the Authority in accordance with the rules of the Authority. For the avoidance of doubt, an entity affiliated with the Consultant shall include a partner in the Consultant’s firm or a person who holds more than 5% (five per cent) of the subscribed and paid up share capital of the Consultant, as the case may be, and any Associate thereof.
	1. Number of Proposals

RFPs have been invited for evaluation ofschemes divided across 10 sectors: (1) Agriculture, Animal Husbandry and Fisheries (2) Women and Child Development (3) Human Resource Development (4) Urban Transformation (5) Rural Development (6) Drinking Water and Sanitation (7) Health (8) Jobs and Skills (9) Water Resource, Environment and Forest (10) Social Inclusion, Law and Order & Justice Delivery.

No Applicant or its Associate shall submit more than one Application per sector/package for the Consultancy. An Applicant applying individually or as an Associate shall not be entitled to submit another application for the same sector/package either individually or as a member of any consortium, as the case may be. An Applicant may submit proposal for more than one sector/package, in which case, the Applicant will submit separate technical and financial bids under the respective RFP for each of such sectors/packages. However, no Applicant shall be selected for more than 5 (five) sectors/packages, of which only 3 (three) may be as Lead Member.

* 1. Cost of Proposal

The Applicants shall be responsible for all of the costs associated with the preparation of their Proposals and their participation in the Selection Process including subsequent negotiation, visits to the Authority etc. The Authority will not be responsible or in any way liable for such costs, regardless of the conduct or outcome of the Selection Process.

* 1. Verification of information

Applicants are encouraged to submit their respective Proposals after verification of the schemes, guidelines etc. within the purview of this RFP and the Applicable Laws and regulations or any other matter considered relevant by them.

* 1. Acknowledgement by Applicant
		1. It shall be deemed that by submitting the Proposal, the Applicant has:
1. made a complete and careful examination of the RFP;
2. received all relevant information requested from the Authority;
3. acknowledged and accepted the risk of inadequacy, error or mistake in the information provided in the RFP or furnished by or on behalf of the Authority or relating to any of the matters referred to in Clause 2.6 above;
4. satisfied itself about all matters, things and information, including matters referred to in Clause 2.6 herein above, necessary and required for submitting an informed Application and performance of all of its obligations thereunder;
5. acknowledged that it does not have a Conflict of Interest; and
6. agreed to be bound by the undertaking provided by it under and in terms hereof.
	* 1. The Authority shall not be liable for any omission, mistake or error on the part of the Applicant in respect of any of the above or on account of any matter or thing arising out of or concerning or relating to RFP or the Selection Process, including any error or mistake therein or in any information or data given by the Authority.
	1. Right to reject any or all Proposals

2.8.1 Notwithstanding anything contained in this RFP, the Authority reserves the right to accept or reject any Proposal and to annul the Selection Process and reject all Proposals, at any time without any liability or any obligation for such acceptance, rejection or annulment, and without assigning any reasons thereof.

2.8.2 Without prejudice to the generality of Clause 2.8.1, the Authority reserves the right to reject any Proposal if:

(a) at any time, a material misrepresentation is made or discovered, or

(b) the Applicant does not provide, within the time specified by the Authority, the supplemental information sought by the Authority for evaluation of the Proposal.

Misrepresentation/ improper response by the Applicant may lead to the disqualification of the Applicant. If the Applicant is the Lead Member of a consortium, then the entire consortium may be disqualified / rejected. If such disqualification / rejection occurs after the Proposals have been opened and the highest-ranking Applicant gets disqualified / rejected, then the Authority reserves the right to consider the next best Applicant, or take any other measure as may be deemed fit in the sole discretion of the Authority, including annulment of the Selection Process.

**B. DOCUMENTS**

* 1. Contents of the RFP

 This RFP comprises the Disclaimer set forth hereinabove, the contents as listed below and will additionally include any Addendum / Amendment issued in accordance with Clause 2.11:

**Request for Proposal**

|  |  |
| --- | --- |
| 1 | Introduction |
| 2 | Instructions to Applicants |
| 3 | Criteria for Evaluation |
| 4 | Fraud and corrupt practices |
| 5 | Pre-Proposal Conference |
| 6 | Miscellaneous |
| **Schedules** |
| 1 | **Terms of Reference** |
| 2 | **Form of Agreement**Annex-1: Terms of ReferenceAnnex-2: Deployment of PersonnelAnnex-3: Estimate of Personnel CostsAnnex-4: Approved Sub-Consultant(s)Annex-5: Cost of ServicesAnnex-6: Payment ScheduleAnnex-7: Bank Guarantee for Performance Security |
| 3 | **Guidance Note on Conflict of Interest** |
| **Appendices** |
|  | **Appendix-I: Technical Proposal** |
|  | Form-1: Letter of Proposal |
|  | Form-2: Particulars of the Applicant |
|  | Form-3: Statement of Legal Capacity |
|  | Form-4: Power of Attorney  |
|  | Form-5: Financial Capacity of Applicant |
|  | Form-6: Particulars of Key Personnel |
|  | Form-7: Proposed Methodology and Work Plan |
|  | Form-8: Abstract of Eligible Assignments of Applicant |
|  | Form-9: Abstract of Eligible Assignments of Key Personnel |
|  | Form-10: Eligible Assignments of Applicant |
|  | Form-11: Eligible Assignments of Key Personnel |
|  | Form-12: Curriculum Vitae (CV) of Key Personnel  |
|  | Form-13: Deployment of Personnel |
|  | Form-14: Survey and Field Investigations |
|  | Form-15: Proposal for Sub-Consultant(s) |
|  | **Appendix–II: Financial Proposal** |
|  | Form-1: Covering Letter  |
|  | Form-2: Financial Proposal |
|  | Form-3: Estimate of Personnel Costs |
|  |  |

* 1. Clarifications
		1. Applicants requiring any clarification on the RFP may send their queries to the Authority in writing by speed post/ courier/ special messenger or by e-mail so as to reach before the date mentioned in the Schedule of Selection Process at Clause 1.8. The envelopes shall clearly bear the following identification:

"Queries concerning RFP for ............ (name of Assignment)"

The Authority shall endeavour to respond to the queries within the period specified therein but not later than 7 (seven) days prior to the Proposal Due Date. The responses will be sent by e-mail. The Authority will post the reply to all such queries on the Official Website without identifying the source of queries.

* + 1. The Authority reserves the right not to respond to any questions or provide any clarifications, in its sole discretion, and nothing in this Clause 2.10 shall be construed as obliging the Authority to respond to any question or to provide any clarification.
	1. Amendment of RFP
		1. At any time prior to the deadline for submission of Proposal, the Authority may, for any reason, whether at its own initiative or in response to clarifications requested by an Applicant, modify the RFP document by the issuance of Addendum/ Amendment and posting it on the Official Website.
		2. All such amendments be posted on the Official Website along with the revised RFP containing the amendments and will be binding on all Applicants.
		3. In order to afford the Applicants a reasonable time for taking an amendment into account, or for any other reason, the Authority may, in its sole discretion, extend the Proposal Due Date[[3]](#footnote-3)$.

**C. PREPARATION AND SUBMISSION OF PROPOSAL**

* 1. Language

The Proposal with all accompanying documents (the “**Documents**”) and all communications in relation to or concerning the Selection Process shall be in English language and strictly on the forms provided in this RFP. No supporting document or printed literature shall be submitted with the Proposal unless specifically asked for and in case any of these Documents is in another language, it must be accompanied by an accurate translation of the relevant passages in English, in which case, for all purposes of interpretation of the Proposal, the translation in English shall prevail.

* 1. Format and signing of Proposal
		1. The Applicant shall provide all the information sought under this RFP. The Authority would evaluate only those Proposals that are received in the specified forms and complete in all respects.
		2. The Applicant shall prepare one original set of the Proposal (together with originals/ copies of Documents required to be submitted along therewith pursuant to this RFP) and clearly marked “ORIGINAL”. In addition, the Applicant shall submit 2 (two) copies of the Proposal, alongwith Documents, marked “COPY”. In the event of any discrepancy between the original and its copies, the original shall prevail.
		3. The Proposal, and its copy, shall be typed or written in indelible ink and signed by the authorised signatory of the Applicant who shall initial each page, in blue ink. In case of printed and published Documents, only the cover shall be initialled. All the alterations, omissions, additions, or any other amendments made to the Proposal shall be initialled by the person(s) signing the Proposal. The Proposals must be properly signed by the authorised representative (the “**Authorised Representative**”) as detailed below:
1. by the proprietor, in case of a proprietary firm; or
2. by a partner, in case of a partnership firm and/or a limited liability partnership; or
3. by a duly authorised person holding the Power of Attorney, in case of a Limited Company or a corporation; or
4. by the Authorised Representative of the Lead Member, in case of consortium.

A copy of the Power of Attorney certified under the hands of a partner or director of the Applicant and notarised by a notary public in the form specified in Appendix-I (Form-4) shall accompany the Proposal.

* + 1. Applicants should note the Proposal Due Date, as specified in Clause 1.8, for submission of Proposals. Except as specifically provided in this RFP, no supplementary material will be entertained by the Authority, and that evaluation will be carried out only on the basis of Documents received by the closing time of Proposal Due Date as specified in Clause 2.17.1. Applicants will ordinarily not be asked to provide additional material information or documents subsequent to the date of submission, and unsolicited material if submitted will be summarily rejected. For the avoidance of doubt, the Authority reserves the right to seek clarifications under and in accordance with the provisions of Clause 2.24.
	1. Technical Proposal
		1. Applicants shall submit the technical proposal in the formats at Appendix-I (the “**Technical Proposal**”).
		2. While submitting the Technical Proposal, the Applicant shall, in particular, ensure that:
1. The Bid Security is provided;
2. all forms are submitted in the prescribed formats and signed by the prescribed signatories;
3. Power of Attorney, if applicable, is executed as per Applicable Laws;
4. CVs of all Professional Personnel have been included;
5. Key Personnel have been proposed only if they meet the Conditions of Eligibility laid down at Clause 2.2.2 (D) of the RFP;
6. no alternative proposal for any Key Personnel is being made and only one CV for each position has been furnished;
7. the CVs have been recently signed and dated in blue ink by the respective Personnel and countersigned by the Applicant. Photocopy or unsigned / countersigned CVs shall be rejected;
8. the CVs shall contain an undertaking from the respective Key Personnel about his/her availability for the duration specified in the RFP;
9. Professional Personnel proposed have good working knowledge of English language;
10. Key Personnel would be available for the period indicated in the TOR;
11. no Key Personnel should have attained the age of 75 (seventy five) years at the time of submitting the proposal; and
12. the proposal is responsive in terms of Clause 2.22.3.
	* 1. Failure to comply with the requirements spelt out in this Clause 2.14 shall make the Proposal liable to be rejected.
		2. If an individual Key Personnel makes a false averment regarding his qualification, experience or other particulars, or his commitment regarding availability for the Project is not fulfilled at any stage after signing of the Agreement, he shall be liable to be debarred for any future assignment of the Authority for a period of 5 (five) years. The award of this Consultancy to the Applicant may also be liable to cancellation in such an event.
		3. The Technical Proposal shall not include any financial information relating to the Financial Proposal.
		4. The proposed team shall be composed of experts and specialists (the “**Professional Personnel**”) in their respective areas of expertise and managerial/support staff (the “**Support Personnel**”) such that the Consultant should be able to complete the Consultancy within the specified time schedule. The Key Personnel specified in Clause 2.1.4 shall be included in the proposed team of Professional Personnel. Other competent and experienced Professional Personnel in the relevant areas of expertise must be added as required for successful completion of this Consultancy. The CV of each such Professional Personnel, if any, should also be submitted in the format at Form-12 of Appendix-I.
		5. An Applicant may, if it considers necessary, propose suitable Sub-Consultants in specific areas of expertise. Credentials of such Sub-Consultants should be submitted in Form-15 of Appendix-I. A Sub-Consultant, however, shall not be a substitute for any Key Personnel.
		6. The Authority reserves the right to verify all statements, information and documents, submitted by the Applicant in response to the RFP. Any such verification or the lack of such verification by the Authority to undertake such verification shall not relieve the Applicant of its obligations or liabilities hereunder nor will it affect any rights of the Authority thereunder.
		7. In case it is found during the evaluation or at any time before signing of the Agreement or after its execution and during the period of subsistence thereof, that one or more of the eligibility conditions have not been met by the Applicant or the Applicant has made material misrepresentation or has given any materially incorrect or false information, the Applicant shall be disqualified forthwith if not yet appointed as the Consultant either by issue of the LOA or entering into of the Agreement, and if the Selected Applicant has already been issued the LOA or has entered into the Agreement, as the case may be, the same shall, notwithstanding anything to the contrary contained therein or in this RFP, be liable to be terminated, by a communication in writing by the Authority without the Authority being liable in any manner whatsoever to the Applicant or Consultant, as the case may be.

In such an event, the Authority shall forfeit and appropriate the Bid Security as mutually agreed pre-estimated compensation and damages payable to the Authority for, *inter alia*, time, cost and effort of the Authority, without prejudice to any other right or remedy that may be available to the Authority.

* 1. Financial Proposal
		1. Applicants shall submit the financial proposal in the formats at Appendix-II (the “**Financial Proposal**”) clearly indicating the total cost of the Consultancy (Item [G] of Form-2 of Appendix-II) in both figures and words, in Indian Rupees, and signed by the Applicant’s Authorised Representative. In the event of any difference between figures and words, the amount indicated in words shall prevail. In the event of a difference between the arithmetic total and the total shown in the Financial Proposal, the lower of the two shall prevail.
		2. While submitting the Financial Proposal, the Applicant shall ensure the following:

(i) All the costs associated with the assignment shall be included in the Financial Proposal. These shall normally cover remuneration for all the Personnel (Resident, in the field, office etc.), accommodation, air fare, equipment, printing of documents, surveys, geo-technical investigations etc. The total amount indicated in the Financial Proposal shall be without any condition attached or subject to any assumption, and shall be final and binding. In case any assumption or condition is indicated in the Financial Proposal, it shall be considered non-responsive and liable to be rejected.

(ii) The Financial Proposal shall take into account all expenses and tax liabilities. For the avoidance of doubt, it is clarified that all taxes shall be deemed to be included in the costs shown under different items of the Financial Proposal. Further, all payments shall be subject to deduction of taxes at source as per Applicable Laws.

(iii) Costs (including break down of costs) shall be expressed in INR.

* 1. Submission of Proposal
		1. The Applicants shall submit the Proposal in hard bound form with all pages numbered serially and by giving an index of submissions. Each page of the submission shall be initialled by the Authorised Representative of the Applicant as per the terms of the RFP. In case the proposal is submitted on the document downloaded from Official Website, the Applicant shall be responsible for its accuracy and correctness as per the version uploaded by the Authority and shall ensure that there are no changes caused in the content of the downloaded document. In case of any discrepancy between the downloaded or photocopied version of the RFP and the original RFP issued by the Authority, the latter shall prevail.
		2. The Proposal will be sealed in an outer envelope which will bear the address of the Authority, RFP Notice number, Consultancy name as indicated at Clauses 1.11.1 and 1.11.3 and the name and address of the Applicant. It shall bear on top, the following:

“Do not open, except in presence of the Authorised Person of the Authority”

If the envelope is not sealed and marked as instructed above, the Authority assumes no responsibility for the misplacement or premature opening of the contents of the Proposal submitted and consequent losses, if any, suffered by the Applicant.

* + 1. The aforesaid outer envelope will contain two separate sealed envelopes, one clearly marked **‘Technical Proposal’** and the other clearly marked **‘Financial Proposal’**. The envelope marked “Technical Proposal” shall contain:
1. Application in the prescribed format (Form-1 of Appendix-I) along with Forms 2 to 15 of Appendix-I and supporting documents; and
2. Bid security
3. as specified in Clause 2.20.1

The envelope marked “Financial Proposal” shall contain the Financial Proposal in the prescribed format (Forms 1, 2 & 3 of Appendix-II).

* + 1. The Technical Proposal and Financial Proposal shall be typed or written in indelible ink and signed by the Authorised Representative of the Applicant. All pages of the original Technical Proposal and Financial Proposal must be numbered and initialled by the person or persons signing the Proposal.
		2. The completed Proposal must be delivered on or before the specified time on Proposal Due Date. Proposals submitted by fax, telex, telegram or e-mail shall not be entertained.
		3. The Proposal shall be made in the Forms specified in this RFP. Any attachment to such Forms must be provided on separate sheets of paper and only information that is directly relevant should be provided. This may include photocopies of the relevant pages of printed documents. No separate documents like printed annual statements, company brochures, copy of contracts etc. will be entertained.
		4. The rates quoted shall be firm throughout the period of performance of the assignment upto and including acceptance of the Consultancy for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector by the Authority and discharge of all obligations of the Consultant under the Agreement.

**2.17 Proposal Due Date**

2.17.1 Proposal should be submitted at or before 11:00 hrs on the Proposal Due Date specified in Clause 1.8 at the address provided in Clause 1.11.1 in the manner and form as detailed in this RFP. A receipt thereof should be obtained from the person specified therein.

2.17.2 The Authority may, in its sole discretion, extend the Proposal Due Date by issuing an Addendum in accordance with Clause 2.11 uniformly for all Applicants.

**2.18 Late Proposals**

 Proposals received by the Authority after the specified time on Proposal Due Date shall not be eligible for consideration and shall be summarily rejected.

**2.19 Modification/ substitution/ withdrawal of Proposals**

2.19.1 The Applicant may modify, substitute, or withdraw its Proposal after submission, provided that written notice of the modification, substitution, or withdrawal is received by the Authority prior to Proposal Due Date. No Proposal shall be modified, substituted, or withdrawn by the Applicant on or after the Proposal Due Date.

2.19.2 The modification, substitution, or withdrawal notice shall be prepared, sealed, marked, and delivered in accordance with Clause 2.16, with the envelopes being additionally marked “MODIFICATION”, “SUBSTITUTION” or “WITHDRAWAL”, as appropriate.

2.19.3 Any alteration / modification in the Proposal or additional information or material supplied subsequent to the Proposal Due Date, unless the same has been expressly sought for by the Authority, shall be disregarded.

**2.20 Bid Security**

2.20.1 The Applicant shall furnish as part of its Proposal, a bid security of Rs. 1,00,000 (one lakh) in the form of a Demand Draft issued by one of the Nationalised/ Scheduled Banks in India in favour of PAO, NITI Aayog payable at New Delhi (the “**Bid Security**”), returnable not later than 30 (thirty) days from PDD except in case of the two highest ranked Applicants as required in Clause 2.25.1. In the event that the first ranked Applicant commences the assignment as required in Clause 2.30, the second ranked Applicant, who has been kept in reserve, shall be returned its Bid Security forthwith, but in no case not later than 120 (one hundred and twenty) days from PDD. The Selected Applicant’s Bid Security shall be returned, upon the Applicant signing the Agreement and completing the Deliverables assigned to it for the first 2 (two) months of the Consultancy in accordance with the provisions thereof.

2.20.2 Any Bid not accompanied by the Bid Security shall be rejected by the Authority as non-responsive.

2.20.3 The Authority shall not be liable to pay any interest on the Bid Security and the same shall be interest free.

2.20.4 The Applicant, by submitting its Application pursuant to this RFP, shall be deemed to have acknowledged that without prejudice to the Authority’s any other right or remedy hereunder or in law or otherwise, the Bid Security shall be forfeited and appropriated by the Authority as the mutually agreed pre-estimated compensation and damage payable to the Authority for, *inter alia*, the time, cost and effort of the Authority in regard to the RFP including the consideration and evaluation of the Proposal under the following conditions:

(a) If an Applicant submits a non-responsive Proposal;

(b) If an Applicant engages in any of the Prohibited Practices specified in Section 4 of this RFP;

(c) If an Applicant withdraws its Proposal during the period of its validity as specified in this RFP and as extended by the Applicant from time to time;

(d) In the case of the Selected Applicant, if the Applicant fails to reconfirm its commitments during negotiations as required vide Clause 2.25.1;

(e) In the case of a Selected Applicant, if the Applicant fails to sign the Agreement or commence the assignment as specified in Clauses 2.29 and 2.30 respectively; or

(f) If the Applicant is found to have a Conflict of Interest as specified in Clause 2.3.

**2.21 Performance Security**

2.21.1 The Applicant, by submitting its Application pursuant to this RFP, shall be deemed to have acknowledged that without prejudice to the Authority’s any other right or remedy hereunder or in law or otherwise, its Performance Security shall be forfeited and appropriated by the Authority as the mutually agreed pre-estimated compensation and damages payable to the Authority for, *inter alia*, the time, cost and effort of the Authority in regard to the RFP, including the consideration and evaluation of the Proposal, under the following conditions:

1. If an Applicant engages in any of the Prohibited Practices specified in Clause 4.1 of this RFP;
2. if the Applicant is found to have a Conflict of Interest as specified in Clause 2.3; and
3. if the Selected Applicant commits a breach of the Agreement.

2.21.2 An amount equal to 10% (ten per cent) of the Agreement Value shall be deemed to be the Performance Security for the purposes of this Clause 2.21, which may be forfeited and appropriated in accordance with the provisions hereof.

**D. EVALUATION PROCESS**

**2.22 Evaluation of Proposals**

2.22.1 The Authority shall open the Proposals at 14:00 hours on the Proposal Due Date, at the place specified in Clause 1.11.1 and in the presence of the Applicants who choose to attend. The envelopes marked “Technical Proposal” shall be opened first. The envelopes marked “Financial Proposal” shall be kept sealed for opening at a later date.

2.22.2 Proposals for which a notice of withdrawal has been submitted in accordance with Clause 2.19 shall not be opened.

2.22.3Prior to evaluation of Proposals, the Authority will determine whether each Proposal is responsive to the requirements of the RFP. The Authority may, in its sole discretion, reject any Proposal that is not responsive hereunder. A Proposal shall be considered responsive only if:

1. the Technical Proposal is received in the form specified at Appendix-I;
2. it is received by the Proposal Due Date including any extension thereof pursuant to Clause 2.17;
3. it is accompanied by the Bid Security as specified in Clause 2.20.1.
4. it is signed, sealed, bound together in hard cover and marked as stipulated in Clauses 2.13 and 2.16;
5. it is accompanied by the Power of Attorney as specified in Clause 2.2.4;
6. it contains all the information (complete in all respects) as requested in the RFP;
7. it does not contain any condition or qualification; and
8. it is not non-responsive in terms hereof.

2.22.4The Authority reserves the right to reject any Proposal which is non-responsive and no request for alteration, modification, substitution or withdrawal shall be entertained by the Authority in respect of such Proposals.

2.22.5 The Authority shall subsequently examine and evaluate Proposals in accordance with the Selection Process specified at Clause 1.6 and the criteria set out in Section 3 of this RFP.

2.22.6After the technical evaluation, the Authority shall prepare a list of pre-qualified and shortlisted Applicants in terms of Clause 3.2 for opening of their Financial Proposals. A date, time and venue will be notified to all Applicants for announcing the result of evaluation and opening of Financial Proposals. Before opening of the Financial Proposals, the list of pre-qualified and shortlisted Applicants along with their Technical Score will be read out. The opening of Financial Proposals shall be done in presence of respective representatives of Applicants who choose to be present. The Authority will not entertain any query or clarification from Applicants who fail to qualify at any stage of the Selection Process. The financial evaluation and final ranking of the Proposals shall be carried out in terms of Clauses 3.3 and 3.4.

2.22.7 Applicants are advised that Selection shall be entirely at the discretion of the Authority. Applicants shall be deemed to have understood and agreed that the Authority shall not be required to provide any explanation or justification in respect of any aspect of the Selection Process or Selection.

2.22.8 Any information contained in the Proposal shall not in any way be construed as binding on the Authority, its agents, successors or assigns, but shall be binding against the Applicant if the Consultancy is subsequently awarded to it.

**2.23 Confidentiality**

Information relating to the examination, clarification, evaluation, and recommendation for the selection of Applicants shall not be disclosed to any person who is not officially concerned with the process or is not a retained professional adviser advising the Authority in relation to matters arising out of, or concerning the Selection Process. The Authority shall treat all information, submitted as part of the Proposal, in confidence and shall require all those who have access to such material to treat the same in confidence. The Authority may not divulge any such information unless it is directed to do so by any statutory entity that has the power under law to require its disclosure or is to enforce or assert any right or privilege of the statutory entity and/or the Authority or as may be required by law or in connection with any legal process.

**2.24 Clarifications**

2.24.1 To facilitate evaluation of Proposals, the Authority may, at its sole discretion, seek clarifications from any Applicant regarding its Proposal. Such clarification(s) shall be provided within the time specified by the Authority for this purpose. Any request for clarification(s) and all clarification(s) in response thereto shall be in writing.

2.24.2 If an Applicant does not provide clarifications sought under Clause 2.24.1 above within the specified time, its Proposal shall be liable to be rejected. In case the Proposal is not rejected, the Authority may proceed to evaluate the Proposal by construing the particulars requiring clarification to the best of its understanding, and the Applicant shall be barred from subsequently questioning such interpretation of the Authority.

**E. APPOINTMENT OF CONSULTANT**

**2.25 Negotiations**

2.25.1 The Selected Applicant may, if necessary, be invited for negotiations. The negotiations shall generally not be for reducing the price of the Proposal, but will be for re-confirming the obligations of the Consultant under this RFP. Issues such as deployment of Key Personnel, understanding of the RFP, methodology and quality of the work plan shall be discussed during negotiations. A Key Personnel who did not score 60% (sixty per cent) marks as required under Clause 3.1.2 shall be replaced by the Applicant with a better candidate to the satisfaction of the Authority. In case the Selected Applicant fails to reconfirm its commitment, the Authority reserves the right to designate the next ranked Applicant as the Selected Applicant and invite it for negotiations.

2.25.2The Authority will examine the CVs of all other Professional Personnel and those not found suitable shall be replaced by the Applicant to the satisfaction of the Authority.

2.25.3The Authority will examine the credentials of all Sub-Consultants proposed for this Consultancy and those not found suitable shall be replaced by the Applicant to the satisfaction of the Authority.

**2.26 Substitution of Key Personnel**

2.26.1 The Authority will not normally consider any request of the Selected Applicant for substitution of Key Personnel as the ranking of the Applicant is based on the evaluation of Key Personnel and any change therein may upset the ranking. Substitution will, however, be permitted if the Key Personnel is not available for reasons of any incapacity or due to health, subject to equally or better qualified and experienced personnel being provided to the satisfaction of the Authority.

2.26.2 The Authority expects all the Key Personnel to be available during implementation of the Agreement. The Authority will not consider substitution of Key Personnel except for reasons of any incapacity or due to health. Such substitution shall ordinarily be limited to one Key Personnel subject to equally or better qualified and experienced personnel being provided to the satisfaction of the Authority. As a condition to such substitution, a sum equal to 20% (twenty per cent) of the remuneration specified for the original Key Personnel shall be deducted from the payments due to the Consultant. In the case of a second substitution hereunder, such deduction shall be 50% (fifty per cent) of the remuneration specified for the original Key Personnel. Any further substitution may lead to disqualification of the Applicant or termination of the Agreement.

2.26.3 Substitution of the Team Leader will not normally be considered and may lead to disqualification of the Applicant or termination of the Agreement.

**2.27 Indemnity**

The Consultant shall, subject to the provisions of the Agreement, indemnify the Authority for an amount not exceeding 3 (three) times the value of the Agreement for any direct loss or damage that is caused due to any deficiency in services.

**2.28 Award of Consultancy**

 After selection, a Letter of Award (the “**LOA**”) shall be issued, in duplicate, by the Authority to the Selected Applicant and the Selected Applicant shall, within 7 (seven) days of the receipt of the LOA, sign and return the duplicate copy of the LOA in acknowledgement thereof. In the event the duplicate copy of the LOA duly signed by the Selected Applicant is not received by the stipulated date, the Authority may, unless it consents to extension of time for submission thereof, appropriate the Bid Security of such Applicant as mutually agreed genuine pre-estimated loss and damage suffered by the Authority on account of failure of the Selected Applicant to acknowledge the LOA, and the next highest ranking Applicant may be considered.

**2.29** **Execution of Agreement**

After acknowledgement of the LOA as aforesaid by the Selected Applicant, it shall execute the Agreement within the period prescribed in Clause 1.8. The Selected Applicant shall not be entitled to seek any deviation in the Agreement.

**2.30 Commencement of assignment**

The Consultant shall commence the Services within 3 (three) days of the date of the Agreement, or such other date as may be mutually agreed. If the Consultant fails to either sign the Agreement as specified in Clause 2.29 or commence the assignment as specified herein, the Authority may invite the second ranked Applicant for negotiations. In such an event, the Bid Security of the first ranked Applicant shall be forfeited and appropriated in accordance with the provisions of Clause 2.20.4.

**2.31 Proprietary data**

Subject to the provisions of Clause 2.23, all documents and other information provided by the Authority or submitted by an Applicant to the Authority shall remain or become the property of the Authority. Applicants and the Consultant, as the case may be, are to treat all information as strictly confidential. The Authority will not return any Proposal or any information related thereto. All information collected, analysed, processed or in whatever manner provided by the Consultant to the Authority in relation to the Consultancy shall be the property of the Authority. The Consultant shall make suitable arrangements for the preservation of data collected during the study, such as filled in schedules, tabulation or working sheets, reports, photographs etc, relating to the Project in electronic form and this shall be shared with the Authority at the time of submission of Final report. The ownership of all such data shall remain with the Authority. All raw data compiled during the study shall be transferred to the authority. No data collected in context of the study may be destroyed or otherwise disposed off or given to any other organization/individual, unless so approved by the Authority.

**3. CRITERIA FOR EVALUATION**

**3.1 Evaluation of Technical Proposals**

3.1.1 In the first stage, the Technical Proposal will be evaluated on the basis of Applicant’s experience, its understanding of TOR, proposed methodology and Work Plan, and the experience of Key Personnel. Only those Applicants whose Technical Proposals get a score of 60 (sixty) marks or more out of100 (one hundred) shall qualify for further consideration, and shall be ranked from highest to the lowest on the basis of their technical score (ST).

3.1.2 Each Key Personnel must score a minimum of 60% (sixty per cent) marks except as provided herein. A Proposal shall be rejected if the Team Leader scores less than 60% (sixty per cent) marks or any two of the remaining Key Personnel score less than 60% (sixty per cent) marks. In case the Selected Applicant has one Key Personnel, other than the Team Leader, who scores less than 60% marks, he would have to be replaced within 2 working days during negotiations, with a better candidate who, in the opinion of the Authority, would score 60% (sixty per cent) or above.

3.1.3 The scoring criteria to be used for evaluation shall be as follows.

|  |  |  |  |
| --- | --- | --- | --- |
| **Item Code** | **Parameter** | **Maximum Marks** | **Criteria** |
| **1.** | **Relevant Experience of the Applicant** | **25** | 30% of the maximum marks shall be awarded for the number of Eligible Assignments undertaken by the Applicant firm. The remaining 70% shall be awarded for: (i) the comparative size and quality of Eligible General and SpecificAssignments; (ii) overall professional income, experience and capacity of the firm.  |
| **2.** | **Proposed Methodology and Work Plan** | **10** | Evaluation will be based on the quality of submissions. |
| **3.** | **Relevant Experience of the Key Personnel** | **65** | 30% of the maximum marks for each Key Personnel shall be awarded for the number of Eligible Assignments the respective Key Personnel has worked on. The remaining 70% shall be awarded forthe comparative size and quality of Eligible Assignments |
| 3(a) | Team Leader  | 20 |  |
| 3(b) | Deputy Team Leader | 15 |  |
| 3(c) | Monitoring and Evaluation Expert | 10 |  |
| 3(d) | Economist | 8 |  |
| 3(e) | Rural Development Sector Lead | 12 |  |
| **Grand Total** | **100** |  |

While awarding marks for the number of Eligible Projects, the Applicant or Key Personnel, as the case may be, that has undertaken the highest number of Eligible Assignments shall be entitled to the maximum score for the respective category and all other competing Applicants or respective Key Personnel, as the case may be, shall be entitled to a proportionate score. No score will be awarded to an Applicant/ Key Personnel for fulfilling the eligibility criteria of a minimum number of Eligible Assignments and only projects exceeding the eligibility criteria shall qualify for scoring. For the avoidance of doubt and by way of illustration, if the minimum number of Eligible Projects for meeting the eligibility criteria is say, 3 (three), then an equivalent number will be ignored for each Applicant/Key Personnel and only the balance remaining will be considered for awarding scores relating to the number of Eligible Assignments on a proportionate basis. However, for assigning scores in respect of the size and quality of Eligible Assignments, all Eligible Assignments of the Applicant/Key Personnel shall be considered.

3.1.4 Eligible Assignments

For the purposes of determining Conditions of Eligibility and for evaluating the Proposals under this RFP, advisory/ consultancy assignments shall be deemed as eligible assignments (the “**Eligible Assignments**”) as follows:

 (i) Advisory/consultancy assignments in India granted by the government, regulatory commission, tribunal, multilateral agencies, statutory authorities, public sector entities etc. in respect of design, implementation, evaluation etc. of government programs shall be deemed as eligible general assignments (the “**Eligible General Assignments**”)

(ii) Evaluation studies involving quantitative and qualitative research, household surveys etc. in India granted by the government, regulatory commission, tribunal, multilateral agencies, statutory authorities, public sector entities etc. in respect of government programs shall be deemed as eligible specific assignments (the **“Eligible Specific Assignments”**)

Provided that the Applicant firm claiming credit for an Eligible General Assignment shall have, prior to PDD, received professional fees of at least Rs. 50 (fifty) lakhs for such assignment, and where credit is being claimed by a Key Personnel, she/he should have completed the relevant assignment prior to PDD.

Provided further that if the Applicant firm is taking credit for an Eligible Specific Assignment, such assignment shall have been completed prior to PDD and the Applicant shall have received professional fees of at least Rs. 20 (twenty) lakhs.

Note: Applicants **cannot**provide the same assignment(s) under both General and Specific assignments mentioned above

**3.2** **Short-listing of Applicants**

Of the Applicants ranked as aforesaid, not more than 5 (five) shall be pre-qualified and short-listed for financial evaluation in the second stage. However, if the number of such pre-qualified Applicants is less than two, the Authority may, in its sole discretion, pre-qualify the Applicant(s) whose technical score is less than 60 (sixty) points even if such Applicant(s) do(es) not qualify in terms of Clause 3.1.2; provided that in such an event, the total number of pre-qualified and short-listed Applicantsshall not exceed two.

**3.3** **Evaluation of Financial Proposal**

3.3.1 In the second stage, the financial evaluation will be carried out as per this Clause 3.3. Each Financial Proposal will be assigned a financial score (SF).

3.3.2 For financial evaluation, the total cost indicated in the Financial Proposal, excluding Additional Costs, will be considered. Additional Costs shall include items specified as such in Form-2 of Appendix-II.

3.3.3 The Authority will determine whether the Financial Proposals are complete, unqualified and unconditional. The cost indicated in the Financial Proposal shall be deemed as final and reflecting the total cost of services. Omissions, if any, in costing any item shall not entitle the firm to be compensated and the liability to fulfil its obligations as per the TOR within the total quoted price shall be that of the Consultant. The lowest Financial Proposal (FM) will be given a financial score (SF) of 100 points. The financial scores of other Proposals will be computed as follows:

SF = 100 x FM/F

(F = amount of Financial Proposal)

* 1. **Combined and final evaluation**

3.4.1 Proposals will finally be ranked according to their combined technical (ST) and financial (SF) scores as follows:

 S = ST x Tw + SF x Fw

Where S is the combined score, and Tw and Fw are weights assigned to Technical Proposal and Financial Proposal, which shall be 0.80 and 0.20 respectively.

 3.4.2 The Selected Applicant shall be the first ranked Applicant (having the highest combined score). The second ranked Applicant shall be kept in reserve and may be invited for negotiations in case the first ranked Applicant withdraws, or fails to comply with the requirements specified in Clauses 2.25, 2.29 and 2.30, as the case may be.

**4. FRAUD AND CORRUPT PRACTICES**

4.1 The Applicants and their respective officers, employees, agents and advisers shall observe the highest standard of ethics during the Selection Process. Notwithstanding anything to the contrary contained in this RFP, the Authority shall reject a Proposal without being liable in any manner whatsoever to the Applicant, if it determines that the Applicant has, directly or indirectly or through an agent, engaged in corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice (collectively the “**Prohibited Practices**”) in the Selection Process. In such an event, the Authority shall, without prejudice to its any other rights or remedies, forfeit and appropriate the Bid Security or Performance Security, as the case may be, as mutually agreed genuine pre-estimated compensation and damages payable to the Authority for, *inter alia*, time, cost and effort of the Authority, in regard to the RFP, including consideration and evaluation of such Applicant’s Proposal.

4.2 Without prejudice to the rights of the Authority under Clause 4.1 hereinabove and the rights and remedies which the Authority may have under the LOA or the Agreement, if an Applicant or Consultant, as the case may be, is found by the Authority to have directly or indirectly or through an agent, engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice during the Selection Process, or after the issue of the LOA or the execution of the Agreement, such Applicant or Consultant shall not be eligible to participate in any tender or RFP issued by the Authority during a period of 2 (two) years from the date such Applicant or Consultant, as the case may be, is found by the Authority to have directly or through an agent, engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice, as the case may be.

4. 3 For the purposes of this Section, the following terms shall have the meaning hereinafter respectively assigned to them:

(a) “**corrupt practice**” means (i) the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence the action of any person connected with the Selection Process (for avoidance of doubt, offering of employment to or employing or engaging in any manner whatsoever, directly or indirectly, any official of the Authority who is or has been associated in any manner, directly or indirectly with the Selection Process or the LOA or has dealt with matters concerning the Agreement or arising therefrom, before or after the execution thereof, at any time prior to the expiry of one year from the date such official resigns or retires from or otherwise ceases to be in the service of the Authority, shall be deemed to constitute influencing the actions of a person connected with the Selection Process); or (ii) save as provided herein, engaging in any manner whatsoever, whether during the Selection Process or after the issue of the LOA or after the execution of the Agreement, as the case may be, any person in respect of any matter relating to the Project or the LOA or the Agreement, who at any time has been or is a legal, financial or technical consultant/ adviser of the Authority in relation to any matter concerning the Project;

(b) “**fraudulent practice**” means a misrepresentation or omission of facts or disclosure of incomplete facts, in order to influence the Selection Process;

(c) “**coercive practice**” means impairing or harming or threatening to impair or harm, directly or indirectly, any persons or property to influence any person’s participation or action in the Selection Process;

(d) “**undesirable practice**” means (i) establishing contact with any person connected with or employed or engaged by the Authority with the objective of canvassing, lobbying or in any manner influencing or attempting to influence the Selection Process; or (ii) having a Conflict of Interest; and

(e) “**restrictive practice**” means forming a cartel or arriving at any understanding or arrangement among Applicants with the objective of restricting or manipulating a full and fair competition in the Selection Process.

**5. PRE-PROPOSAL CONFERENCE**

5.1 Pre-Proposal Conference of the Applicants shall be convened at the designated date, time and place. Only those Applicants, who have downloaded the RFP document from the Official Website of the Authority, shall be allowed to participate in the Pre-Proposal Conference. A maximum of two representatives of each Applicant shall be allowed to participate on production of an authority letter from the Applicant.

5.2 During the course of Pre-Proposal Conference, the Applicants will be free to seek clarifications and make suggestions for consideration of the Authority. The Authority shall endeavour to provide clarifications and such further information as it may, in its sole discretion, consider appropriate for facilitating a fair, transparent and competitive Selection Process.

**6. MISCELLANEOUS**

6.1 The Selection Process shall be governed by, and construed in accordance with, the laws of India and the Courts in the State in which the Authority has its headquarters shall have exclusive jurisdiction over all disputes arising under, pursuant to and/or in connection with the Selection Process.

6.2 The Authority, in its sole discretion and without incurring any obligation or liability, reserves the right, at any time, to:

(a) suspend and/or cancel the Selection Process and/or amend and/or supplement the Selection Process or modify the dates or other terms and conditions relating thereto;

(b) consult with any Applicant in order to receive clarification or further information;

(c) retain any information and/or evidence submitted to the Authority by, on behalf of and/or in relation to any Applicant; and/or

(d) independently verify, disqualify, reject and/or accept any and all submissions or other information and/or evidence submitted by or on behalf of any Applicant.

6.3 It shall be deemed that by submitting the Proposal, the Applicant agrees and releases the Authority, its employees, agents and advisers, irrevocably, unconditionally, fully and finally from any and all liability for claims, losses, damages, costs, expenses or liabilities in any way related to or arising from the exercise of any rights and/or performance of any obligations hereunder, pursuant hereto and/or in connection herewith and waives any and all rights and/or claims it may have in this respect, whether actual or contingent, whether present or future.

6.4 All documents and other information supplied by the Authority or submitted by an Applicant shall remain or become, as the case may be, the property of the Authority. The Authority will not return any submissions made hereunder. Applicants are required to treat all such documents and information as strictly confidential.

6.5 The Authority reserves the right to make inquiries with any of the clients listed by the Applicants in their previous experience record.

**SCHEDULES**

SCHEDULE–1

 *(See Clause 1.1.3)*

Consultancy for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector

Terms of Reference (TOR)

for

TECHNICAL CONSULTANT

|  |
| --- |
| **Contents** |
| **1. Background of the Sector****2. Objectives of the Evaluation Study****3. Approach**1. **Scope of Services**

**5. Primary Data Collection Methodology****6. Listing of Stakeholders to be Consulted****7. Time Schedule** **8. Deliverables and Timelines****9. Payment Schedule****10. Indicative Structure of the Final Evaluation Report****11. Support from NITI Aayog****12. Reporting****13. Meetings****14. Miscellaneous** |
|  |
|  |

**Terms Of Reference (TOR) For Consultancy for Evaluation of Centrally Sponsored Schemes in Package 5 – Rural Development**

1. **Background of the Sector**

India is predominantly a rural country with two third population and 70% workforce residing in rural areas. Rural economy constitutes 46 per cent of national income. Despite the rise of urbanisation more than half of India’s population is projected to be rural by 2050[[4]](#footnote-4). Thus growth and development of rural economy and population is a key to overall growth and inclusive development of the country. The Government of India along with the various State and Local Governments is implementing several flagship rural Missions.To achieve sustainable and inclusive growth of rural India through a multipronged strategy for eradication of poverty by increasing livelihoods opportunities, providing social safety net, promoting sustainable ecosystems of development (Natural Resource Management) and developing infrastructure for growth. Thereby, improving quality of life in rural India and to bridge the rural urban divide, aiming in the process, to reach out to vulnerable sections of the rural society.

India has a commitment to effectively implement Sustainable Development Agenda 2030.[[5]](#footnote-5) Rural development through its various programmes is intrinsically linked with many SDGs like Goal 1: End poverty in all its forms everywhere; Goal 5: Achieve gender equality and empower all women and girls; Goal 8: Promote sustained, inclusive and sustainable Economic growth, full and productive employment and decent work for all; Goal 9: Build resilient infrastructure, promote inclusive and sustainable industrialization and foster innovation; Goal 10: Reduce inequality within and among countries and Goal 12: Ensure Sustainable consumption and Production patterns.

Further, policy direction for rural development has been enunciated in Strategy for New India[[6]](#footnote-6) with overarching objectives for sustainable ecosystem, to increase rural income, and to create integrated value chain system.

**Appendix IV (A)** provides a list of various Umbrella programmes and CSS schemes contributing to the sector and their outlays in tabular format.

1. **Pradhan Mantri Gram Sadak Yojana (PMGSY):** Under PMGSY, total Length of road works completed is 5,83,568.2 km while 1,50,266 Habitations has been connected.
2. **Pradhan Mantri Awas Yojana-Gramin (PMAY-G):** 96.22 lakh houses have been sanctioned of which 77.15 lakh houses have been reported to be completed, against a target of 1.5 crore houses in rural areas.
3. **National Social Assistance Programme (NSAP):** The programme covers 3.21 crore beneficiaries which include about 2.40 crore old age pensioners, 69.96 lakh widow pensioners and 10.30 lakh pensioners with disability.
4. **Shyama Prasad Mukherjee Rurban Mission**: In total 300 clusters have been identified, out of which 295 has been approved. While, 226 Integrated Cluster Action Plan (ICAPs) have been prepared. Total amount of Rs 5551.66 crore CGF for the development of these clusters has been approved.
5. **National Rural Livelihood Mission (NRLM):** Under this mission 51.9 lakh SHGs have been promoted. 591.7 lakh of households have been mobilized into SHGs. 11.01 lakh of SHGs have been provided Community Investment Fund (CIF).
6. **Mahatma Gandhi National Rural Employment Guarantee Program (MGNREGA):** During 2018-19, 5.27 Crore households benefited while 267.78 person-days have been generated and 87.32 assets has been created.

The CSS schemes of the Rural Development Sector are being implemented through a tiered structure, comprising of Central Ministries/Departments/Agencies, State level Agencies, District and Block level Project Management units, Panchayati Raj Institutions (PRI), village level institutions (Gram Sabha, committees) and the groups/beneficiaries at the scheme level.

Implementation issues and challenges[[7]](#footnote-7) [[8]](#footnote-8) include majorly the following:

1. The sustainability challenge[[9]](#footnote-9)with regards to core institutions and assets created under the various programme heads.
2. The process adherence and suitability of the processes for achieving the desired outcome poses an issue under various schemes.
3. The inclusion challenge with regards to households/beneficiaries.
4. Effectiveness and Efficiency of the program (social, behavioural, financial, resource use, human resources).
5. Democratically driven feedback and course correction in the implementation of the programme.

Over the past few years a few evaluation studies have been undertaken to examine the efficacy of schemes as follows:

* Impact Assessment of PMGSY by CMI Social Research Centre in 2009-10 and also by Indian Institute of Management Ahmedabad on Outcome Monitoring Study, 2017
* Impact ofPradhan Mantri Awaas Yojana -Gramin (PMAY-G) on income and employment by National Institute of Public Finance and Policy in 2018.
* Evaluation of Indira Gandhi National Old Age Pension Scheme (NSAP: IGNOAPS) in Kerala conducted by Centre for Rural Management (CRM) Kottayam, Kerala during 2012.
* Independent Assessment of Design, Strategies, and Impacts of DAY-NRLM by Institute of Rural Management Anand in 2017.
* Rapid Assessment of Natural Resource Management Component Under MGNREGA and its impact on Sustainable Livelihoods by Institute of Economic Growth, Delhi during 2017.

These studies have provided insights with respect to implementation and performance of specific schemes only. Also, the sectoral level studies undertaken so far have focussed on agri and non-agri aspects and not on the Rural Development discourse in totality. Therefore, there is a need for a comprehensive study to evaluate, map and analyse the various government interventions (Programmes/Flagship schemes) in terms of design, implementation and overall outcome for the rural development sector as a whole. A sector level analysis will also be crucial in identifying and analysing the gaps in the sector. The sectoral evaluation period for this study will be 2015-16 to 2018-19.

1. **Objectives of the Evaluation Study**
	1. **Sectoral analysis:**
		1. To **assess the status of the Rural Development sector performance** in the country in terms of Asset creation (Physical assets like roads and social assets like Self Help Groups), Increase in household income through various support programmes (MGNREGA, NRLM, RURBAN etc.), achieving sustainable infrastructure and assets, promoting the ease of living with Housing, Connectivity, Convergence and Alleviating poverty in terms of social protection system, income generation etc. and other intended development outcomes. To study the aspects of increase in Economic activity at the village level (Farm and Non-farm, also cluster based activity under RURBAN, MGNREGA etc.). To establish convergence of various programme heads and suggest changes for the same at the village level. To assess the programmes in cross cutting themes listed in the Section 3c.
		2. To qualitatively and quantitatively **map the intended and actual contribution** of Umbrella schemes and each CSS scheme to assess the performance of Rural Development Sector on the key outcomes:
* Eradication of Poverty ( social protection system, income generation)
* Sustainable ecosystem (asset creation, social infrastructure, community behaviour)
* Quality of Life (livelihood promotion, connectivity, rural infrastructure, mobility, creation of a home (with all basic amenities), economic activity
	1. **Umbrella and Scheme level analysis:**
		1. To assess the Umbrella schemes and each CSS scheme on the Relevance, Effectiveness, Efficiency, Sustainability, Impact (REESI)[[10]](#footnote-10)and Equity framework.
		2. To assess the Umbrella schemes and each CSS scheme on various cross-sectional themes as elaborated in the next section, as well as unintended consequences/negative externalities of programme implementation. Existing mechanisms such as environmental and social safeguards within the scheme design to mitigate these risks may be assessed as well.
	2. **To identify and highlight scalable best practices** and home-grown innovations, if any, create case studies for further dissemination
	3. **Programme Harmonization:**
		1. To **provide recommendations** based on the synthesis of sectoral and scheme-level analysis, on the need to continue the schemes in their existing form, modify, scale-up, scale-down or close down the schemes
		2. To suggest revisions in the scheme/schemes design for the effective implementation in future, if modification is recommended
1. **Approach**
	1. The **sectoral analysis** will be driven by the meta-analysis of secondary data, and validated through the primary data collection.
		1. **Gaps in the broad sectoral outcomes** where national priorities/SDGs are not being addressed either due to absence of interventions or non-performance of existing schemes/interventions. For gap analysis, new schemes and initiatives announced in 2019-20 may also be considered.
		2. **Convergence** of the scheme, both intended and actual, to other developmental programmes of the Central and the State Governments as well as with private sector, Corporate Social Responsibility (CSR) efforts, international multilateral and bilateral aid, etc.
	2. The **Umbrella and scheme-level analysis** will be based on triangulation of primary and secondary data, as outlined in the methodology. It will include an assessment of the relevance, effectiveness, efficiency, equity and sustainability of the Umbrella schemes and CSS schemes. Details on this framework are available in the Guidelines for Evaluation placed at Appendix IV. In line with this understanding, the following aspects will have to be assessed as a part of the analysis:
		1. **Input use efficiency** of various CSS schemes i.e. institutional mechanism, fund flow (adequacy & timeliness) & utilization through public expenditure tracking, policy guidelines and human resources allocated for the implementation of the schemes at central, state, district, block, and village, mechanisms to identify and reward best practices within the scheme design as well as M&E systems
		2. **Coverage** of the various schemes in terms of eligible target beneficiaries, services, geographies etc. and analyse the reasons for non-coverage, if applicable.
		3. **Key bottlenecks/issues & challenges** in the **implementation mechanism** like governance mechanism, capacity constraints at state, district & block & below block level i.e. both technical and administrative, supporting stakeholder & community engagement, timeliness, regularities, stakeholder conflict of interest, IEC, on-ground coordination with other programmes /departments and issues in the bottom-up district-level planning and in monitoring and evaluationsof various development schemes.
		4. **Quality of assets created/services provided** under the schemes and see how far these assets/services benefited the end beneficiaries.
		5. **Convergence** within and across Umbrella schemes and CSS schemes, and **gaps in sectoral outcomes** (as in the sectoral approach).

For scheme-specific analysis and preparation of Appendix 2 of the Final Evaluation Report (as specified in para 10 of this TOR), the scheme-specific areas of inquiry in Appendix IV (E-J) of this RFP should also be taken into consideration.

* 1. **Cross-sectional Thematic Assessment**

The cross-sectional themes based on which the Umbrella scheme and each CSS scheme will be assessed may include:

* + 1. Accountability and transparency
		2. Direct/indirect employment generation
		3. Gender mainstreaming
		4. Climate change & sustainability
		5. Role of Tribal Sub-Plan (TSP) and Scheduled Caste Sub-Plan component of the scheme in mainstreaming of Tribal and Scheduled Caste population
		6. Use of IT/Technology in driving efficiency
		7. Stakeholder & beneficiary behavioural change
		8. Research and Development
		9. Unlocking synergies with other government programmes
		10. Reforms & regulations
		11. Impact on and role of private sector, community and civil society/NGOs in the scheme.
	1. **Prioritization of Schemes:**
		1. For prioritization of schemes for evaluation, **two parameters** are to be taken into consideration: (i) duration of implementation, and (ii) budget allocation.
		2. Based on **duration of implementation**, schemes can be classified into two categories: (a) those introduced prior to 14th Finance Commission cycle; and (b) those that were introduced during the 14th Finance Commission cycle. Schemes that were launched prior to 14th Finance Commission cycle (prior to 2015-16) are more amenable to full scale evaluation. For those schemes that are introduced during the 14th Finance Commission cycle (between 2015-16 to 2019-20), one needs to be cognizant that new schemes need time to be introduced, take off,  and stabilize, and generally have to face a number of initiation challenges. This means, most of the schemes introduced in the 14th Finance Commission cycle have had only few years of full implementation, and therefore for these schemes a mid-term evaluation may be more relevant. Additionally, there are a few schemes that have been launched recently, in 2018-19, which can be categorized as ‘new’ schemes, for which a limited assessment of their progress till date could be conducted by the Consultant.
		3. Schemes can also be classified based on the **budget outlay**. Of the 126 total schemes, 18 large schemes take up 80% of the CSS outlay, while 80 odd smaller schemes take up just 5%. Schemes with budget outlay less than Rs 3,000 crores cumulatively over five years (2015-16 to 2019-20) need to be particularly carefully evaluated from the perspective of Report of the Sub-Group of Chief Ministers on Rationalisation of Centrally Sponsored Schemes, 2015. Within these 80 small schemes, there are certain schemes that have zero budget allocations during 1-4 years of the evaluation period. The selected Consultant may confer with the concerned Ministry/Department the status of these schemes, and conduct a short analysis for the schemes that are proposed to be closed.
		4. In addition, there are certain schemes as MGNREGA which are empowered through **specific acts of legislation**. Assuming that these schemes will continue, evaluation of these legislatively-backed schemes should focus on input and process insights for improving the outcomes and impact of these schemes.
1. **Scope of Services**
	1. Reference period of the study: The sectoral evaluation will be for the period from 2015-16 to 2018-19.
	2. Based on meta-analysis and key informant interviews, and community and household surveys, the evaluation study will provide insights into reasons for success and failure of program design, institutional arrangements, human resources, political economy considerations, among others. The study will also provide strategic insights into:
* Sector gaps both due to lack of specific interventions and failure or poor outcomes of existing schemes;
* Institutional and human resource failures and best practices;
* Institutional provisions for monitoring and evaluation;
* Degree of adoption of outcome-output framework;
* Adoption of technology for effective program implementation;
* Political economy constraints and program design constraints/provisions; among others.
	1. The analysis of sectoral performance and Umbrella programmes’ contribution to this performance will primarily be based on meta-analysis whereas the individual CSS scheme-wise analysis will be based on the field study as well as scheme-wise secondary data analysis. The findings of scheme-wise analysis will feed into the broader Umbrella programme & sectoral findings through a synthesis of this sectoral and scheme-wise approaches.
	2. **Meta-Analysis:** The meta-analysis will involve review of
1. National and International development goals and sector documents;
2. Financial data on allocation and expenditures of the schemes;
3. Annual reports of the ministries for output and outcome assessment;
4. Available evaluation reports for output and outcomes assessment;
5. Annual progress reports and implementation documents to assess the institutional arrangements;
6. Available evaluation reports done at the district and state level;
7. Evaluations done by non-government agencies.

An indicative list of key documents to be referred to by the consultant is placed at **Appendix IV (C)**.

* 1. **The field study** would also include the following:
1. Designing of the discussions guides for focus group discussions, interview guides for in-depth interviews and structured questionnaires/schedules for household surveys.
2. Preparation of the analysis plan
3. Pre-testing and finalising the required tools in partnership with DMEO team.
4. Establishment of a managerial structure for field operations
5. Recruitment of investigators and training/capacity building of the field investigators.
6. Putting in place appropriate IT hardware and application software for data collection and management.
7. Collecting and compiling the quality data from selected areas.
8. High quality data management and adherence to quality assurance mechanisms as per agreed protocols, plans and schedules.
9. Collation and data cleaning
10. Running data analysis and submitting cross-tabulations/summarizations.
11. Preparation of draft evaluation report and conducting stakeholder consultations
12. Submission of final report and dissemination of the key findings
13. Incorporating concurrent feedback into the workflow.

During meta-analysis and field study, inputs from the concerned ministry/department may be incorporated for fine tuning the methodology, preparation of analysis plan, listing of secondary data sources, investigator training and tool/questionnaire design.

1. **Primary Data Collection Methodology**
	1. A quantitative and qualitative study backed with extensive meta-analysis will be conducted to provide a sectoral assessment. The study will consist of following components:
2. Key Informant Interviews & Focus Group Discussions - Herein, it is proposed that key informant interviews be held with officials from central ministries/departments, state-level implementing bodies and district and block level adminstration. Other stakeholders supporting implementation or indirectly involved in enabling the scheme’s success, as well as opinion makers at the village levelshould also be interviewed. National level key informants should also include experts from recognized national level think tanks, institutions and prominent non-profit organizations.

Additionally, focus group discussions will be conducted, mostly at block and village level with diverse groups involving implementing stakeholders, opinion makers as well as selected beneficiaries.

1. Household Surveys - A selected sample of household surveys shall be conducted to assess the beneficiary-level perspective of the programmes.

Since, various CSS schemes have different target groups, it is to be ensured that the sample and geography selection for Key Informant Interviews/household surveys factors in representation from each of the respective target groups/geographies.

Additionally, the key information areas to be covered in the discussion guides/questionnaires for key informant interviews and household surveys should cover data points included but not limited to NITI Aayog’s Output-Outcome Monitoring Framework for corresponding schemes. This is further detailed in **Appendix IV (D)** of the RFP.

* 1. **Sampling**

The sample design for a household survey must be stratified in such a way that the sample actually selected is spread over geographic sub-areas and population sub-groups properly. The size of the sample must take account of competing needs so that costs and precision are optimally balanced. Given all India nature of the CSS scheme implementation, the sampling methodology will involve multi-stage, stratified and clustered features. In view of the sector level evaluation, the household surveys will have a general-purpose in scope, covering multiple topics of interest to the government. The sample plan must make use of clusters of households in order to keep costs to a manageable level but at the same time it must avoid being overly clustered. Keeping in view time frame and other factors, a non-probability judgmental and/or convenience sampling will be followed. The sample size can be based on a comparatively small proportion of the target population focused on several subjects. The survey managers may decide to base the sample size on being able to measure reliably, a characteristic held by certain percent of the population dependent upon budget considerations.

An indicative sampling framework and minimum sample sizes for costing purposes is as follows:

Entire country can be divided into 6 geographical zones i.e. (i) North & Central, (ii) South, (iii) East, (iv) West, (v) North-East and (vi) Northern Hilly states.

Zone-wise list of states are mentioned in the table below:

|  |  |  |
| --- | --- | --- |
| Sr No. | Zone | States / UTs |
| 1 | North & Central | Chandigarh, Chhattisgarh, Delhi, Haryana, Madhya Pradesh, Punjab, Uttar Pradesh |
| 2 | South | Andhra Pradesh, Karnataka, Kerala, Lakshadweep, Puducherry, [Tamil Nad](https://www.mapsofindia.com/tamilnadu/)u, Telangana |
| 3 | East | Andaman & Nicobar Islands, Bihar, Jharkhand, Orissa, [West Beng](https://www.mapsofindia.com/west-bengal/)al |
| 4 | West | Dadra & Nagar Haveli, Daman & Diu, Goa, Gujarat, Maharashtra, [Rajasthan](https://www.mapsofindia.com/rajasthan/) |
| 5 | North East | Arunachal Pradesh , Assam, Manipur, Meghalaya, Mizoram, Nagaland, Sikkim, Tripura |
| 6 | Northern Hilly States | Himachal Pradesh, Jammu & Kashmir, Uttarakhand |

A minimum of 11 States and 1 Union Territory are to be selected, of which each zone must be represented by at least one State. The State/UT selection criteria is to be proposed by the Consultant as a part of the Methodology and Work Plan in Appendix I Form 7. Subsequently, within each selected state, all the districts will be classified into 2 to 3 strata based on key sectoral performance/index and a district will be selected from each strata; thereby taking the total no. of districts selected to around 30-35. In a similar way, 2 villages per block will be selected in each district using stratified sampling. Selection of a state, district or village in each strata can be based on either systematic random or probability proportional to size sample selection technique. Within each village, about 10 households will be selected which will cover eligible beneficiaries of one or more CSS covered in the sector. In case of UTs, a minimum of 1 district with 3-4 villages should be selected and a minimum of 10 households from each village should be covered. Also, it should be ensured that Left Wing Extremism-affected (LWE) areas, aspirational districts and island areas are not inadvertently left out, if relevant.

However, it is important to note that these numbers are indicative and it is proposed that the Consultant may suggest their methodology best suited to meet the objectives of the evaluation. However, a minimum of about 800 key informant interviews, about 150 focus group discussions and about 1500 household interviews should be conducted as a part of the field study.

* 1. Details of the Evaluation Framework & Guidelines are included in **Appendix IV(L)** of the RFP.
	2. **Mechanisms to ensure Data Quality**

A multi-pronged robust process for quality control needs to be followed during data collection. The following aspects need to considered:

1. The field investigators to be engaged for conducting the household study & key informant interviews/FGDs should have at least 3 years of experience in conducting similar surveys/interviews. 2-step training (classroom and then on-the-field training) should be conducted for all field investigators.
2. It is recommended that pilots should be conducted on at least 2% of the sample size for both Key Informant Interviews as well as Household surveys to fine tune the inquiry tools. A brief on the learnings from such a pilot exercise and subsequent improvements in the tools/questionnaires should also be shared with NITI Aayog.
3. 100% data collected should be validated using a validation checklist. Missing data points should be recollected.
4. In case of household survey, at least 50% data should also be telephonically verified and if not verified via phone, back checks should be undertaken to ensure at least 50% data verification.
5. Use of mobile-based, near real-time and geo-tagged data collection and validation tools should be done to ensure efficiency and accuracy in data collection. Access to tools and data should be provided to the Authority
6. **Listing of stakeholders to be consulted**

A detailed list of stakeholders to be interacted with during the key informant interviews, FGDs, institutional household surveys is placed at **Appendix IV(B)**.

1. **Time Schedule**

The schedule will be as follows:

| **S No** | **Activity** | **Deadline** |
| --- | --- | --- |
| 1 | Release of RFP | 6thMay 2019 |
| 2 | Last date for receiving queries/requests for clarifications | 16th May 2019 |
| 3 | Pre-Proposal Conference | 20thMay 2019 |
| 4 | Final date for submission of bids | 4thJune 2019 |
| 5 | Award of contract | 19thJune 2019 |

1. **Deliverables & Timelines**
2. Inception report with final scope, methodology and approach. This should also include findings from the meta-analysis and therefore the areas which will be further explored during field visits.
3. Mid-term report with initial findings of the study.
4. Draft evaluation report for stakeholder consultations.
5. Final Evaluation Report after incorporation of inputs from all the concerned stakeholders.

All the reports are required to be submitted in hard copy in triplicate and in soft copy. In addition to the reports, for further analysis in future, verifiable raw data in soft copy should also be shared with NITI Aayog. This will include detailed transcriptions of key informant interviews and focus group discussions as well as raw data from household surveys in MS Excel/CSV format.

Timelines for the above deliverables would be as follows:

| **Sr. No** | **Activity** | **Deadline** |
| --- | --- | --- |
| 1 | Award of contract | T |
| 2 | Inception report | T+15 days |
| 3 | Finalization of inception report based on comments by NITI Aayog | T+17 days |
| 4 | Mid-term report | T+45 days |
| 5 | Sign-off on the mid-term report based on comments by NITI Aayog | T+48 days |
| 6 | Draft evaluation report | T+85 days |
| 7 | Comments on draft evaluation report by NITI Aayog | T+92 days |
| 8 | Sign-off on the Final Evaluation Report | T+100 days |

1. **Payment Schedule**

The payment schedule linked to the specified deliverables above is given below:

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Date No.** | **Description of Deliverables** | **Week No.** | **Payment** |
| KD1 | Inception report approved by Authority | 3 | 20% |
| KD2 | Mid-term report approved by Authority | 7 | 30% |
| KD3 | Draft evaluation report | 13 | 30% |
| KD4 | Final Evaluation Report approved by Authority | 14 | 20% |
|  | **Total** |  | **100%** |

$Excludes the time taken by the Authority in providing its comments on the Draft evaluation report. The Consultant shall get one week for submission of the Final Evaluation Report after comments of the Authority are provided.

1. **Indicative Structure of the Final Evaluation Report[[11]](#footnote-11):**
2. **Executive Summary**
3. **Introduction**
4. **Background to the Study**
	1. Objectives of the Study
	2. Scope of the Study
	3. Structure of Report
5. **Approach and Methodology**
	1. Overall Approach
	2. Meta-analysis Methodology
	3. Field Study Methodology
		1. Qualitative
			1. Stakeholder & geographical coverage
			2. Tools
		2. Quantitative
			1. Sampling - Geographical coverage & respondent profile
			2. Sample size
			3. Sample selection
			4. Tools
	4. Limitations of the Study
6. **Sector-level Analysis**

(*This section will be a synthesis of the findings from the meta-analysis and the field study. This should draw from the literature/desk review of evaluations studies, government reports, academic literature etc., as well as the granular Umbrella CSS and CSS level analysis.)*

* 1. Background of the Sector

*(This should include public/private structures and stakeholders; government interventions – State and Centre; trends, key drivers and dynamics within the sector, the sector’s contribution to the economy and job creation, and levels of social inclusion in the sector etc.)*

* 1. Performance of the Sector

*(This should include sectoral performance on key metrics including the cross-sectional themes*[[12]](#footnote-12) *and performance against global benchmarks; the intended and actual performance of the government sector; contribution of Umbrella CSS, CSS, State, CS schemes and other noteworthy multilateral interventions etc. to sectoral outcomes)*

* 1. Issues & Challenges

*(This should outline what the key gaps and bottlenecks in the sector are and why they continue to exist. This will include a root cause analysis, implementation challenges, policy/structural challenges, negative externalities etc.)*

* 1. Recommendations and Solutions

*(These should be provided based on the pillars of Relevance, Effectiveness, Efficiency, Equity, Sustainability and Impact at Sectoral level, and should also correspond to the issues and challenges as identified above.)*

* + 1. Policy interventions including the cross-sectional themes
		2. Legislative framework
		3. Others
1. **Umbrella CSS-level Analysis**

(*This section will be a synthesis of the findings from the meta-analysis and the field study. This should draw from the literature/desk review of evaluations studies, government reports, academic literature etc., as well as the granular CSS level analysis. There should be one chapter on each Umbrella CSS.)*

* 1. Background of the Umbrella CSS

*(This should include the origins, history and evolution of the Umbrella scheme; its objectives, structures and stakeholders; details of schemes under the Umbrella; intended contribution to sectoral performance and national and international goals etc.)*

* 1. Performance of the Umbrella CSS

*(This should include performance on key metrics including the Output-Outcome Framework and cross-sectional themes; the actual vs intended contribution of Umbrella programmes to sectoral performance, etc.)*

* 1. Issues & Challenges

*(This should outline what the key gaps and bottlenecks in the UCSS are and why they continue to exist. This will include a root cause analysis, implementation challenges, structural challenges, negative externalities etc. The aspects to be covered will include: governance, institutional mechanisms, convergence with other schemes and programmes, fund flow efficiency and utilization, capacity-building and M&E systems)*

* 1. Recommendations and Solutions

*(These should be provided based on the pillars of Relevance, Effectiveness, Efficiency, Equity, Sustainability and Impact at Umbrella CSS level, and should also correspond to the issues and challenges as identified above. The interventions should include modifications/deletions/additions required in the Umbrella CSS to fill sectoral gaps. Recommendations should be provided separately across the cross-sectional themes)*

1. **Conclusions**
	1. Summary of sectoral level issues & challenges
	2. Sector Way Forward
2. **References & Appendices**
	1. Appendix 1 - Details of Key Informant Interviews and Household Survey
		1. Appendix 1a – Details of Key Informant Interviews

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sr. No. | Concerned Umbrella CSS | Scheme | Date of Interaction | Name & Designation of the key informant interviewed |
|  |  |  |  |  |

* + 1. Appendix 1b – Details of Household Surveys

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sr. No. | State | District | Beneficiary type | Number of samples covered |
|  |  |  |  |  |

* 1. Appendix 2 - Format for CSS scheme-level analysis[[13]](#footnote-13)
		1. Scheme-level Analysis

(*This section will be a synthesis of the findings from the meta-analysis and the field study. This should draw from the literature/desk review of evaluations studies, government reports, academic literature etc., as well as the granular CSS level analysis.* *There should be one section on each scheme.)*

* + - 1. Background of the scheme

*(This should include the origins, history and evolution of the scheme; its objectives, implementation structures and stakeholders; intended contribution to sectoral performance and national and international goals etc.)*

* + - 1. Performance of the scheme

*(This should include performance on key metrics including the Output-Outcome Framework and cross-sectional themes; the actual vs. intended contribution of schemes to sectoral performance, etc.)*

* + - 1. Issues & Challenges

*(This should outline what the key gaps and bottlenecks in the scheme are and why they continue to exist. This will include a root cause analysis, implementation challenges, structural challenges, negative externalities etc. The aspects to be covered will include: governance, institutional mechanisms, convergence with other schemes and programmes, fund flow efficiency and utilization, capacity-building and M&E systems)*

* + - 1. Recommendations and Solutions

*(These should be provided based on the pillars of Relevance, Effectiveness, Efficiency, Equity, Sustainability and Impact at CSS level, and should also correspond to the issues and challenges as identified above. The interventions should include modifications/deletions/additions required in the CSS to fill sectoral gaps. Recommendations should be provided separately across the cross-sectional themes)*

* 1. Appendix 3 - Case Studies

The case studies should be identified using the criteria of effectiveness, efficiency, relevance, ethical soundness, scalability, sustainability and partner & community engagement and political commitment[[14]](#footnote-14). Kindly refer to the Chapter 1, 2 and 3 of the WHO Guidelines mentioned in the footnote for identifying and documenting best practices.

It is to be ensured that the Final Evaluation Report submitted is in the proper format, well-designed and readable.

1. **Support from NITI Aayog**
2. A detailed list of scheme-specific information required for better contextual understanding of the Consultant is given in Appendix IV of the RFP.
3. An authority letter will be provided to the Consutant to accord the necessary permissions for accessing the requisite stakeholders.
4. **Reporting**
	* + 1. The Consultant will work closely with the Authority. The Authority has established a Working Group (the “**WG**”) to enable conduct of this assignment. A designated Project Director of the Authority will be responsible for the overall coordination and project development. He will play a coordinating role in dissemination of the Consultant’s outputs, facilitating discussions, and ensuring required reactions and responses to the Consultant.
			2. The Consultant may prepare Issue Papers highlighting issues that could become critical for the timely completion of the Project and that require attention from the Authority.
			3. The Consultant will make a presentation on the inception report, mid-term report and draft evaluation report for discussion with the WG at a meeting. This will be a working document. The Consultant is required to prepare and submit a weekly update that includes and describes, inter alia, general progress to date; data and reports obtained and reviewed, conclusions to date, if any; concerns about availability of, or access to, data, analyses, reports; questions regarding the TOR or any other matters regarding work scope and related issues; and so on. The Consultants’ work on the TOR tasks should continue while the report is under consideration and is being discussed.
			4. Regular communication with the WG and the Project Director is required in addition to all key communications. This may take the form of telephone/ teleconferencing, emails, faxes, and occasional meetings.
			5. The Deliverables will be submitted as per schedule provided in this RFP.
			6. **Meetings**

The Authority may review with the Consultant, any or all of the documents and advice forming part of the Consultancy, in meetings and conferences which will be held at the Authority’s office. The expenses towards attending such meetings during the period of Consultancy, including travel costs and per diem, shall be reimbursed in accordance with the Financial Proposal contained in Form–2 of Appendix-II of the RFP. The days required to be spent at the office of the Authority shall be computed at the rate of 8 (eight) man hours a day in case of an outstation Consultant. For a Consultant having its office within or near the city where the Authority’s office is situated, the time spent during meetings at the Authority’s office shall be calculated as per actuals. No travel time shall be payable.

* + - 1. **Miscellaneous**
			2. The Consultant shall have/establish an office in Delhi/NCR, for efficient and coordinated performance of its Services. All the Key Personnel shall be deployed at this office during the first 16 (sixteen) weeks as specified in the Manning Schedule forming part of the Agreement. The authorised officials of the Authority may visit the Consultant’s Project Office or field locations any time during office hours for inspection and interaction with the Consultant’s Personnel. It is not expected of the Consultant to carry out the operations from the Head/Home Office.
			3. The Consultant shall mobilise and demobilise its Professional Personnel and Support Personnel with the concurrence of the Authority and shall maintain the time sheet/ attendance sheet of the working of all Personnel in the Project Office. These time sheets/ attendance sheets shall be made available to the Authority as and when asked for and a copy of such record shall be submitted to the Authority at the end of each calendar month.
			4. All the study outputs including primary data shall be compiled, classified and submitted by the Consultant to the Authority in soft form apart from the reports indicated in the Deliverables (Paragraph 4). The study outputs shall remain the property of the Authority and shall not be used for any purpose other than that intended under these Terms of Reference without the permission of the Authority. The Consultancy shall stand completed on acceptance by the Authority of all the Deliverables of the Consultant and execution of the Agreement or 52 (fifty two) weeks from the Effective Date, whichever is earlier. The Authority shall issue a certificate to that effect. The Consultancy shall in any case be deemed to be completed upon expiry of 1 (one) year from the Effective Date, unless extended by mutual consent of the Authority and the Consultant.

SCHEDULE–2

*(See Clause 2.1.3)*

# **AGREEMENT**

**FOR**

Consultancy for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector

|  |
| --- |
| **CONTENTS** |
|  **1. General** 1.1 Definitions and Interpretation 1.2 Relation between the Parties 1.3 Rights and Obligations 1.4 Governing law and jurisdiction 1.5 Language 1.6 Table of contents and headings 1.7 Notices1.8 Location 1.9 Authority of Member-in-Charge 1.10 Authorised representatives 1.11 Taxes and duties **2. Commencement**, **Completion and Termination** **of Agreement**  2.1 Effectiveness of Agreement  2.2 Commencement of Services  2.3 Termination of Agreement for failure to commence Services  2.4 Expiry of Agreement * 1. Entire Agreement
	2. Modification of Agreement

 2.7 Force Majeure * 1. Suspension of Agreement

 2.9 Termination of Agreement  **3. Obligations of the Consultant**  3.1 General  3.2 Conflict of Interest 3.3 Confidentiality  3.4 Liability of the Consultant  3.5 Insurance to be taken out by the Consultant  3.6 Accounting, inspection and auditing  3.7 Consultant’s actions requiring the Authority’s prior approval  3.8 Reporting obligations  3.9 Documents prepared by the Consultant to be the property of the Authority 3.10 Equipment and materials furnished by the Authority3.11 Providing access to the Project Office and Personnel 3.12 Accuracy of Documents**4. Consultant’s Personnel and Sub-Consultant**  4.1 General  4.2 Deployment of Personnel  4.3 Approval of Personnel  4.4 Substitution of Key Personnel  4.5 Working hours, overtime, leave etc.  4.6 Resident Team Leader and Project Manager  4.7. Sub-Consultants **5. Obligations of the Authority**  5.1 Assistance in clearances etc.  5.2 Access to land and property  5.3 Change in Applicable Law  5.4 Payment  **6. Payment to the Consultant**  6.1 Cost estimates and Agreement Value  6.2 Currency of payment  6.3 Mode of billing and payment **7. Liquidated damages and penalties**7.1 Performance Security7.2 Liquidated Damages7.3 Penalty for deficiency in Services**8. Fairness and Good Faith**  8.1 Good Faith  8.2 Operation of the Agreement **9. Settlement of Disputes** 9.1 Amicable settlement 9.2 Dispute resolution9.3 Conciliation9.4 Arbitration**ANNEXES**  Annex-1: Terms of Reference Annex-2: Deployment of Personnel Annex-3: Estimate of Personnel Costs Annex-4: Approved Sub-Consultant(s)Annex-5: Cost of ServicesAnnex-6: Payment Schedule Annex-7: Bank Guarantee for Performance Security |

**AGREEMENT**

**Consultancy for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector**

This AGREEMENT (hereinafter called the “**Agreement**”) is made on the ...........………. day of the month of ………… 20…, between, on the one hand, the President of India acting through Development Monitoring & Evaluation Office (hereinafter called the “**Authority**” which expression shall include their respective successors and permitted assigns, unless the context otherwise requires) and, on the other hand, …………………………………. (hereinafter called the “**Consultant**” which expression shall include their respective successors and permitted assigns).

WHEREAS

(A) The Authority vide its Request for Proposal for Consultancy for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector(hereinafter called the “**Consultancy**”) for the ……………….. Project (hereinafter called the “**Project**”);

(B) the Consultant submitted its proposals for the aforesaid work, whereby the Consultant represented to the Authority that it had the required professional skills, and in the said proposals the Consultant also agreed to provide the Services to the Authority on the terms and conditions as set forth in the RFP and this Agreement; and

(C) the Authority, on acceptance of the aforesaid proposals of the Consultant, awarded the Consultancy to the Consultant vide its Letter of Award dated .................. (the “**LOA**”); and

(D) in pursuance of the LOA, the parties have agreed to enter into this Agreement.

NOW, THEREFORE, the parties hereto hereby agree as follows:

**1. GENERAL**

* 1. **Definitions and Interpretation**

1.1.1 The words and expressions beginning with capital letters and defined in this Agreement shall, unless the context otherwise requires, have the meaning hereinafter respectively assigned to them:

1. “**Additional Costs**” shall have the meaning set forth in Clause 6.1.2;
2. “**Agreement**” means this Agreement, together with all the Annexes;
3. “**Agreement Value**” shall have the meaning set forth in Clause 6.1.2;
4. “**Applicable Laws**” means the laws and any other instruments having the force of law in India as they may be issued and in force from time to time;
5. “**Confidential Information**” shall have the meaning set forth in Clause 3.3;
6. “**Conflict of Interest**” shall have the meaning set forth in Clause 3.2 read with the provisions of RFP;
7. “**Dispute**” shall have the meaning set forth in Clause 9.2.1;
8. “**Effective Date**” means the date on which this Agreement comes into force and effect pursuant to Clause 2.1;
9. “**Government**” means the Government of .............;
10. “**INR**, **Re**. or **Rs**.” means Indian Rupees;

(l) “**Member**”, in case the Consultant consists of a joint venture or consortium of more than one entity, means any of these entities, and “Members” means all of these entities;

(m) “**Party**” means the Authority or the Consultant, as the case may be, and Parties means both of them;

(n) “**Personnel**” means persons hired by the Consultant or by any Sub-Consultant as employees and assigned to the performance of the Services or any part thereof;

 (o) “**Resident Personnel**” means such persons who at the time of being so hired had their domicile inside India;

(p) “**RFP**” means the Request for Proposal document in response to which the Consultant’s proposal for providing Services was accepted;

(q) “**Services**” means the work to be performed by the Consultant pursuant to this Agreement, as described in the Terms of Reference hereto;

(r) “**Sub-Consultant**” means any entity to which the Consultant subcontracts any part of the Services in accordance with the provisions of Clause 4.7; and

(s) “**Third Party**” means any person or entity other than the Government, the Authority, the Consultant or a Sub-Consultant.

 All terms and words not defined herein shall, unless the context otherwise requires, have the meaning assigned to them in the RFP.

1.1.2 The following documents along with all addenda issued thereto shall be deemed to form and be read and construed as integral parts of this Agreement and in case of any contradiction between or among them the priority in which a document would prevail over another would be as laid down below beginning from the highest priority to the lowest priority:

1. Agreement;
2. Annexes of Agreement;
3. RFP; and

(d) Letter of Award.

* 1. **Relation between the Parties**

Nothing contained herein shall be construed as establishing a relation of master and servant or of agent and principal as between the Authority and the Consultant. The Consultant shall, subject to this Agreement, have complete charge of Personnel performing the Services and shall be fully responsible for the Services performed by them or on their behalf hereunder.

**1.3** **Rights and obligations**

The mutual rights and obligations of the Authority and the Consultant shall be as set forth in the Agreement, in particular:

(a) the Consultant shall carry out the Services in accordance with the provisions of the Agreement; and

(b) the Authority shall make payments to the Consultant in accordance with the provisions of the Agreement.

**1.4 Governing law and jurisdiction**

## This Agreement shall be construed and interpreted in accordance with and governed by the laws of India, and the courts in the State in which the Authority has its headquarters shall have exclusive jurisdiction over matters arising out of or relating to this Agreement.

**1.5** **Language**

## All notices required to be given by one Party to the other Party and all other communications, documentation and proceedings which are in any way relevant to this Agreement shall be in writing and in English language.

**1.6Table of contents andheadings**

The table of contents, headings or sub-headings in this Agreement are for convenience of reference only and shall not be used in, and shall not affect, the construction or interpretation of this Agreement.

**1.7 Notices**

## Any notice or other communication to be given by any Party to the other Party under or in connection with the matters contemplated by this Agreement shall be in writing and shall:

(a) in the case of the Consultant, be given by e-mail and by letter delivered by hand to the address given and marked for attention of the Consultant’s Representative set out below in Clause 1.10 or to such other person as the Consultant may from time to time designate by notice to the Authority; provided that notices or other communications to be given to an address outside the city specified in Sub-clause (b) below may, if they are subsequently confirmed by sending a copy thereof by registered acknowledgement due, air mail or by courier, be sent by e-mail to the number as the Consultant may from time to time specify by notice to the Authority;

(b) in the case of the Authority, be given by e-mail and by letter delivered by hand and be addressed to the Authority with a copy delivered to the Authority Representative set out below in Clause 1.10 or to such other person as the Authority may from time to time designate by notice to the Consultant; provided that if the Consultant does not have an office in the same city as the Authority’s office, it may send such notice by e-mail and by registered acknowledgement due, air mail or by courier; and

(c) any notice or communication by a Party to the other Party, given in accordance herewith, shall be deemed to have been delivered when in the normal course of post it ought to have been delivered and in all other cases, it shall be deemed to have been delivered on the actual date and time of delivery; provided that in the case of e-mail, it shall be deemed to have been delivered on the working days following the date of its delivery.

**1.8 Location**

The Services shall be performed at the site of the Project in accordance with the provisions of RFP and at such locations as are incidental thereto, including the offices of the Consultant.

**1.9 Authority of Member-in-charge**

In case the Consultant consists of a consortium of more than one entity, the Parties agree that the Lead Member shall act on behalf of the Members in exercising all the Consultant’s rights and obligations towards the Authority under this Agreement, including without limitation the receiving of instructions and payments from the Authority.

**1.10 Authorised Representatives**

1.10.1 Any action required or permitted to be taken, and any document required or permitted to be executed, under this Agreement by the Authority or the Consultant, as the case may be, may be taken or executed by the officials specified in this Clause 1.10.

1.10.2 The Authority may, from time to time, designate one of its officials as the Authority Representative. Unless otherwise notified, the Authority Representative shall be:

..........

..........

Tel: ..........

Mobile: ..........

Email: ..........

1.10.3 The Consultant may designate one of its employees as Consultant’s Representative. Unless otherwise notified, the Consultant’s Representative shall be:

..........

..........

Tel: ..........

Mobile: ..........

Email: ..........

**1.11 Taxes and duties**

Unless otherwise specified in the Agreement, the Consultant shall pay all such taxes, duties, fees and other impositions as may be levied under the Applicable Laws and the Authority shall perform such duties in regard to the deduction of such taxes as may be lawfully imposed on it.

**2.** **COMMENCEMENT, COMPLETION AND TERMINATION OF AGREEMENT**

* 1. **Effectiveness of Agreement**

This Agreement shall come into force and effect on the date of this Agreement (the “**Effective Date**”).

* 1. **Commencement of Services**

The Consultant shall commence the Services within a period of 3 (three) days from the Effective Date, unless otherwise agreed by the Parties.

* 1. **Termination of Agreement for failure to commence Services**

If the Consultant does not commence the Services within the period specified in Clause 2.2 above, the Authority may, by not less than 2 (two) weeks’ notice to the Consultant, declare this Agreement to be null and void, and in the event of such a declaration, the Bid Security of the Consultant shall stand forfeited.

* 1. **Expiry of Agreement**

 Unless terminated earlier pursuant to Clauses 2.3 or 2.9 hereof, this Agreement shall, unless extended by the Parties by mutual consent, expire upon the earlier of (i) expiry of a period of 90 (ninety) days after the delivery of the final deliverable to the Authority; and (ii) the expiry of 1 (one) year from the Effective Date. Upon Termination, the Authority shall make payments of all amounts due to the Consultant hereunder.

* 1. **Entire Agreement**
		1. This Agreement and the Annexes together constitute a complete and exclusive statement of the terms of the agreement between the Parties on the subject hereof, and no amendment or modification hereto shall be valid and effective unless such modification or amendment is agreed to in writing by the Parties and duly executed by persons especially empowered in this behalf by the respective Parties. All prior written or oral understandings, offers or other communications of every kind pertaining to this Agreement are abrogated and withdrawn; provided, however, that the obligations of the Consultant arising out of the provisions of the RFP shall continue to subsist and shall be deemed to form part of this Agreement.
		2. Without prejudice to the generality of the provisions of Clause 2.5.1, on matters not covered by this Agreement, the provisions of RFP shall apply.
	2. **Modification of Agreement**

Modification of the terms and conditions of this Agreement, including any modification of the scope of the Services, may only be made by written agreement between the Parties. Pursuant to Clauses 4.2.3 and 6.1.3 hereof, however, each Party shall give due consideration to any proposals for modification made by the other Party.

* 1. **Force Majeure**

2.7.1 Definition

1. For the purposes of this Agreement, “**Force Majeure**” means an event which is beyond the reasonable control of a Party, and which makes a Party’s performance of its obligations hereunder impossible or so impractical as reasonably to be considered impossible in the circumstances, and includes, but is not limited to, war, riots, civil disorder, earthquake, fire, explosion, storm, flood or other adverse weather conditions, strikes, lockouts or other industrial action (except where such strikes, lockouts or other industrial action are within the power of the Party invoking Force Majeure to prevent), confiscation or any other action by government agencies.
2. Force Majeure shall not include (i) any event which is caused by the negligence or intentional action of a Party or such Party’s Sub-Consultant or agents or employees, nor (ii) any event which a diligent Party could reasonably have been expected to both (A) take into account at the time of the conclusion of this Agreement, and (B) avoid or overcome in the carrying out of its obligations hereunder.

(c) Force Majeure shall not include insufficiency of funds or failure to make any payment required hereunder.

* + 1. No breach of Agreement

The failure of a Party to fulfil any of its obligations hereunder shall not be considered to be a breach of, or default under, this Agreement insofar as such inability arises from an event of Force Majeure, provided that the Party affected by such an event has taken all reasonable precautions, due care and reasonable alternative measures, all with the objective of carrying out the terms and conditions of this Agreement.

* + 1. Measures to be taken
1. A Party affected by an event of Force Majeure shall take all reasonable measures to remove such Party’s inability to fulfil its obligations hereunder with a minimum of delay.
2. A Party affected by an event of Force Majeure shall notify the other Party of such event as soon as possible, and in any event not later than 14 (fourteen) days following the occurrence of such event, providing evidence of the nature and cause of such event, and shall similarly give notice of the restoration of normal conditions as soon as possible.
3. The Parties shall take all reasonable measures to minimise the consequences of any event of Force Majeure.
	* 1. Extension of time

Any period within which a Party shall, pursuant to this Agreement, complete any action or task, shall be extended for a period equal to the time during which such Party was unable to perform such action as a result of Force Majeure.

* + 1. Payments

During the period of its inability to perform the Services as a result of an event of Force Majeure, the Consultant shall be entitled to be reimbursed for Additional Costs reasonably and necessarily incurred by it during such period for the purposes of the Services and in reactivating the Services after the end of such period.

* + 1. Consultation

Not later than 30 (thirty) days after the Consultant has, as the result of an event of Force Majeure, become unable to perform a material portion of the Services, the Parties shall consult with each other with a view to agreeing on appropriate measures to be taken in the circumstances.

**2.8 Suspension of Agreement**

The Authority may, by written notice of suspension to the Consultant, suspend all payments to the Consultant hereunder if the Consultant shall be in breach of this Agreement or shall fail to perform any of its obligations under this Agreement, including the carrying out of the Services; provided that such notice of suspension (i) shall specify the nature of the breach or failure, and (ii) shall provide an opportunity to the Consultant to remedy such breach or failure within a period not exceeding 30 (thirty) days after receipt by the Consultant of such notice of suspension.

* 1. **Termination of Agreement**
		1. By the Authority

The Authority may, by not less than 30 (thirty) days’ written notice of termination to the Consultant, such notice to be given after the occurrence of any of the events specified in this Clause 2.9.1, terminate this Agreement if:

(a) the Consultant fails to remedy any breach hereof or any failure in the performance of its obligations hereunder, as specified in a notice of suspension pursuant to Clause 2.8 hereinabove, within 30 (thirty) days of receipt of such notice of suspension or within such further period as the Authority may have subsequently granted in writing;

(b) the Consultant becomes insolvent or bankrupt or enters into any agreement with its creditors for relief of debt or take advantage of any law for the benefit of debtors or goes into liquidation or receivership whether compulsory or voluntary;

(c) the Consultant fails to comply with any final decision reached as a result of arbitration proceedings pursuant to Clause 9 hereof;

(d) the Consultant submits to the Authority a statement which has a material effect on the rights, obligations or interests of the Authority and which the Consultant knows to be false;

(e) any document, information, data or statement submitted by the Consultant in its Proposals, based on which the Consultant was considered eligible or successful, is found to be false, incorrect or misleading;

(f) as the result of Force Majeure, the Consultant is unable to perform a material portion of the Services for a period of not less than 60 (sixty) days; or

(g) the Authority, in its sole discretion and for any reason whatsoever, decides to terminate this Agreement.

2.9.2 By the Consultant

The Consultant may, by not less than 30 (thirty) days’ written notice to the Authority, such notice to be given after the occurrence of any of the events specified in this Clause 2.9.2, terminate this Agreement if:

* 1. the Authority fails to pay any money due to the Consultant pursuant to this Agreement and not subject to dispute pursuant to Clause 9 hereof within 45 (forty five) days after receiving written notice from the Consultant that such payment is overdue;
	2. the Authority is in material breach of its obligations pursuant to this Agreement and has not remedied the same within 45 (forty five) days (or such longer period as the Consultant may have subsequently granted in writing) following the receipt by the Authority of the Consultant’s notice specifying such breach;
	3. as the result of Force Majeure, the Consultant is unable to perform a material portion of the Services for a period of not less than 60 (sixty) days; or
	4. the Authority fails to comply with any final decision reached as a result of arbitration pursuant to Clause 9 hereof.

2.9.3 Cessation of rights and obligations

Upon termination of this Agreement pursuant to Clauses 2.3 or 2.9 hereof, or upon expiration of this Agreement pursuant to Clause 2.4 hereof, all rights and obligations of the Parties hereunder shall cease, except (i) such rights and obligations as may have accrued on the date of termination or expiration, or which expressly survive such Termination; (ii) the obligation of confidentiality set forth in Clause 3.3 hereof; (iii) the Consultant’s obligation to permit inspection, copying and auditing of such of its accounts and records set forth in Clause 3.6, as relate to the Consultant’s Services provided under this Agreement; and (iv) any right or remedy which a Party may have under this Agreement or the Applicable Law.

2.9.4 Cessation of Services

Upon termination of this Agreement by notice of either Party to the other pursuant to Clauses 2.9.1 or 2.9.2 hereof, the Consultant shall, immediately upon dispatch or receipt of such notice, take all necessary steps to bring the Services to a close in a prompt and orderly manner and shall make every reasonable effort to keep expenditures for this purpose to a minimum. With respect to documents prepared by the Consultant and equipment and materials furnished by the Authority, the Consultant shall proceed as provided respectively by Clauses 3.9 or 3.10 hereof.

2.9.5 Payment upon Termination

Upon termination of this Agreement pursuant to Clauses 2.9.1 or 2.9.2 hereof, the Authority shall make the following payments to the Consultant (after offsetting against these payments any amount that may be due from the Consultant to the Authority):

(i) remuneration pursuant to Clause 6 hereof for Services satisfactorily performed prior to the date of termination;

(ii) reimbursable expenditures pursuant to Clause 6 hereof for expenditures actually incurred prior to the date of termination; and

(iii) except in the case of termination pursuant to sub-clauses (a) through (e) of Clause 2.9.1 hereof, reimbursement of any reasonable cost incidental to the prompt and orderly termination of the Agreement including the cost of the return travel of the Consultant’s personnel.

 2.9.6Disputes about Events of Termination

If either Party disputes whether an event specified in Clause 2.9.1 or in Clause 2.9.2 hereof has occurred, such Party may, within 30 (thirty) days after receipt of notice of termination from the other Party, refer the matter to arbitration pursuant to Clause 9 hereof, and this Agreement shall not be terminated on account of such event except in accordance with the terms of any resulting arbitral award.

1. **OBLIGATIONS OF THE CONSULTANT**
	1. **General**

3.1.1 Standards of Performance

The Consultant shall perform the Services and carry out its obligations hereunder with all due diligence, efficiency and economy, in accordance with generally accepted professional techniques and practices, and shall observe sound management practices, and employ appropriate advanced technology and safe and effective equipment, machinery, materials and methods. The Consultant shall always act, in respect of any matter relating to this Agreement or to the Services, as a faithful adviser to the Authority, and shall at all times support and safeguard the Authority's legitimate interests in any dealings with Sub-Consultants or Third Parties.

* + 1. Terms of Reference

The scope of services to be performed by the Consultant is specified in the Terms of Reference (the “**TOR**”) at Annex-1 of this Agreement. The Consultant shall provide the Deliverables specified therein in conformity with the time schedule stated therein.

3.1.3Applicable Laws

The Consultant shall perform the Services in accordance with the Applicable Laws and shall take all practicable steps to ensure that any Sub-Consultant, as well as the Personnel and agents of the Consultant and any Sub-Consultant, comply with the Applicable Laws.

**3.2** **Conflict of Interest**

3.2.1 The Consultant shall not have a Conflict of Interest and any breach hereof shall constitute a breach of the Agreement.

3.2.2 Consultant and Affiliates not to be otherwise interested in the Project

The Consultant agrees that, during the term of this Agreement and after its termination, the Consultant or any Associate thereof and any entity affiliated with the Consultant, as well as any Sub-Consultant and any entity affiliated with such Sub-Consultant, shall be disqualified from providing goods, works, services, loans or equity for any project resulting from or closely related to the Services and any breach of this obligation shall amount to a Conflict of Interest; provided that the restriction herein shall not apply after a period of five years from the completion of this assignment or to consulting assignments granted by banks/ lenders at any time; provided further that this restriction shall not apply to consultancy/ advisory services provided to the Authority in continuation of this Consultancy or to any subsequent consultancy/ advisory services provided to the Authority in accordance with the rules of the Authority. For the avoidance of doubt, an entity affiliated with the Consultant shall include a partner in the Consultant’s firm or a person who holds more than 5% (five per cent) of the subscribed and paid up share capital of the Consultant, as the case may be, and any Associate thereof.

3.2.3 Prohibition of conflicting activities

Neither the Consultant nor its Sub-Consultant nor the Personnel of either of them shall engage, either directly or indirectly, in any of the following activities:

1. during the term of this Agreement, any business or professional activities which would conflict with the activities assigned to them under this Agreement;
2. after the termination of this Agreement, such other activities as may be specified in the Agreement; or
3. at any time, such other activities as have been specified in the RFP as Conflict of Interest.

3.2.4 Consultant not to benefit from commissions, discounts, etc.

The remuneration of the Consultant pursuant to Clause 6 hereof shall constitute the Consultant’s sole remuneration in connection with this Agreement or the Services and the Consultant shall not accept for its own benefit any trade commission, discount or similar payment in connection with activities pursuant to this Agreement or to the Services or in the discharge of its obligations hereunder, and the Consultant shall use its best efforts to ensure that any Sub-Consultant, as well as the Personnel and agents of either of them, similarly shall not receive any such additional remuneration.

3.2.5 The Consultant and its Personnel shall observe the highest standards of ethics and shall not have engaged in and shall not hereafter engage in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice (collectively the “**Prohibited Practices**”**).** Notwithstanding anything to the contrary contained in this Agreement, the Authority shall be entitled to terminate this Agreement forthwith by a communication in writing to the Consultant, without being liable in any manner whatsoever to the Consultant, if it determines that the Consultant has, directly or indirectly or through an agent, engaged in any Prohibited Practices in the Selection Process or before or after entering into of this Agreement. In such an event, the Authority shall forfeit and appropriate the performance security, if any, as mutually agreed genuine pre-estimated compensation and damages payable to the Authority towards, *inter alia*, the time, cost and effort of the Authority, without prejudice to the Authority’s any other rights or remedy hereunder or in law.

3.2.6 Without prejudice to the rights of the Authority under Clause 3.2.5 above and the other rights and remedies which the Authority may have under this Agreement, if the Consultant is found by the Authority to have directly or indirectly or through an agent, engaged or indulged in any Prohibited Practices, during the Selection Process or before or after the execution of this Agreement, the Consultant shall not be eligible to participate in any tender or RFP issued during a period of 2 (two) years from the date the Consultant is found by the Authority to have directly or indirectly or through an agent, engaged or indulged in any Prohibited Practices.

3.2.7 For the purposes of Clauses 3.2.5 and 3.2.6, the following terms shall have the meaning hereinafter respectively assigned to them:

(a) “**corrupt practice**” means (i) the offering, giving, receiving or soliciting, directly or indirectly, of anything of value to influence the actions of any person connected with the Selection Process (for removal of doubt, offering of employment or employing or engaging in any manner whatsoever, directly or indirectly, any official of the Authority who is or has been associated in any manner, directly or indirectly with Selection Process or LOA or dealing with matters concerning the Agreement before or after the execution thereof, at any time prior to the expiry of one year from the date such official resigns or retires from or otherwise ceases to be in the service of the Authority, shall be deemed to constitute influencing the actions of a person connected with the Selection Process); or (ii) engaging in any manner whatsoever, whether during the Selection Process or after the issue of LOA or after the execution of the Agreement, as the case may be, any person in respect of any matter relating to the Project or the LOA or the Agreement, who at any time has been or is a legal, financial or technical adviser the Authority in relation to any matter concerning the Project;

(b) “**fraudulent practice**” means a misrepresentation or omission of facts or suppression of facts or disclosure of incomplete facts, in order to influence the Selection Process;

(c) “**coercive practice**” means impairing or harming, or threatening to impair or harm, directly or indirectly, any person or property to influence any person’s participation or action in the Selection Process or the exercise of its rights or performance of its obligations by the Authority under this Agreement;

(d) “**undesirable practice**” means (i) establishing contact with any person connected with or employed or engaged by the Authority with the objective of canvassing, lobbying or in any manner influencing or attempting to influence the Selection Process; or (ii) having a Conflict of Interest; and

(e) “**restrictive practice**” means forming a cartel or arriving at any understanding or arrangement among Applicants with the objective of restricting or manipulating a full and fair competition in the Selection Process.

**3.3 Confidentiality**

The Consultant, its Sub-Consultants and the Personnel of either of them shall not, either during the term or within two years after the expiration or termination of this Agreement disclose any proprietary information, including information relating to reports, data, drawings, design software or other material, whether written or oral, in electronic or magnetic format, and the contents thereof; and any reports, digests or summaries created or derived from any of the foregoing that is provided by the Authority to the Consultant, its Sub-Consultants and the Personnel; any information provided by or relating to the Authority, its technology, technical processes, business affairs or finances or any information relating to the Authority’s employees, officers or other professionals or suppliers, customers, or contractors of the Authority; and any other information which the Consultant is under an obligation to keep confidential in relation to the Project, the Services or this Agreement ("**Confidential Information**"), without the prior written consent of the Authority.

Notwithstanding the aforesaid, the Consultant, its Sub-Consultants and the Personnel of either of them may disclose Confidential Information to the extent that such Confidential Information:

(i) was in the public domain prior to its delivery to the Consultant, its Sub-Consultants and the Personnel of either of them or becomes a part of the public knowledge from a source other than the Consultant, its Sub-Consultants and the Personnel of either of them;

(ii) was obtained from a third party with no known duty to maintain its confidentiality;

(iii) is required to be disclosed by Applicable Laws or judicial or administrative or arbitral process or by any governmental instrumentalities, provided that for any such disclosure, the Consultant, its Sub-Consultants and the Personnel of either of them shall give the Authority, prompt written notice, and use reasonable efforts to ensure that such disclosure is accorded confidential treatment; and

(iv) is provided to the professional advisers, agents, auditors or representatives of the Consultant or its Sub-Consultants or Personnel of either of them, as is reasonable under the circumstances; provided, however, that the Consultant or its Sub-Consultants or Personnel of either of them, as the case may be, shall require their professional advisers, agents, auditors or its representatives, to undertake in writing to keep such Confidential Information, confidential and shall use its best efforts to ensure compliance with such undertaking.

**3.4** **Liability of the Consultant**

3.4.1 The Consultant’s liability under this Agreement shall be determined by the Applicable Laws and the provisions hereof.

3.4.2 The Consultant shall, subject to the limitation specified in Clause 3.4.3, be liable to the Authority for any direct loss or damage accrued or likely to accrue due to deficiency in Services rendered by it.

3.4.3 The Parties hereto agree that in case of negligence or wilful misconduct on the part of the Consultant or on the part of any person or firm acting on behalf of the Consultant in carrying out the Services, the Consultant, with respect to damage caused to the Authority’s property, shall not be liable to the Authority:

(i) for any indirect or consequential loss or damage; and

(ii) for any direct loss or damage that exceeds (a) the Agreement Value set forth in Clause 6.1.2 of this Agreement, or (b) the proceeds the Consultant may be entitled to receive from any insurance maintained by the Consultant to cover such a liability in accordance with Clause 3.5.2, whichever of (a) or (b) is higher.

3.4.4 This limitation of liability specified in Clause 3.4.3 shall not affect the Consultant’s liability, if any, for damage to Third Parties caused by the Consultant or any person or firm acting on behalf of the Consultant in carrying out the Services subject, however, to a limit equal to 3 (three) times the Agreement Value.

**3.5** **Insurance to be taken out by the Consultant**

3.5.1 (a) The Consultant shall, for the duration of this Agreement, take out and maintain, and shall cause any Sub-Consultant to take out and maintain, at its (or the Sub-Consultant’s, as the case may be) own cost, but on terms and conditions approved by the Authority, insurance against the risks, and for the coverages, as specified in the Agreement and in accordance with good industry practice.

(b) Within 15 (fifteen) days of receiving any insurance policy certificate in respect of insurances required to be obtained and maintained under this clause, the Consultant shall furnish to the Authority, copies of such policy certificates, copies of the insurance policies and evidence that the insurance premia have been paid in respect of such insurance. No insurance shall be cancelled, modified or allowed to expire or lapse during the term of this Agreement.

 (c) If the Consultant fails to effect and keep in force the aforesaid insurances for which it is responsible pursuant hereto, the Authority shall, apart from having other recourse available under this Agreement, have the option, without prejudice to the obligations of the Consultant, to take out the aforesaid insurance, to keep in force any such insurances, and pay such premia and recover the costs thereof from the Consultant, and the Consultant shall be liable to pay such amounts on demand by the Authority.

(d) Except in case of Third Party liabilities, the insurance policies so procured shall mention the Authority as the beneficiary of the Consultant and the Consultant shall procure an undertaking from the insurance company to this effect; provided that in the event the Consultant has a general insurance policy that covers the risks specified in this Agreement and the amount of insurance cover is equivalent to 3 (three) times the cover required hereunder, such insurance policy may not mention the Authority as the sole beneficiary of the Consultant or require an undertaking to that effect.

3.5.2 The Parties agree that the risks and coverages shall include but not be limited to the following:

(a) Third Party liability insurance as required under Applicable Laws, with a minimum coverage of Rs. 1 (one) crore;

(b) employer’s liability and workers’ compensation insurance in respect of the Personnel of the Consultant and of any Sub-Consultant, in accordance with Applicable Laws; and

(c) professional liability insurance for an amount no less than the Agreement Value.

The indemnity limit in terms of “Any One Accident” (AOA) and “Aggregate limit on the policy period” (AOP) should not be less than the amount stated in Clause 6.1.2 of the Agreement. In case of consortium, the policy should be in the name of Lead Member and not in the name of individual Members of the consortium.

* 1. **Accounting, inspection and auditing**

The Consultant shall:

(a) keep accurate and systematic accounts and records in respect of the Services provided under this Agreement, in accordance with internationally accepted accounting principles and in such form and detail as will clearly identify all relevant time charges and cost, and the basis thereof (including the basis of the Consultant’s costs and charges); and

(b) permit the Authority or its designated representative periodically, and up to one year from the expiration or termination of this Agreement, to inspect the same and make copies thereof as well as to have them audited by auditors appointed by the Authority.

**3.7 Consultant’s actions requiring the Authority's prior approval**

The Consultant shall obtain the Authority's prior approval in writing before taking any of the following actions:

1. appointing such members of the Professional Personnel as are not listed in Annex–2.
2. entering into a subcontract for the performance of any part of the Services, it being understood (i) that the selection of the Sub-Consultant and the terms and conditions of the subcontract shall have been approved in writing by the Authority prior to the execution of the subcontract, and (ii) that the Consultant shall remain fully liable for the performance of the Services by the Sub-Consultant and its Personnel pursuant to this Agreement; or
3. any other action that is specified in this Agreement.

**3.8 Reporting obligations**

The Consultant shall submit to the Authority the reports and documents specified in the Agreement, in the form, in the numbers and within the time periods set forth therein.

**3.9 Documents prepared by the Consultant to be property of the Authority**

3.9.1 All plans, drawings, specifications, designs, reports and other documents (collectively referred to as “**Consultancy Documents**”) prepared by the Consultant (or by the Sub-Consultants or any Third Party) in performing the Services shall become and remain the property of the Authority, and all intellectual property rights in such Consultancy Documents shall vest with the Authority. Any Consultancy Document, of which the ownership or the intellectual property rights do not vest with the Authority under law, shall automatically stand assigned to the Authority as and when such Consultancy Document is created and the Consultant agrees to execute all papers and to perform such other acts as the Authority may deem necessary to secure its rights herein assigned by the Consultant.

3.9.2 The Consultant shall, not later than termination or expiration of this Agreement, deliver all Consultancy Documents to the Authority, together with a detailed inventory thereof. The Consultant may retain a copy of such Consultancy Documents. The Consultant, its Sub-Consultants or a Third Party shall not use these Consultancy Documents for purposes unrelated to this Agreement without the prior written approval of the Authority.

3.9.3 The Consultant shall hold the Authority harmless and indemnified for any losses, claims, damages, expenses (including all legal expenses), awards, penalties or injuries (collectively referred to as ‘Claims’) which may arise from or due to any unauthorised use of such Consultancy Documents, or due to any breach or failure on part of the Consultant or its Sub-Consultants or a Third Party to perform any of its duties or obligations in relation to securing the aforementioned rights of the Authority.

**3.10 Equipment and materials furnished by the Authority**

Equipment and materials made available to the Consultant by the Authority shall be the property of the Authority and shall be marked accordingly. Upon termination or expiration of this Agreement, the Consultant shall furnish forthwith to the Authority, an inventory of such equipment and materials and shall dispose of such equipment and materials in accordance with the instructions of the Authority. While in possession of such equipment and materials, the Consultant shall, unless otherwise instructed by the Authority in writing, insure them in an amount equal to their full replacement value.

**3.11** **Providing access to Project Office and Personnel**

 The Consultant shall ensure that the Authority, and officials of the Authority having authority from the Authority, are provided unrestricted access to the Project Office and to all Personnel during office hours. The Authority’s official, who has been authorised by the Authority in this behalf, shall have the right to inspect the Services in progress, interact with Personnel of the Consultant and verify the records relating to the Services for his satisfaction.

**3.12.** **Accuracy of Documents**

 The Consultant shall be responsible for accuracy of the data collected by it directly or procured from other agencies/authorities, the designs, drawings, estimates and all other details prepared by it as part of these services. Subject to the provisions of Clause 3.4, it shall indemnify the Authority against any inaccuracy in its work which might surface during implementation of the Project, if such inaccuracy is the result of any negligence or inadequate due diligence on part of the Consultant or arises out of its failure to conform to good industry practice. The Consultant shall also be responsible for promptly correcting, at its own cost and risk, the drawings including any re-survey / investigations.

**4. CONSULTANT’S PERSONNEL AND SUB-CONSULTANTS**

**4.1 General**

The Consultant shall employ and provide such qualified and experienced Personnel as may be required to carry out the Services.

**4.2 Deployment of Personnel**

4.2.1 The designations, names and the estimated periods of engagement in carrying out the Services by each of the Consultant’s Personnel are described in Annex-2 of this Agreement. The estimate of Personnel costs and man day rates are specified in Annex-3 of this Agreement.

4.2.2 Adjustments with respect to the estimated periods of engagement of Personnel set forth in the aforementioned Annex-3 may be made by the Consultant by written notice to the Authority, provided that: (i) such adjustments shall not alter the originally estimated period of engagement of any individual by more than 20% (twenty per cent) or one week, whichever is greater, and (ii) the aggregate of such adjustments shall not cause payments under the Agreement to exceed the Agreement Value set forth in Clause 6.1.2 of this Agreement. Any other adjustments shall only be made with the written approval of the Authority.

4.2.3 If additional work is required beyond the scope of the Services specified in the Terms of Reference, the estimated periods of engagement of Personnel, set forth in the Annexes of the Agreement may be increased by agreement in writing between the Authority and the Consultant, provided that any such increase shall not, except as otherwise agreed, cause payments under this Agreement to exceed the Agreement Value set forth in Clause 6.1.2.

**4.3 Approval of Personnel**

4.3.1 The Professional Personnel listed in Annex-2 of the Agreement are hereby approved by the Authority. No other Professional Personnel shall be engaged without prior approval of the Authority.

4.3.2 If the Consultant hereafter proposes to engage any person as Professional Personnel, it shall submit to the Authority its proposal along with a CV of such person in the form provided at Appendix–I (Form-12) of the RFP. The Authority may approve or reject such proposal within 14 (fourteen) days of receipt thereof. In case the proposal is rejected, the Consultant may propose an alternative person for the Authority’s consideration. In the event the Authority does not reject a proposal within 14 (fourteen) days of the date of receipt thereof under this Clause 4.3, it shall be deemed to have been approved by the Authority.

**4.4 Substitution of Key Personnel**

The Authority expects all the Key Personnel specified in the Proposal to be available during implementation of the Agreement. The Authority will not consider any substitution of Key Personnel except under compelling circumstances beyond the control of the Consultant and the concerned Key Personnel. Such substitution shall be limited to not more than two Key Personnel subject to equally or better qualified and experienced personnel being provided to the satisfaction of the Authority. Without prejudice to the foregoing, substitution of one Key Personnel shall be permitted subject to reduction of remuneration equal to 20% (twenty per cent) of the total remuneration specified for the Key Personnel who is proposed to be substituted. In case of a second substitution, such reduction shall be equal to 50% (fifty per cent) of the total remuneration specified for the Key Personnel who is proposed to be substituted.

**4.5 Working hours, overtime, leave, etc.**

The Personnel shall not be entitled to be paid for overtime nor to take paid sick leave or vacation leave except as specified in the Agreement, and the Consultant’s remuneration shall be deemed to cover these items. All leave to be allowed to the Personnel is excluded from the Person Days of service set forth in Annex-2. Any taking of leave by any Personnel for a period exceeding 7 (seven) days shall be subject to the prior approval of the Authority, and the Consultant shall ensure that any absence on leave will not delay the progress and quality of the Services.

**4.6 Resident Team Leader and Project Manager**

 The person designated as the Team Leader of the Consultant’s Personnel shall be responsible for the coordinated, timely and efficient functioning of the Personnel. In addition, the Consultant shall designate a suitable person as Project Manager (the “**Project Manager**”) who shall be responsible for day to day performance of the Services.

**4.7** **Sub-Consultants**

 Sub-Consultants listed in Annex-4 of this Agreement are hereby approved by the Authority. The Consultant may, with prior written approval of the Authority, engage additional Sub-Consultants or substitute an existing Sub-Consultant. The hiring of Personnel by the Sub-Consultants shall be subject to the same conditions as applicable to Personnel of the Consultant under this Clause 4.

**5.** **OBLIGATIONS OF THE AUTHORITY**

**5.1 Assistance in clearances etc.**

Unless otherwise specified in the Agreement, the Authority shall make best efforts to ensure that the Government shall:

1. provide the Consultant, its Sub-Consultants and Personnel with work permits and such other documents as may be necessary to enable the Consultant, its Sub-Consultants or Personnel to perform the Services;

(b) facilitate prompt clearance through customs of any property required for the Services; and

(c) issue to officials, agents and representatives of the Government all such instructions as may be necessary or appropriate for the prompt and effective implementation of the Services.

**5.2** **Access to land and property**

The Authority warrants that the Consultant shall have, free of charge, unimpeded access to the site of the project in respect of which access is required for the performance of Services; provided that if such access shall not be made available to the Consultant as and when so required, the Parties shall agree on (i) the time extension, as may be appropriate, for the performance of Services, and (ii) the additional payments, if any, to be made to the Consultant as a result thereof pursuant to Clause 6.1.3.

**5.3** **Change in Applicable Law**

If, after the date of this Agreement, there is any change in the Applicable Laws with respect to taxes and duties which increases or decreases the cost or reimbursable expenses incurred by the Consultant in performing the Services, by an amount exceeding 2% (two per cent) of the Agreement Value specified in Clause 6.1.2, then the remuneration and reimbursable expenses otherwise payable to the Consultant under this Agreement shall be increased or decreased accordingly by agreement between the Parties hereto, and corresponding adjustments shall be made to the aforesaid Agreement Value.

**5.4** **Payment**

In consideration of the Services performed by the Consultant under this Agreement, the Authority shall make to the Consultant such payments and in such manner as is provided in Clause 6 of this Agreement.

**6.** **PAYMENT TO THE CONSULTANT**

* 1. **Cost estimates and Agreement Value**

6.1.1 An abstract of the cost of the Services payable to the Consultant is set forth in Annex-5 of the Agreement**.**

6.1.2 Except as may be otherwise agreed under Clause 2.6 and subject to Clause 6.1.3, the payments under this Agreement shall not exceed the agreement value specified herein (the “**Agreement Value**”). The Parties agree that the Agreement Value is Rs. ………. (Rupees. …………………….), which does not include the Additional Costs specified in Annex-5 (the “**Additional Costs**”).

6.1.3 Notwithstanding anything to the contrary contained in Clause 6.1.2, if pursuant to the provisions of Clauses 2.6 and 2.7, the Parties agree that additional payments shall be made to the Consultant in order to cover any additional expenditures not envisaged in the cost estimates referred to in Clause 6.1.1 above, the Agreement Value set forth in Clause 6.1.2 above shall be increased by the amount or amounts, as the case may be, of any such additional payments.

**6.2** **Currency of payment**

All payments shall be made in Indian Rupees. The Consultant shall be free to convert Rupees into any foreign currency as per Applicable Laws.

* 1. **Mode of billing and payment**

Billing and payments in respect of the Services shall be made as follows:-

1. No Mobilisation Advance shall be paid.
2. The Consultant shall be paid for its services as per the Payment Schedule at Annex-6 of this Agreement, subject to the Consultant fulfilling the following conditions:

(i) No payment shall be due for the next stage till the Consultant completes, to the satisfaction of the Authority, the work pertaining to the preceding stage.

(ii) The Authority shall pay to the Consultant, only the undisputed amount.

1. The Authority shall cause the payment due to the Consultant to be made within 30 (thirty) days after the receipt by the Authority of duly completed bills with necessary particulars (the “**Due Date**”). Interest at the rate of 10% (ten per cent) per annum shall become payable as from the Due Date on any amount due by, but not paid on or before, such Due Date.
2. The final payment under this Clause shall be made only after the final report and a final statement, identified as such, shall have been submitted by the Consultant and approved as satisfactory by the Authority. The Services shall be deemed completed and finally accepted by the Authority and the final deliverable shall be deemed approved by the Authority as satisfactory upon expiry of 90 (ninety) days after receipt of the final deliverable by the Authority unless the Authority, within such 90 (ninety) day period, gives written notice to the Consultant specifying in detail, the deficiencies in the Services. The Consultant shall thereupon promptly make any necessary corrections and/or additions, and upon completion of such corrections or additions, the foregoing process shall be repeated. The Authority shall make the final payment upon acceptance or deemed acceptance of the final deliverable by the Authority.
3. Any amount which the Authority has paid or caused to be paid in excess of the amounts actually payable in accordance with the provisions of this Agreement shall be reimbursed by the Consultant to the Authority within 30 (thirty) days after receipt by the Consultant of notice thereof. Any such claim by the Authority for reimbursement must be made within 1 (one) year after receipt by the Authority of a final report in accordance with Clause 6.3 (d). Any delay by the Consultant in reimbursement by the due date shall attract simple interest @ 10% (ten per cent) per annum.
4. 10% (ten per cent) of the Agreement Value has been earmarked as Final Payment to be made to the Consultant upon execution of the Agreement. In the event the Agreement does not get executed within 1 (one) year of the Effective Date the Final Payment shall not become due to the Consultant, save and except the costs incurred for meeting its reimbursable expenses during the period after expiry of 18 (eighteen) weeks from the Effective Date, including travel costs and personnel costs, at the agreed rates.
5. All payments under this Agreement shall be made to the account of the Consultant as may be notified to the Authority by the Consultant.

**7. LIQUIDATED DAMAGES AND PENALTIES**

**7.1**  **Performance Security**

7.1.1The Authority shall retain by way of performance security (the “**Performance Security**”), 10% (ten per cent) of all the amounts due and payable to the Consultant, to be appropriated against breach of this Agreement or for recovery of liquidated damages as specified in Clause 7.2. The balance remaining out of the Performance Security shall be returned to the Consultant at the end of 3 (three) months after the expiry of this Agreement pursuant to Clause 2.4 hereof. For the avoidance of doubt, the parties hereto expressly agree that in addition to appropriation of the amounts withheld hereunder, in the event of any default requiring the appropriation of further amounts comprising the Performance Security, the Authority may make deductions from any subsequent payments due and payable to the Consultant hereunder, as if it is appropriating the Performance Security in accordance with the provisions of this Agreement.

7.1.2The Consultantmay, in lieu of retention of the amounts as referred to in Clause 7.1.1 above, furnish a Bank Guarantee substantially in the form specified at Annex-7 of this Agreement.

**7.2 Liquidated Damages**

7.2.1Liquidated Damages for error/variation

In case any error or variation or plagiarism is detected in the data, data analysis or reports, submitted by the Consultant and such error or variation is the result of negligence or lack of due diligence on the part of the Consultant, the consequential damages thereof shall be quantified by the Authority in a reasonable manner and recovered from the Consultant by way of deemed liquidated damages, subject to a maximum of 10% (10 per cent) of the Agreement Value

7.2.2Liquidated Damages for delay

In case of delay in completion of Services, liquidated damages not exceeding an amount equal to 1% (one per cent) of the Agreement Value per week, subject to a maximum of 10% (ten per cent) of the Agreement Value will be imposed and shall be recovered by appropriation from the Performance Security or otherwise. However, in case of delay due to reasons beyond the control of the Consultant, suitable extension of time shall be granted.

7.2.3 Encashment and appropriation of Performance Security

The Authority shall have the right to invoke and appropriate the proceeds of the Performance Security, in whole or in part, without notice to the Consultant in the event of breach of this Agreement or for recovery of liquidated damages specified in this Clause 7.2.

**7.3 Penalty for deficiency in Services**

In addition to the liquidated damages not amounting to penalty, as specified in Clause 7.2, warning may be issued to the Consultant for minor deficiencies on its part. In the case of significant deficiencies in Services causing adverse effect on the Project or on the reputation of the Authority, other penal action including debarring for a specified period may also be initiated as per policy of the Authority.

**8.** **FAIRNESS AND GOOD FAITH**

**8.1 Good Faith**

The Parties undertake to act in good faith with respect to each other’s rights under this Agreement and to adopt all reasonable measures to ensure the realisation of the objectives of this Agreement.

**8.2 Operation of the Agreement**

The Parties recognise that it is impractical in this Agreement to provide for every contingency which may arise during the life of the Agreement, and the Parties hereby agree that it is their intention that this Agreement shall operate fairly as between them, and without detriment to the interest of either of them, and that, if during the term of this Agreement either Party believes that this Agreement is operating unfairly, the Parties will use their best efforts to agree on such action as may be necessary to remove the cause or causes of such unfairness, but failure to agree on any action pursuant to this Clause shall not give rise to a dispute subject to arbitration in accordancewithClause9 hereof.

**9.** **SETTLEMENT OF DISPUTES**

**9.1 Amicable settlement**

The Parties shall use their best efforts to settle amicably all disputes arising out of or in connection with this Agreement or the interpretation thereof.

**9.2 Dispute resolution**

9.2.1 Any dispute, difference or controversy of whatever nature howsoever arising under or out of or in relation to this Agreement (including its interpretation) between the Parties, and so notified in writing by either Party to the other Party (the “**Dispute**”) shall, in the first instance, be attempted to be resolved amicably in accordance with the conciliation procedure set forth in Clause 9.3.

9.2.2 The Parties agree to use their best efforts for resolving all Disputes arising under or in respect of this Agreement promptly, equitably and in good faith, and further agree to provide each other with reasonable access during normal business hours to all non-privileged records, information and data pertaining to any Dispute.

## 9.3 Conciliation

In the event of any Dispute between the Parties, either Party may call upon CEO, NITI Aayogand the Chairman of the Board of Directors of the Consultant or a substitute thereof for amicable settlement, and upon such reference, the said persons shall meet no later than 10 (ten) days from the date of reference to discuss and attempt to amicably resolve the Dispute. If such meeting does not take place within the 10 (ten) day period or the Dispute is not amicably settled within 15 (fifteen) days of the meeting or the Dispute is not resolved as evidenced by the signing of written terms of settlement within 30 (thirty) days of the notice in writing referred to in Clause 9.2.1 or such longer period as may be mutually agreed by the Parties, either Party may refer the Dispute to arbitration in accordance with the provisions of Clause 9.4.

## 9.4 Arbitration

9.4.1 Any Dispute which is not resolved amicably by conciliation, as provided in Clause 9.3, shall be finally decided by reference to arbitration by an Arbitral Tribunal appointed in accordance with Clause 9.4.2. Such arbitration shall be held in accordance with the Rules of Arbitration of the International Centre for Alternative Dispute Resolution, New Delhi (the “**Rules**”), or such other rules as may be mutually agreed by the Parties, and shall be subject to the provisions of the Arbitration and Conciliation Act,1996. The place of such arbitration shall be the capital of the State where the Authority has its headquarters and the language of arbitration proceedings shall be English.

9.4.2 There shall **be a sole arbitrator whose appointment or an Arbitral Tribunal of three arbitrators, of whom each Party shall select one, and the third arbitrator shall be appointed by the two arbitrators so selected, and in the event of disagreement between the two arbitrators, the appointment[[15]](#footnote-15)** shall be made in accordance with the Rules.

9.4.3 The arbitrators shall make a reasoned award (the “**Award**”). Any Award made in any arbitration held pursuant to this Clause 9 shall be final and binding on the Parties as from the date it is made, and the Consultant and the Authority agree and undertake to carry out such Award without delay.

9.4.4 The Consultant and the Authority agree that an Award may be enforced against the Consultant and/or the Authority, as the case may be, and their respective assets wherever situated.

9.4.5 This Agreement and the rights and obligations of the Parties shall remain in full force and effect, pending the Award in any arbitration proceedings hereunder.

**IN WITNESS WHEREOF, the Parties hereto have caused this Agreement to be signed in their respective names as of the day and year first above written.**

|  |  |
| --- | --- |
| SIGNED, SEALED AND DELIVERED | SIGNED, SEALED AND DELIVERED |
| For and on behalf of |  | For and on behalf of |
| Consultant: |  | Authority  |
|  | (Signature) |  | (Signature) |
|  | (Name) |  | (Name) |
|  | (Designation) |  | (Designation) |
|  | (Address) |  | (Address) |
|  |  |  |  |
| In the presence of: |  |  |  |
| 1. |  | 2. |  |

Annex-1

**Terms of Reference**

*(Refer Clause 3.1.2)*

(Reproduce Schedule-1 of RFP)

Annex-2

**Deployment of Personnel**

*(Refer Clause 4.2)*

(Reproduce as per Form-13 of Appendix-I)

Annex-3

**Estimate of Personnel Costs**

*(Refer Clause 4.2)*

(Reproduce as per Form-3 of Appendix-II)

Annex-4

**Approved Sub-Consultant(s)**

*(Refer Clause 4.7)*

(Reproduce as per Form-15 of Appendix-I)

Annex-5

**Cost of Services**

*(Refer Clause 6.1)*

(Reproduce as per Form-2 of Appendix-II)

Annex-6

**Payment Schedule**

*(Refer Clause 6.3)*

|  |  |  |  |
| --- | --- | --- | --- |
| **Key Date No.** | **Description of Deliverables** | **Week No.** | **Payment** |
| KD1 | Inception report approved by Authority | 3 | 20% |
| KD2 | Mid term report approved by Authority | 7 | 30% |
| KD3 | Draft evaluation report | 13 | 30% |
| KD4 | Final Evaluation Report approved by Authority | 14 | 20% |
|  | Total |  | 100% |

$Excludes the time taken by the Authority in providing its comments on the Draft evaluation report. The Consultant shall get two weeks for submission of the Final Evaluation Report after comments of the Authority are provided.

*Notes:*

*1*. *The above payments shall be made to the Consultant provided that the payments to be made at any time shall not exceed the amount certified by the Consultant in its Statement of Expenses.*

*2. All Reports shall first be submitted as draft reports for comments of the Authority. The Authority shall provide its comments no later than 3 (three) weeks from the date of receiving a draft report and in case no comments are provided within such 3 (three) weeks, the Consultant shall finalise its report. Provided, however, that the Authority may take upto 4 (four) weeks in providing its comments on the Draft evaluation report.*

*3. Draft evaluation report shall be completed in 13 (thirteen) weeks excluding the time taken by the Authority in providing its comments on the Draft evaluation report. The Consultant may take 1 (one) week for submitting its Final Evaluation Report after receipt of comments from the Authority.*

Annex- 7

**Bank Guarantee for Performance Security**

*(Refer Clause 7.1.2)*

To

[The President of India /Governor of ..................]

acting through

....................

....................

....................

In consideration of ............................. acting on behalf of the [President of India/Governor of ................................] (hereinafter referred as the “**Authority**”, which expression shall, unless repugnant to the context or meaning thereof, include its successors, administrators and assigns) awarding to ……………….., having its office at ……………….. (hereinafter referred as the “**Consultant**” which expression shall, unless repugnant to the context or meaning thereof, include its successors, administrators, executors and assigns), vide the Authority’s Agreement no. ………………. dated ……………….. valued at Rs. ……………….. (Rupees ………………..), (hereinafter referred to as the “**Agreement**”) the assignment for consultancy services in respect of the …………………. Project, and the Consultant having agreed to furnish a Bank Guarantee amounting to Rs. ……………….. (Rupees ………………..) to the Authority for performance of the said Agreement.

 We, ……………….. (hereinafter referred to as the “**Bank**”) at the request of the Consultant do hereby undertake to pay to the Authority an amount not exceeding Rs. ………………… (Rupees …………………. ) against any loss or damage caused to or suffered or would be caused to or suffered by the Authority by reason of any breach by the said Consultant of any of the terms or conditions contained in the said Agreement.

2. We, ……………….. (indicate the name of the Bank) do hereby undertake to pay the amounts due and payable under this Guarantee without any demur, merely on a demand from the Authority stating that the amount/claimed is due by way of loss or damage caused to or would be caused to or suffered by the Authority by reason of breach by the said Consultant of any of the terms or conditions contained in the said Agreement or by reason of the Consultant’s failure to perform the said Agreement. Any such demand made on the bank shall be conclusive as regards the amount due and payable by the Bank under this Guarantee. However, our liability under this Guarantee shall be restricted to an amount not exceeding Rs. ……………….. (Rupees …………………..).

3. We, ……………….. (indicate the name of the Bank) do hereby undertake to pay to the Authority any money so demanded notwithstanding any dispute or disputes raised by the Consultant in any suit or proceeding pending before any court or tribunal relating thereto, our liability under this present being absolute and unequivocal. The payment so made by us under this bond shall be a valid discharge of our liability for payment thereunder and the Consultant shall have no claim against us for making such payment.

4. We, ……………….. (indicate the name of Bank) further agree that the Guarantee herein contained shall remain in full force and effect during the period that would be required for the performance of the said Agreement and that it shall continue to be enforceable till all the dues of the Authority under or by virtue of the said Agreement have been fully paid and its claims satisfied or discharged or till the Authority certifies that the terms and conditions of the said Agreement have been fully and properly carried out by the said Consultant and accordingly discharges this Guarantee. Unless a demand or claim under this Guarantee is made on us in writing on or before a period of one year from the date of this Guarantee, we shall be discharged from all liability under this Guarantee thereafter.

5. We, ………………… (indicate the name of Bank) further agree with the Authority that the Authority shall have the fullest liberty without our consent and without affecting in any manner our obligations hereunder to vary any of the terms and conditions of the said Agreement or to extend time of performance by the said Consultant from time to time or to postpone for any time or from time to time any of the powers exercisable by the Authority against the said Consultant and to forbear or enforce any of the terms and conditions relating to the said Agreement and we shall not be relieved from our liability by reason of any such variation, or extension being granted to the said Consultant or for any forbearance, act or omission on the part of the Authority or any indulgence by the Authority to the said Consultant or any such matter or thing whatsoever which under the law relating to sureties would, but for this provision, have the effect of so relieving us.

6. This Guarantee will not be discharged due to the change in the constitution of the Bank or the Consultant(s).

7. We, ……………….. (indicate the name of Bank) lastly undertake not to revoke this Guarantee during its currency except with the previous consent of the Authority in writing.

8. For the avoidance of doubt, the Bank’s liability under this Guarantee shall be restricted to Rs. .......... crore (Rupees ........................................... crore) only. The Bank shall be liable to pay the said amount or any part thereof only if the Authority serves a written claim on the Bank in accordance with Paragraph 2 hereof, on or before [.......... (indicate the date falling 365 days after the date of this Guarantee)].

 For ..............................................................

Name of Bank:

Seal of the Bank:

Dated, the ...........................day of ................., 20......

(Signature, name and designation of the authorised signatory)

NOTES:

* 1. The Bank Guarantee should contain the name, designation and code number of the officer(s) signing the Guarantee.
	2. The address, telephone no. and other details of the Head Office of the Bank as well as of issuing Branch should be mentioned on the covering letter of issuing Branch.

**SCHEDULE-3**

*(See Clause 2.3.3)*

# **Guidance Note on Conflict of Interest**

1. This Note further explains and illustrates the provisions of Clause 2.3 of the RFP and shall be read together therewith in dealing with specific cases.

2. Consultants should be deemed to be in a conflict of interest situation if it can be reasonably concluded that their position in a business or their personal interest could improperly influence their judgment in the exercise of their duties. The process for selection of consultants should avoid both actual and perceived conflict of interest.

3. Conflict of interest may arise between the Authority and a consultant or between consultants and present or future contractors. Some of the situations that would involve conflict of interest are identified below:

(a) Authority and consultants:

(i) Potential consultant should not be privy to information from the Authority which is not available to others;

(ii) potential consultant should not have defined the project when earlier working for the Authority;

(iii) potential consultant should not have recently worked for the Authority overseeing the project.

(b) Consultants and contractors:

(i) No consultant should have an ownership interest or a continuing business interest or an on-going relationship with a potential contractor save and except relationships restricted to project-specific and short-term assignments; or

(ii) no consultant should be involved in owning or operating entities resulting from the project; or

(iii) no consultant should bid for works arising from the project.

The participation of companies that may be involved as investors or consumers and officials of the Authority who have current or recent connections to the companies involved, therefore, needs to be avoided.

4. The normal way to identify conflicts of interest is through self-declaration by consultants. Where a conflict exists, which has not been declared, competing companies are likely to bring this to the notice of the Authority. All conflicts must be declared as and when the consultants become aware of them.

5. Another approach towards avoiding a conflict of interest is through the use of “Chinese walls” to avoid the flow of commercially sensitive information from one part of the consultant’s company to another. This could help overcome the problem of availability of limited numbers of experts for the project. However, in reality effective operation of “Chinese walls” may be a difficult proposition. As a general rule, larger companies will be more capable of adopting Chinese walls approach than smaller companies. Although, “Chinese walls” have been relatively common for many years, they are an increasingly discredited means of avoiding conflicts of interest and should be considered with caution. As a rule, “Chinese walls” should be considered as unacceptable and may be accepted only in exceptional cases upon full disclosure by a consultant coupled with provision of safeguards to the satisfaction of the Authority.

6. Another way to avoid conflicts of interest is through the appropriate grouping of tasks. For example, conflicts may arise if consultants drawing up the terms of reference or the proposed documentation are also eligible for the consequent assignment or project.

7. Another form of conflict of interest called “scope–creep” arises when consultants advocate either an unnecessary broadening of the terms of reference or make recommendations which are not in the best interests of the Authority but which will generate further work for the consultants. Some forms of contractual arrangements are more likely to lead to scope-creep. For example, lump-sum contracts provide fewer incentives for this, while time and material contracts provide built in incentives for consultants to extend the length of their assignment.

8. Every project contains potential conflicts of interest. Consultants should not only avoid any conflict of interest, they should report any present/ potential conflict of interest to the Authority at the earliest. Officials of the Authority involved in development of a project shall be responsible for identifying and resolving any conflicts of interest. It should be ensured that safeguards are in place to preserve fair and open competition and measures should be taken to eliminate any conflict of interest arising at any stage in the process.

**APPENDICES**

APPENDIX-I

*(See Clause 2.1.3)*

**TECHNICAL PROPOSAL**

Form-1

**Letter of Proposal**

(On Applicant’s letter head)

(Date and Reference)

To,

........................

......................

.....................

Sub: Appointment of Consultant for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector

Dear Sir,

With reference to your RFP Document dated ………….., I/we, having examined all relevant documents and understood their contents, hereby submit our Proposal for selection as Consultant for the …………………… Project. The proposal is unconditional and unqualified.

2. All information provided in the Proposal and in the Appendices is true and correct and all documents accompanying such Proposal are true copies of their respective originals.

3. This statement is made for the express purpose of appointment as the Consultant for the aforesaid Project.

4. I/We shall make available to the Authority any additional information it may deem necessary or require for supplementing or authenticating the Proposal.

5. I/We acknowledge the right of the Authority to reject our application without assigning any reason or otherwise and hereby waive our right to challenge the same on any account whatsoever.

6. I/We certify that in the last three years, we or any of our Associates have neither failed to perform on any contract, as evidenced by imposition of a penalty by an arbitral or judicial authority or a judicial pronouncement or arbitration award against the Applicant, nor been expelled from any project or contract by any public authority nor have had any contract terminated by any public authority for breach on our part.

7. I/We declare that:

(a)I/We have examined and have no reservations to the RFP Documents, including any Addendum issued by the Authority;

(b) I/We do not have any Conflict of Interest in accordance with Clause 2.3 of the RFP Document;

(c) I/We have not directly or indirectly or through an agent engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice, as defined in Clause 4.3 of the RFP document, in respect of any tender or request for proposal issued by or any agreement entered into with the Authority or any other public sector enterprise or any government, Central or State; and

(d) I/We hereby certify that we have taken steps to ensure that in conformity with the provisions of Section 4 of the RFP, no person acting for us or on our behalf will engage in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice.

8. I/We understand that you may cancel the Selection Process at any time and that you are neither bound to accept any Proposal that you may receive nor to select the Consultant, without incurring any liability to the Applicants in accordance with Clause 2.8 of the RFP document.

9. I/We declare that we/any member of the consortium, are/is not a Member of a/any other Consortium applying for Selection as a Consultant.

10. I/We certify that in regard to matters other than security and integrity of the country, we or any of our Associates have not been convicted by a Court of Law or indicted or adverse orders passed by a regulatory authority which would cast a doubt on our ability to undertake the Consultancy for the Project or which relates to a grave offence that outrages the moral sense of the community.

11. I/We further certify that in regard to matters relating to security and integrity of the country, we have not been charge-sheeted by any agency of the Government or convicted by a Court of Law for any offence committed by us or by any of our Associates.

12. I/We further certify that no investigation by a regulatory authority is pending either against us or against our Associates or against our CEO or any of our Directors/Managers/employees.[[16]](#footnote-16)$

13. I/We hereby irrevocably waive any right or remedy which we may have at any stage at law or howsoever otherwise arising to challenge or question any decision taken by the Authority [and/ or the Government of India] in connection with the selection of Consultant or in connection with the Selection Process itself in respect of the above mentioned Project.

14. The Bid Security of Rs. ................... (Rupees ........................................) in the form of a Demand Draft is attached, in accordance with the RFP document.

15. I/We agree and understand that the proposal is subject to the provisions of the RFP document. In no case, shall I/we have any claim or right of whatsoever nature if the Consultancy for the Project is not awarded to me/us or our proposal is not opened or rejected.

16. I/We agree to keep this offer valid for 90 (ninety) days from the Proposal Due Date specified in the RFP.

17. A Power of Attorney in favour of the authorised signatory to sign and submit this Proposal and documents is attached herewith in Form-4.

18. In the event of my/our firm/ consortium being selected as the Consultant, I/we agree to enter into an agreement in accordance with the form at Schedule–2 of the RFP.We agree not to seek any changes in the aforesaid form and agree to abide by the same.

 19.I/We have studied RFP and all other documents carefully. We understand that except to the extent as expressly set forth in the Agreement, we shall have no claim, right or title arising out of any documents or information provided to us by the Authority or in respect of any matter arising out of or concerning or relating to the Selection Process including the award of Consultancy.

 20. The Financial Proposal is being submitted in a separate cover. This Technical Proposal read with the Financial Proposal shall constitute the Application which shall be binding on us.

21 I/We agree and undertake to abide by all the terms and conditions of the RFP Document. In witness thereof, I/we submit this Proposal under and in accordance with the terms of the RFP Document.

Yours faithfully,

(Signature, name and designation of the authorised signatory)

 (Name and seal of the Applicant / Lead Member)

APPENDIX-I

Form-2

**Particulars of the Applicant**

|  |  |
| --- | --- |
| 1.1 | Title of Consultancy: Evaluation ofCentrally Sponsored Schemes |
| 1.2 | Title of Project:Package 5 - Rural Development Sector |
| 1.3 | State whether applying as Sole Firm or Lead Member of a consortium:Sole FirmorLead Member of a consortium |
| 1.4 | State the following:Name of Company or Firm: Legal status (e.g. incorporated private company, unincorporated business, partnership etc.):Country of incorporation:Registered address:Year of Incorporation: Year of commencement of business: Principal place of business: Brief description of the Company including details of its main lines of business Name, designation, address and phone numbers of authorised signatory of the Applicant:Name:Designation:Company:Address:Phone No.:E-mail address: |
| 1.5 | If the Applicant is Lead Member of a consortium, state the following for each of the other Member Firms: |
| (i) Name of Firm:(ii) Legal Status and country of incorporation(iii) Registered address and principal place of business. |
| 1.6 | For the Applicant, (in case of a consortium, for each Member), state the following information:(i) In case of non Indian Firm, does the Firm have business presence in India? Yes/No If so, provide the office address(es) in India. (ii) Has the Applicant or any of the Members in case of a consortium been penalized by any organization for poor quality of work or breach of contract in the last five years? Yes/No(iii) Has the Applicant/ Member ever failed to complete any work awarded to it by any public authority/ entity in last five years?Yes/No (iv) Has the Applicant or any member of the consortium been blacklisted by any Government department/Public Sector Undertaking in the last five years?Yes/No (v) Has the Applicant or any of the Members, in case of a consortium, suffered bankruptcy/insolvency in the last five years?Yes/No**Note: If answer to any of the questions at (ii) to (v) is yes, the Applicant is not eligible for this consultancy assignment.** |
| 1.7 | Does the Applicant’s firm/company (or any member of the consortium) combine functions as a consultant or adviser along with the functions as a contractor and/or a manufacturer?Yes/No If yes, does the Applicant (and other Member of the Applicant’s consortium) agree to limit the Applicant’s role only to that of a consultant/ adviser to the Authority and to disqualify themselves, their Associates/ affiliates, subsidiaries and/or parent organization subsequently from work on this Project in any other capacity? Yes/No |
| 1.8 | Does the Applicant intend to borrow or hire temporarily, personnel from contractors, manufacturers or suppliers for performance of the Consulting Services? Yes/NoIf yes, does the Applicant agree that it will only be acceptable as Consultant, if those contractors, manufacturers and suppliers disqualify themselves from subsequent execution of work on this Project (including tendering relating to any goods or services for any other part of the Project) other than that of the Consultant?Yes/No If yes, have any undertakings been obtained (and annexed) from such contractors, manufacturers, etc. that they agree to disqualify themselves from subsequent execution of work on this Project and they agree to limit their role to that of consultant/ adviser for the Authority only? Yes/No(Signature, name and designation of the authorised signatory)For and on behalf of ……………….. |

APPENDIX-I

Form-3

**Statement of Legal Capacity**

*(To be forwarded on the letter head of the Applicant)*

Ref. Date:

To,

.....................

....................

....................

Dear Sir,

Sub: RFP for Consultant: .................................. Project

I/We hereby confirm that we, the Applicant (along with other members in case of consortium, the constitution of which has been described in the Proposal[[17]](#footnote-17)$), satisfy the terms and conditions laid down in the RFP document.

I/We have agreed that ……………….. (insert Applicant’s name) will act as the Lead Member of our consortium.

I/We have agreed that ……………….. (insert individual’s name) will act as our Authorised Representative/ will act as the Authorised Representative of the consortium on our behalf and has been duly authorized to submit our Proposal. Further, the authorised signatory is vested with requisite powers to furnish such proposal and all other documents, information or communication and authenticate the same.

Yours faithfully,

(Signature, name and designation of the authorised signatory)

For and on behalf of ..............................................

APPENDIX-I

Form-4

**Power of Attorney**

Know all men by these presents,we, ......................................... (name of Firm and address of the registered office) do hereby constitute, nominate, appoint and authorise Mr / Ms........................................ son/daughter/wife and presently residingat ........................................**,** who is presently employed with us and holding the position of .................... as our true and lawful attorney (hereinafter referred to as the “**Authorised Representative**”) to do in our name and on our behalf, all such acts, deeds and things as are necessary or required in connection with or incidental to submission of our Proposal for and selection as the Consultant for Evaluation of Centrally Sponsored Schemesin Package 5 - Rural Development Sector for the ........................................ Project**,** proposed to be developed by the .......................................... (the “**Authority**”) including but not limited to signing and submission of all applications, proposals and other documents and writings, participating in pre-bid and other conferences and providing information/ responses to the Authority, representing us in all matters before the Authority, signing and execution of all contracts and undertakings consequent to acceptance of our proposal and generally dealing with the Authority in all matters in connection with or relating to or arising out of our Proposal for the said Project and/or upon award thereof to us till the entering into of the Agreement with the Authority.

AND, we do hereby agree to ratify and confirm all acts, deeds and things lawfully done or caused to be done by our said Authorised Representative pursuant to and in exercise of the powers conferred by this Power of Attorney and that all acts, deeds and things done by our said Authorised Representative in exercise of the powers hereby conferred shall and shall always be deemed to have been done by us.

IN WITNESS WHEREOF WE, ................................THE ABOVE-NAMED PRINCIPAL HAVE EXECUTED THIS POWER OF ATTORNEY ON THIS ...................................... DAY OF ...................., 20.......

For ............................................

(Signature, name, designation and address)

Witnesses:

1.

2.

Notarised

Accepted

........................................

 (Signature, name, designation and address of the Attorney)

*Notes:*

* *The mode of execution of the Power of Attorney should be in accordance with the procedure, if any, laid down by the applicable law and the charter documents of the executant(s) and when it is so required the same should be under common seal affixed in accordance with the required procedure. The Power of Attorney should be executed on a non-judicial stamp paper of Rs. 100 (hundred) and duly notarised by a notary public.*
* *Wherever required, the Applicant should submit for verification the extract of the charter documents and other documents such as a resolution/power of attorney in favour of the person executing this Power of Attorney for the delegation of power hereunder on behalf of the Applicant.*
* *For a Power of Attorney executed and issued overseas, the document will also have to be legalised by the Indian Embassy and notarised in the jurisdiction where the Power of Attorney is being issued. However, Applicants from countries that have signed the Hague Legislation Convention 1961 need not get their Power of Attorney legalised by the Indian Embassy if it carries a conforming Apostille certificate.*

APPENDIX-I

Form-5

**Financial Capacity of the Applicant**

(Refer Clause 2.2.2 (B))

|  |  |  |
| --- | --- | --- |
| **S. No.** | **Financial Year** | **Annual Revenue** **(Rs./US $ in million)** |
|  |  |  |
|  |  |  |
|  |  |  |
| **Certificate from the Statutory Auditor$**This is to certify that .................... (name of the Applicant) has received the payments shown above against the respective years on account of professional fees.Name of the audit firm:Seal of the audit firmDate:(Signature, name and designation of the authorised signatory) |

**$** In case the Applicant does not have a statutory auditor, it shall provide the certificate from its chartered accountant that ordinarily audits the annual accounts of the Applicant.

**Note:** Please do not attach any printed Annual Financial Statement.

APPENDIX-I

Form-6

**Particulars of Key Personnel**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **S. No.** | **Designation of Key Personnel** | **Name** | **Educational Qualification** | **Length of Professional Experience** | **Present Employment** | **No. of Eligible General Assignments$** | **No. of Eligible Specific Assignments$** |
| **Name of Firm** | **Employed Since** |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |
| 1. | Team Leader  |  |  |  |  |  |  |  |
| 2 | Deputy Team Leader |  |  |  |  |  |  |  |
| 3 | Monitoring and Evaluation Expert |  |  |  |  |  |  |  |
| 4 | Economist |  |  |  |  |  |  |  |
| 5 | Development Sector Lead |  |  |  |  |  |  |  |
| 6 | Finance Specialist |  |  |  |  |  |  |  |
| 7 | Statistician |  |  |  |  |  |  |  |
| 8 | Public Institution Specialist |  |  |  |  |  |  |  |
| 9 | Gender and Social Inclusion Specialist |  |  |  |  |  |  |  |
| 10 | Environment and Climate Change Specialist |  |  |  |  |  |  |  |
| 11 | Information Technology specialist |  |  |  |  |  |  |  |
| 12 | Safeguards Specialist |  |  |  |  |  |  |  |
| 13 | Livelihood Expert |  |  |  |  |  |  |  |
| 14 | Rural Infrastructure Expert |  |  |  |  |  |  |  |

**$**Refer Form 9 of Appendix I Experience of Key Personnel

APPENDIX-I

Form-7

**Proposed Methodology and Work Plan**

The proposed methodology and work plan shall be described as follows:

1. Understanding of TOR (not more than two pages)

 The Applicant shall clearly state its understanding of the TOR and also highlight its important aspects. The Applicant may supplement various requirements of the TOR and also make precise suggestions if it considers this would bring more clarity and assist in achieving the Objectives laid down in the TOR.

2. Methodology and Work Plan (not more than four pages)

 The Applicant will submit its methodology for carrying out this assignment, outlining its approach toward achieving the Objectives laid down in the TOR, including approach, methodology, sampling, criteria for State/UT selection etc. The Applicant will submit a brief write up on its proposed team and organisation of personnel explaining how different areas of expertise needed for this assignment have been fully covered by its proposal. In case the Applicant is a consortium, it should specify how the expertise of each firm is proposed to be utilised for this assignment. The Applicant should specify the sequence, locations and timelines of important activities in the form of a Gantt chart, and provide a quality assurance plan for carrying out the Consultancy Services.

**Note**: Marks will be deducted for writing lengthy and out of context responses.

APPENDIX-I

Form-8

**Abstract of Eligible Assignments of the Applicant$**

(Refer Clause 3.1.4)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| S.No  | Name of Project | Name of Client | Estimated cost of Project/Assignment (in Rs. crore/ US$ million) | Payment**$$** of professional fees received by the Applicant (in Rs. crore) | Type of Assignment (General/Specific)As per Clause 3.1.4 |
| (1)£ | (2) | (3) | (4) | (5) | (6) |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |

$ The Applicant should provide details of only those projects that have been undertaken by it under its own name.

$$ Exchange rate for conversion of US $ shall be as per Clause 1.7.1.

£ The names and chronology of Eligible Projects included here should conform to the project-wise details submitted in Form-10 of Appendix-I.

|  |
| --- |
| **Certificate from the Statutory Auditor$**This is to certify that the information contained in Column 5 above is correct as per the accounts of the Applicant and/ or the clients.Name of the audit firm:Seal of the audit firmDate:(Signature, name and designation of the authorised signatory) |

$ In case the Applicant does not have a statutory auditor, it shall provide the certificate from its chartered accountant that ordinarily audits the annual accounts of the Applicant.

**Note:** The Applicant may attach separate sheets to provide brief particulars of other relevant experience of the Applicant.

APPENDIX-I

Form-9

**Abstract of Eligible Assignments of Key Personnel**$

(Refer Clause 3.1.4)

Name of Key Personnel: Designation:

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **S.No** | **Name of Project**$ | **Name of Client** | **Estimated capital cost of project (in Rs. cr./ US$ million)** | **Name of firm for which the Key Personnel worked** | **Designation of the Key Personnel on the assignment** | **Date of completion of the assignment**  | **Person Days spent** | **Type of Assignment****(General/Specific)****As per Clause 3.1.4** |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |

$ Use separate Form for each Key Personnel.

$$ The names and chronology of projects included here should conform to the project-wise details submitted in Form-11 of Appendix-I.

**Note**: The Applicant may attach separate sheets to provide brief particulars of other relevant experience of the Key Personnel.

APPENDIX-I

Form-10

**Eligible Assignments of Applicant**

(Refer Clause 3.1.4)

|  |  |  |
| --- | --- | --- |
|  | Name of Applicant: |  |
|  | Name of the Project: |  |
|  | Type of Assignment (General/Specific) as per Clause 3.1.4 |  |
|  | Description of services performed by the Applicant Firm: |  |
|  | Name of client and Address:(indicate whether public or private) |  |
|  | Name and telephone no. of client’s representative: |  |
|  | Estimated capital cost of the Project (in Rs crore or US$ million): |  |
|  | Paymentreceived by the Applicant (in Rs. crore): |  |
|  | Start date of the services (month/ year): |  |
|  | Finish date of the services (month/ year): |  |
|  | Brief description of the Project:  |
| It is certified that the aforesaid information is true and correct to the best of my knowledge and belief. (Signature and name of Key Personnel) |

**Notes:**

1. Use separate sheet for each Eligible Project.

2. The Applicant may attach separate sheets to provide brief particulars of other relevant experience of the Applicant.

3. Exchange rate for conversion of US $ shall be as per Clause 1.7.1.

APPENDIX-I

Form-11

**Eligible Assignments of Key Personnel**

(Refer Clause 3.1.4)

|  |  |  |
| --- | --- | --- |
|  | Name of Key Personnel: |  |
|  | Designation of Key Personnel: |  |
|  | Name of the Project: |  |
|  | Type of Assignment (General/Specific) as per Clause 3.1.4 |  |
|  | Name of Consulting Firm where employed: |  |
|  | Description of services performed by the Key Personnel (including designation): |  |
|  | Name of client and Address:(indicate whether public or private) |  |
|  | Name and telephone no. of client’s representative: |  |
|  | Estimated capital cost of the Project (in Rs crore or US$ million): |  |
|  | Start date of the services (month/ year): |  |
|  | Finish date of the services (month/ year): |  |
|  | Brief description of the Project:  |
| It is certified that the aforesaid information is true and correct to the best of my knowledge and belief. (Signature and name of Key Personnel) |

**Notes:**

1. Use separate sheet for each Eligible Project.

2. The Applicant may attach separate sheets to provide brief particulars of other relevant experience of the Key Personnel.

3. Exchange rate for conversion of US $ shall be as per Clause 1.7.1.

APPENDIX-I

Form-12

**Curriculum Vitae (CV) of Key Personnel**

**1.** Proposed Position:

**2.** Name of Personnel:

**3.** Date of Birth:

**4.** Nationality:

**5.** Educational Qualifications:

**6.** Employment Record:

(Starting with present position, list in reverse order every employment held.)

**7.** List of projects on which the Personnel has worked

|  |  |
| --- | --- |
| Name of project |  Description of responsibilities  |
|  |  |

**8.** Details of the current assignment and the time duration for which services are required for the current assignment.

Certification:

1. I am willing to work on the Project and I will be available for entire duration of the Project assignment as required.
2. I, the undersigned, certify that to the best of my knowledge and belief, this CV correctly describes me, my qualifications and my experience.

## (Signature and name of the Key Personnel)

Place.........................................

(Signature and name of the authorised signatory of the Applicant)

**Notes:**

1.Use separate form for each Key Personnel

2. The names and chronology of assignments included here should conform to the project-wise details submitted in Form-8 of Appendix-I.

3. Each page of the CV shall be signed in ink and dated by both the Personnel concerned and by the Authorised Representative of the Applicant firm along with the seal of the firm. Photocopies will not be considered for evaluation.

APPENDIX-I

Form-13

**Deployment of Personnel**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| S.No. | Designation | Name | Person Days (MD) | Week Numbers |
|  |  |  | On Field | In Office | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| 1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **Total Person Days** |

APPENDIX-I

Form–14

**Survey and Field Investigations**

|  |  |  |
| --- | --- | --- |
| **Item of Work/ Activity** | **To be carried out/ prepared by** | **Week** |
| Name | Designation |
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

APPENDIX-I

Form-15

**Proposal for Sub-Consultant(s)**

|  |
| --- |
| 1. Details of the Firm |
| Firm’s Name, Address and Telephone  |  |
| Name and Telephone No. of the Contact Person |  |
| Fields of Expertise |  |
| No. of Years in business in the above Fields |  |
| 2. Services that are proposed to be sub contracted: |
| 3. Person who will lead the Sub- ConsultantName:Designation:Telephone No:Email: |
| 4. Details of Firm’s previous experience |
| Name of Work | Name, address and telephone no. of Client | Total Value of Services Performed | Duration of Services | Date of Completion of Services |
| 1.2.3. |  |  |  |  |

(Signature and name of the authorised signatory)

**Note:**

* + - 1. The Proposal for Sub-Consultant(s) shall be accompanied by the details specified in Forms 12 and 13 of Appendix –I.
			2. Use separate form for each Sub-Consultant

APPENDIX-II

**FINANCIAL PROPOSAL**

Form-1

**Covering Letter**

(On Applicant’s letter head)

(Date and Reference)

To,

......................

.......................

.......................

Dear Sir,

Subject: Appointment of Consultant for Evaluation of Centrally Sponsored Schemes in Package 5 - Rural Development Sector

I/We, ................................. (Applicant’s name) herewith enclose the Financial Proposal for selection of my/our firm as Consultant for above.

I/We agree that this offer shall remain valid for a period of 90 (ninety) days from the Proposal Due Date or such further period as may be mutually agreed upon.

 Yours faithfully,

 (Signature, name and designation of the authorised signatory)

Note: The Financial Proposal is to be submitted strictly as per forms given in the RFP.APPENDIX-II

*(See Clause 2.1.3)*

Form-2

**Financial Proposal**

|  |  |  |
| --- | --- | --- |
| **Item No.** | **Description** | **Amount (Rs.)** |
| **A.** | **RESIDENT PERSONNEL** |  |
| III | Remuneration for Resident Professional Personnel(inclusive of all personal allowances)Remuneration for Resident Support Personnel(inclusive of all personal allowances) |  |
|  | **Sub-total Resident Personnel (A):** |  |
| **B.** | **LOCAL COSTS** |  |
| IIIIIIIVVVI | Office RentOffice Consumables like stationery, communication etc.Office Furniture and Equipment (Rental)Reports and Document PrintingSurveys & Investigations Miscellaneous Expenses |  |
|  | **Subtotal Local Costs (B):** |  |
|  | **Total of Personnel and Local Costs (A+B):** |  |
| **C.** | **POST REPORT CONSULTATIONS** |  |
| IIIIIIIVV | 2 Person Days each ofTeam LeaderDeputy Team LeaderMonitoring and Evaluation ExpertEconomistRural Development Sector Lead |  |
|  | **Subtotal Post Report Consultations (C):** |  |
| **D**  | **SUBTOTAL OF A+B+C** |  |
| **E** | **OVERHEAD EXPENSES @..........% of (D)** |  |
| **F** | **SERVICE TAX** |  |
| **G** | **TOTAL (including taxes) (D+E+F) (in Rs.)**In Indian Rupees ………………………………...(in figures) ………………………………………………….. (in words) |  |
| **H** | **ADDITIONAL COSTS (not included in evaluation)** |  |
| III | Domestic travel from firm’s office to the Project Office (restricted to five return economy class air fares for each Key Personnel)Return journeys from Project Office to Authority’s office to attend meetings held by the Authority (provide indicative amount for five return fares) |  |
|  | **Total of Additional Costs (H)** |  |
| **I** | **TOTAL COST OF THE CONSULTANCY (G+H)**In Indian Rupees ………………………….. (in figures) ………………………………………………… (in words) |  |

**Note:**

1. The financial evaluation shall be based on the above Financial Proposal, excluding Additional Costs. The total in Item G shall, therefore, be the amount for purposes of evaluation. Additional Costs in Item H shall not be reckoned for purposes of financial evaluation.

2. Estimate of Costs for Item A I and A II shall be as per Form-3.

3. Miscellaneous Expenses in Item B VI shall not exceed 15% (fifteen per cent) of the total amount in Item D.

4. Domestic Air Fare in Item H I shall not be payable to the Consultant’s Personnel who are normally stationed in Delhi NCR.

5. All costs shall be reimbursed on production of a Statement of Expenses, duly certified by the Authorised Representative. However, no details of expenditures would be sought for overhead expenses, which will be reimbursed in proportion to the total expenses under Item D.

6. The reimbursement of expenses shall be limited to the amounts indicated above.

7. Savings of upto 20% (twenty per cent) under any head of expenditure specified in the summary of Financial Proposal may be reappropriated by the Consultant and added to any other head of expenditure, subject to a ceiling of 10% (ten per cent) in respect of the recipient head of expenditure. Upon Notification of such reappropriation to the Authority, the Financial Proposal shall be deemed to be amended, and payment shall be made accordingly.

8. No escalation on any account will be payable on the above amounts.

9. All other charges not shown here and all insurance premia are considered included in the man day rate/ overhead/ miscellaneous expenses.

10. The Authority may require the Key Personnel to visit the Project/ the Authority’s offices for further consultations after their Report has been accepted. The cost (remuneration including personal allowances) of 2 (two) Person Days of each Key Personnel is included in the Financial Proposal. The Authority may require upto 12 (twelve) extra days of consultation with any or all Key Personnel on payment of additional charges. For any increase as compared to the aforesaid 2 (two) days, payment shall be computed solely on the basis of relevant man day rates specified in the Financial Proposal. In all cases, return full fare economy class airfare shall be reimbursed in addition, as per actuals.

11. The Authority may require Professional Personnel to visit the Project/the Authority’s offices for further consultations or undertake desk work after the report has been accepted. The Additional Costs on this account shall be paid to the Consultant as per agreed man day rates and economy return airfare as per actuals shall also be reimbursed. However, the total number of additional Person Days requisitioned hereunder shall not exceed 120 (one hundred and twenty).

12. All payments shall be made in Indian Rupees and shall be subject to applicable Indian laws withholding taxes if any.

13. For the purposes hereof “**Statement of Expenses**” means a statement of the expenses incurred on each of the heads indicated in the Financial Proposal; provided that in relation to expenses on Personnel, the Statement of Expenses shall be accompanied by the particulars of Personnel and the Person Days spent on the Consultancy.

APPENDIX-II

Form-3

**Estimate of Personnel Costs**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ID No.** | **Position** | **Name** | **Man day Rate****(Rs.)**  | **Total Person Days** | **Amount****(Rs.)** |
| **A I. Remuneration for Resident Professional Personnel (including all personal allowances)** |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
| Total  |  |  |
| **A II. Remuneration for Resident Support Personnel (including all personal allowances)** |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
| Total |  |  |
| Total: |  |  |  |

APPENDIX - III

**LIST OF BID-SPECIFIC PROVISIONS**[[18]](#footnote-18)$

**A. Clauses with currency-based footnotes**

1. Introduction.
2. Clause 2.2.3: Conditions of Eligibility of Applicants.
3. Clause 2.11.3: Amendment of RFP.

**Note**: The above footnotes marked “$” shall be retained in the RFP for guidance of the Applicants while submitting their respective Proposals.

**B. Schedules with non-numeric footnotes**

All non-numeric footnotes marked “$” in the Schedules shall be retained in the respective Schedules for guidance of the Applicants while submitting their respective Proposals.

**C. Appendices with non-numeric footnotes**

All non-numeric footnotes in the Appendices shall be retained in the respective Appendices for guidance of the Applicants. These shall be omitted by the Applicants while submitting their respective Proposals.

**D. Schedules and Appendices with blank spaces**

All blank spaces in the Schedules and Appendices shall be retained in the RFP. These shall be filled up when the format of the respective Schedule or Appendix is used.

APPENDIX-IV

**REFERENCES**

**APPENDIX-IV**

1. **Table 1: Umbrella Programmes and CSS schemes under Rural Development Sector**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ministry/Department | Umbrella CSS Scheme | CSS Schemes | Cumulative outlay for past 5 years (2015-16 to 2019-20) ( in crores)**[[19]](#footnote-19)** | Year of scheme launch |
| M/o Rural Development | National Social Assistance Programme | 1. Indira Gandhi National Old Age Pension Scheme (IGNOAPS),
 | 29829.95 | 1995 |
| 1. Indira Gandhi National Widow Pension Scheme (IGNWPS),
 | 9828.66 |
| 1. National Family Benefit Scheme (NFBS)
 | 3140.29 |
| 1. Indira Gandhi National Disability Pension Scheme (IGNDPS),
 | 1255.64 |
| 1. Annapurna.
 | 140.21 |
|  | Pradhan Mantri Awas Yojna (PMAY-G) | Pradhan Mantri Awas Yojna (PMAY): Rural | 87659.33 | 2016 |
|  | Shyama Prasad Mukherjee Rurban Mission | Shyama Prasad Mukherjee Rurban Mission | 2435.77 | 2016 |
|  | National Livelihood Mission - Ajeevika | National Livelihood Mission – Ajeevika: National Rural Livelihood Mission | 24806.77 | 2011 |
|  | Pradhan Mantri Gram Sadak Yojna | Pradhan Mantri Gram Sadak Yojna | 87574.86 | 2000 |
|  | Mahatma Gandhi National Rural Employment Guarantee Program (MGNREGA) | Mahatma Gandhi National Rural Employment  | 261824.8 | 2006 |

1. **Table 2.1: Indicative Stakeholder Mapping (Sectoral Level)**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Key Informant Interviews** | **Focus Group Discussions** | **Surveys** |
| **National\*** | DoRD , NRRDA, National Mission Directorate, NTSA (National Technical Support Agency, NRLM CC/ NMMU,  | Not Applicable | Not Applicable |
| **State** | State Rural Development Department, SRRDA, State Level Empowered Committee, SPMU/STSA, SRLM/SMMU | Not Applicable | Not Applicable |
| **District/****Town** | PIA , District Panchayat, District Program Officer, DRDA, DPMU/Cluster development and management unit, District Level PMU, District Mission Management Unit, Centre,0020State Employment Guarantee Council | Not Applicable | Not Applicable |
| **Block** | BDO, BMMU | Not Applicable | Not Applicable |
| **Village** | Not Applicable | GP , Village Committee/Gram Sabha, /gram rozgar sahayak, JE/Contractor, Sarpanch, Bharat Nirman Volunteers , SHGs, Civil Society | Not Applicable |
| **Households** | Not Applicable | Widow/Disabled/Old/Mothers/Household | Beneficiary, SHG Members, Widow/Disabled/Old/Mothers/Household (NFBS), |

*\*includes Government, Academia, Think tanks, Multilaterals, NGOs, Experts, etc.*

**Table 2.2: Indicative Stakeholder Mapping (Scheme Level)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Scheme** | **Centre** | **State** | **District** | **Block** | **Village** | **Household** |
| NSAP | DoRD (Key Informant Interviews) | State Rural Development Department (Key Informant Interviews) | DRDA (Key Informant Interviews) |  | GP/gram rozgarsahayak (Focus group Discussions) | Beneficiary- Widow/Disabled/Old/Mothers/Household (NFBS) (Focus group Discussions, Household Survey) |
| MGNREGA | Central Employment Guarantee Council(Key Informant interviews)  | State Employment Guarantee Council (Key Informant interviews )  | District Panchayat, District Program Officer (Key Informant Interviews)  | Block Panchayat (Program Officer) Key Informant interviews  | GP (Focus group Discussions) | Beneficiary (Focus group Discussions, Household Survey) |
| PMGSY | NRRDA (Key Informant Interviews) | SRRDA (Key Informant Interviews) | PIA (Key Informant Interviews) | SDO (Key Informant Interviews) | JE/Contractor, GP,Community (Focus group Discussions) | Household Survey |
| RURBAN | National Mission Directorate (Key Informant Interviews) | State Level Empowered Committee (Key Informant Interviews) | DPMU/Cluster development and management unit (Key Informant Interviews) | BDO (Key Informant Interviews) | Village GPs / Sarpanch (Focus group Discussions) | Household Survey |
| PMAY | NTSA (National Technical Support Agency) (Key Informant Interviews) | SPMU/STSA (Key Informant Interviews) | District Level PMU (Key Informant Interviews) | Block PMU (Key Informant Interviews) | GP/gram rozgarsahayak, Bharat nirman Volunteers , SHGs, Civil Society (Focus group Discussions) | Beneficiary (Focus group Discussions,Household Survey) |
| NRLM | NRLM CC/ NMMU (Key Informant Interviews) | SRLM/SMMU (Key Informant Interviews) | DMMU – District Mission Management Unit (DMMU)(Key Informant Interviews) | BMMU (Key Informant Interviews) | Village Committee/Gram Sabha (Focus group Discussions) | SHG Members (Focus group Discussions, Household Survey) |
| The members participate in Focus Group Discussions (FGDs) must include Implementing functionaries , Women, SC, ST, Vulnerable Section, PRI members, Village Sarpanch, Knowledgeable Person, Teacher, Postman, Ex-servicemen (if available), Self Help Group members etc. |

**C. Indicative List of key documents to be referred by the Consultant**

1. National level:

a. Strategy for New India @ 75, NITI Aayog

b. Three Year Action Agenda, 2017-18 to 2019-20, NITI Aayog

c. Finance Commission Reports;

d. Report of the Sub-Group of Chief Ministers on the Rationalisation of CSS, October 2015;

e. Annual Economic Survey of India,

f. SDG related reports; etc

2. Sector specific: Evaluations, reports

3. Scheme specific: guidelines, annual reports, etc are available at ministry’s website:

4. Evaluation studies: Indicative list of studies by Ministry, NITI, CAG, independent

agencies etc. is as follows:

1. Independent Assessment of Design, Strategies, and Impacts of DAY-NRLM by Institute of Rural Management Anand in 2017.<https://rural.nic.in/documents/institute-rural-management-anand-irma>
2. Rapid Assessment of Natural Resource Management Component Under MGNREGA and its impact on Sustainable Livelihoods by Institute of Economic Growth, Delhi during 2017.<https://rural.nic.in/sites/default/files/IEG_ReportNRM_Summary_11122017_0.pdf>
3. PMGSY: 2017, Indian Institute of Management Ahmedabad on Outcome Monitoring Study, <https://rural.nic.in/sites/default/files/PMGSY_Outcome_Monitoring_Study_IIMA.pdf>
4. Impact ofPMAY-G on income and employment by National Institute of Public Finance and Policy in 2018
5. <https://rural.nic.in/sites/default/files/IMPACT_OF_PMAYG_ON_INCOME_AND_EMPLOYMENT_REPORT.pdf>
6. Evaluation of Indira Gandhi National Old Age Pension Scheme (NSAP: IGNOAPS) in Kerala conducted by Centre for Rural Management (CRM) Kottayam, Kerala during 2012.

5. Important websites: Department of Rural Development, Scheme-specific Dashboards, CAG, NITI Aayog, etc.

Department of Rural Development: <https://rural.nic.in/>

PMAY-G: Awasapp <https://rhreporting.nic.in/netiay/newreport.aspx>

MGNREGA: <https://www.nrega.nic.in/netnrega/home.aspx>

PMGSY: omms.nic.in

NRLM:<https://aajeevika.gov.in/>

 NSAP: [nsap.nic.in/](http://nsap.nic.in/)

1. **Table 3: Scheme level Output-Outcome framework**
2. **Pradhan Mantri Awaas Yojana (PMAY)-Rural**

|  |  |
| --- | --- |
| **Output** | **Outcomes** |
| **Output** | **Indicator(s)** | **Outcome** | **Indicator(s)** |
|
| Construction of Pucca houses with adequate basic services | 1.1.Number of houses completed (with toilet)1.2.Number of masons trained | 1. More HHs live in dignified homes with access to basic services | 1.1. No. of households provided with all basic amenities i.e. Electricity connection, LPG connection & Safe drinking water |

1. **Mahatma Gandhi National Rural Employment Guarantee Programme (MGNREGA)**

|  |  |
| --- | --- |
| **Outputs** | **Outcomes** |
| **Output** | **Indicator(s)** | **Outcome** | **Indicator(s)** |
|
| 1. Providing employment, improved institutional capacity and creation of durable assets | 1.1 Number of Person days generated1.2 Total Number of Assets generated during the year | 1. Providing Economic security, creating rural assets and Empowerment of socially disadvantaged groups | 1.1. Irrigation Potential created under MGNREGA (in Hectares) |
| 1.2.Afforestation under MGNREGA (in KMs) |
| 2. Introducing New Work Programmes |  |  | 2.1.Total Number of water bodies constructed/ rejuvenated2.2 Participation of women (%) |

1. **Scheme : PradhanMantri Gram SadakYojana (PMGSY)**

|  |  |
| --- | --- |
| **Outputs** | **Outcomes** |
| **Output** | **Indicator(s)** | **Outcome** | **Indicator(s)** |
|
| 1. Availability of quality all weather roads and their timely maintenance | 1.1. Road length added (in 000 Km)1.2 Works inspected by NQM1.3 Completed works rated unsatisfactory(% of inspected works by NQM, average of last 3 years)1.4 Maintenance works rated unsatisfactory (% of inspected works by NQM, average of last 3 years)1.5 Proportion of complaints addressed out of registered on MeriSadak App (%) | 1. All weather road connectivity of eligible habitations are also pathways for access to education, health, market and mobility

2. Use of sustainable & green technology for construction of rural roads | 1.1. % of eligible habitations connected w.r.t. the no. of eligible habitations (as per 2001 census)  |
| 1.2. Road length added using Green Technology (in 000 Km) |
|  |

1. **National Social Assistance Programme (NSAP)**

|  |  |
| --- | --- |
| **Output** | **Outcomes** |
| **Output** | **Indicator(s)** | **Outcome** | **Indicator(s)** |
|
| Beneficiary coverage | 1.1.No. of beneficiaries covered- Scheme wise (IGNOAPS, NFBS, IGNWPS, IGNDPS, Annapurna) | 1. Providing social assistance and improved safety net | 1.1.% of eligible beneficiaries with Aadhar linkage |

1. **Deendayal Antyodaya Yojana-National Rural Livelihoods Mission (DAY-NRLM)**

|  |  |
| --- | --- |
| **Outputs** | **Outcomes** |
| **Output** | **Indicator(s)** | **Outcome** | **Indicator(s)** |
|
| 1. Social Mobilization of poor households and Institution building
2. Skill Training and Placement
3. No. of SHGs provided
 | 1.1 No. of Households mobilized into SHGs1.2. No. of predominantly SC/ST/Minority SHGs promoted2.1 **N**o. of persons trained under DDU-GKY2.2 No. of persons trained under RSETI3.1.No. of SHGs provided Community Investment Fund (CIF)3.2 Amount of Bank Credit accessed by SHGs | 1.Sustainable livelihoods of poor through skill building, access to credit, marketing and other livelihoods services | 1.1. No. of women producers covered under /farmers organization |
| 1.2 No. of SHGs provided with bank credit |
| 1.3. No. of persons placed under DDU-GKY1.4 No. of persons settled under RSETI |

1. **Shyama Prasad Mukherji Rurban Mission**

|  |  |
| --- | --- |
| **Outputs** | **Outcomes** |
| **Output** | **Indicator(s)** | **Outcome** | **Indicator(s)** |
|
| 1. Approval of Integrated Cluster Action Plan (ICAP)
2. Detailed Project Report (DPR) with SLEC approval
3. Development of Clusters as per DPRs submitted
 | No of ICAPs to be mobilized from statesNo. of DPRs to be mobilized from statesNo. of interventions proposed in DPR | Development of RURBAN Clusters | No of ODF Clusters |
| No of skill development clusters |
| Total CGF released (in Rs Cr) |

1. **Areas of Inquiry - National Social Assistance Programme (NSAP)**
2. **Background**

In the year 1995, the National Social Assistance Programme (NSAP) was introduced as a Centrally Sponsored Scheme and this was converted into Additional Central Assistance (ACA) Scheme in the year 2002. Initially, it had three components:- National Old Age Pension Scheme (NOAPS) providing a monthly pension of Rs. 75 to destitute of 65 years or higher; National Family Benefit Scheme (NFBS) providing one time assistance of Rs. 5000 in the case of death due to natural causes and Rs. 10000 in the case of death due to accidental causes of primary breadwinner in the age group of 18-64 years in a below poverty line household; and National Maternity Benefit Scheme (NMBS) providing a lump sum cash assistance of Rs. 300 to pregnant women of 19 years and above for up to the first two live births in a below poverty line household. NMBS was later transferred to the Ministry of Health and Family Welfare from 2001-2002. On 1st April, 2000, a new scheme with the objective of providing food security to the destitute called Annapurna was introduced to benefit deserving beneficiaries who could not be given assistance under the National Old Age Pension Scheme. In 2007 NOAPS was renamed as Indira Gandhi National Old Age Pension Scheme (IGNOAPS) and made applicable to all aged persons belonging to families living below the poverty line, instead of restricting it to destitute aged persons. Further, in 2009, two more pension schemes for widows and the disabled were introduced. Approximately, 3 crore beneficiaries are being assisted annually under the program. The major objective of the National Social Assistance Schemes is a social security and welfare programme to provide support to aged persons, widows, disabled persons and bereaved families on death of primary bread winner, belonging to socially and economically backward households.

NSAP at present has the following components:

1. Indira Gandhi National Old Age Pension Scheme(IGNOAPS)
2. Indira Gandhi National Widow Pension Scheme(IGNWPS)
3. Indira Gandhi National Disability Pension Scheme(IGNDPS)
4. National Family Benefits Scheme(NFBS)
5. Annapurna

The scale of Central Assistance under NSAP is as follows:

1. Indira Gandhi National Old Age Pension Scheme (IGNOAPS): Rs. 200/- per month per beneficiary to BPL persons who are in the age group of 60-79 years and Rs 500/- per month to 80 years and above.
2. Indira Gandhi National Widow Pension Schemes (IGNWPS): Rs. 300/- per month per beneficiary who are BPL and in the age group of 40-79 years.
3. Indira Gandhi National Disability Pension Scheme (IGNDPS):Rs. 300/- per month per beneficiary who are in the age group of 18-79 years.
4. National Family Benefit Scheme: Rs. 20000/- to the bereaved household in case of the death of primary bread winner of the family. The eligibility criteria are BPL person who is primary bread winner of the family and in the age group of 18-59 years.
5. Annapurna Scheme: 10 kg of food grain (wheat or rice) per month per beneficiary to those who are not covered under IGNOAPS.
6. **Objectives of the Evaluation Study**

The primary objective of Evaluation study of NSAP is to assess the extent to which the programme has achieved its objectives and to suggest solutions that need to be employed to improve the implementation processes. More specific objectives of the study are:

1. To assess the achievement of the objectives of the NSAP, as mentioned in paragraph 1;
2. Assessment of implementation of NSAP to ascertain the progress made under the scheme vis a vis the physical and financial target & its achievements;
3. To study the role of people and people’s organizations in planning, implementation and monitoring of NSAP;
4. To evaluate disbursement processes, mode of disbursement, periodicity and timely receipt of benefits;
5. To access the success of convergence of the scheme with other schemes/programmes
6. To evaluate the status of digitization, Aadhaar seeding of beneficiaries, verification processes and progress made by the States;
7. To examine the role of Gram Sabhas in identification of eligible beneficiaries
8. To analyze the effectiveness of the administrative and implementing system to draw the lessons for design for future schemes.
9. **Approach**

The selection of the Institution/Agency will be based on its financial status, existing faculty, proven track record and previous experience in the field of evaluation. The selection Institution/ agency will perform the following instruction:

* To develop study schedule /questionnaires in consultation with the subject matter Division and Development Monitoring and Evaluation Office (DMEO);
* To conduct the survey at all levels;
* To prepare the software for data entry, validation, compilation, report generation, etc.;
* To prepare the report under the overall supervision and guidance of DMEO while incorporating necessary corrections/ modification as suggested by NITI Aayog till the final report is approved by the Competent Authority;
* To submit five compact discs and five copies of the final report along with the basic data.
* For this project, the agency/institutions assigned this study should be available for discussion, etc. with the DMEO, as and when required, at short notice.
1. **Monitoring/ supervision of the framework and the Study**

The survey and the data collection work will be supervised by the officer of the DMEO, NITI Aayog as well as the officer of the concerned subject Vertical of NITI Aayog. There will be a Central Monitoring Committee in DMEO to review/facilitate the evaluation work.

1. **Areas of Inquiry – Pradhan Mantri Awaas Yojana-Gramin (PMAY-G)**

**1. Background**

To address these gaps in the rural housing program and in view of Government’s commitment to providing “Housing for All’’ by the scheme 2022, the IAY has been re-structured into Pradhan Mantri Awaas Yojana –Gramin (PMAY-G) w.e.f. 1st April 2016.

PMAY-G aims at providing a pucca house, with basic amenities, to all houseless householder and those households living in kutcha and dilapidated house, by 2022. The immediate the objective is to cover 1.00 crore household living in kutcha house/dilapidated house in three years from 2016-17 to 2018- 19.The minimum size of the house has been increased to 25 sq.mt (from20sq.mt) with a hygienic cooking space. The unit assistance has been increased from Rs. 70,000 to Rs. 1.20 lakh in plain and from Rs. 75,000 to Rs 1.30 lakh in hilly states, difficult areas and IAP district. The beneficiary is entitled to 90.95 person day of unskilled labour from MGNREGS. The assistance for construction of toilet shall be leveraged though convergence with SBM-G, MGNREGS or any other dedicated the source of funding. Convergence for piped drinking water, electricity connection, LPG gas connection etc. different Government programmers are also to be attempted.

The cost of unit assistance is to be shared between Central and State Government in the ratio 60:40 in plain areas and 90:10 for North Eastern and the Himalayan States. From the annual budgetary grant for PMAY-G, 90% of funds is to be released to States/UTs for the construction of new house under PMAY-G This would also include 4% allocation towards Administrative expenses .5% of the budgetary grant is to be retained at the central Level as reserve found for special Projects. The annual allocation to the states is to be based on the Annual Action Plan (AAP) approved by the Empowered Committee and the found to States /UTs is to be released in two equal instalments.

Once of the most important features of PMAY-G is the selection of beneficiary. To ensure that assistance is targeted at those who are genuinely deprived and that the selection is objective and verifiable, PMAY-G instead of selecting a the beneficiary from among the BPL households selects beneficiary using housing deprivation parameters in the Socio Economic and Caste Census (SECC), 2011 date which is to be verified by the Gram Sabhas. The SECC data captures specific deprivation related to housing among households. Using the data households that are houseless and living in 0, 1 and 2 kutcha wall and kutcha roof houses can be segregated and targeted. The Permanent Wait List so generated also ensures that the states have the ready list of the household to be covered under the scheme in the coming years (through Annual Select Lists) leading to better planning of implementation. To address grievances in beneficiary selection an appellate process has also been put in place.

**2. Objectives of the Evaluation Study:**

2.1 To assess the achievement of the objectives of PMAY-G, i.e. providing housing security, creating linked infrastructure like toilet, water availability, hygienic cooking space, gas connection etc.

2.2 To evaluate the physical and financial progress of PMAY-G.

2.3 To study the role of people and people’s organizations in planning, implementation and monitoring of PMAY-G.

2.4 To analyse the effectiveness of the administrative and implementing systems to draw lessons for design of future.

2.5 To evaluate disbursement processes, mode of disbursement, periodicity and timely receipt of benefits.

2.6 To assess the success of convergence of the scheme with other schemes/programmes.

2.7 To assess requirement of renovation of the houses constructed under IAY in rural areas.2.8 To evaluate the status of digitization, Aadhaar seeding of beneficiaries, verification processes and progress made by the States.

2.9 To examine the role of Gram Sabhas in identification of eligible beneficiaries.

**3. Approach**

The selection of institution/agency will be based on its financial status, existing faculty, proven track record and previous experience in the field of evaluation. The selected institution/agency will perform the following functions:

1. To develop study schedule/questionnaires in consultation with the subject matter vertical and the Development Monitoring and Evaluation Office (DMEO);
2. To conduct the survey at all levels;
3. To prepare the software for data entry, validation, compilation, report generation, etc.;
4. To prepare the report under the overall supervision and guidance of the DMEO while incorporating necessary corrections/modifications as suggested by it, till the final report is approved by competent authority;
5. For this project, the agency/institutions assigned this study should be available for discussion, etc. with the DMEO, as and when required, at short notice.

**4. Monitoring/Supervision of the Fieldwork and the Study**

1. The survey and the data collection work will be supervised by the officers of the DMEO.
2. There will be a Central Monitoring Committee in DMEO to review/facilitate the evaluation work.

**G. Areas of Inquiry - DAY-National Rural Livelihoods Mission (DAY-NRLM)**

**1. Background**

* 1. The Ministry of Rural Development (MORD), Government of India (GOI) has been implementing National Rural Livelihoods Mission (NRLM) since June, 2011, after restructuring Swarn jayanti Gram Swarozgari Yojana (SGSY). The central objective of the Mission is to eliminate rural poverty through innovative implementation strategies involving mobilization and organization of the rural poor and building their financial and economic inclusion. The NRLM is implemented on a cost sharing basis between the Center and the States.
	2. Implementation Structure of the scheme: At the national level, the Mission is implemented by a National Mission Management Unit (NMMU) comprising several thematic groups and professional experts, under the MORD. As part of transition to NRLM, the state governments are required to establish an autonomous and empowered State Rural Livelihoods Mission (SRLM) at the state level. As part of rolling- out SRLM, the states are required to set-up dedicated Mission Implementation Units at the State (SMMU), District (DMMU) and Sub-Districts Units like Block (BMMU) or Project Facilitation Team at Cluster Level. As NRLM is designed to promote certain new strategies requiring intensive application of financial, social capital and human resources, a phased expansion approach has been adopted. The phased implementation implies following a two track approach i.e. Intensive and non-intensive strategies of NRLM. While NRLP is absolutely an intensive strategy, under NRLM there is a freedom for the state to follow either intensive or non-intensive strategies.
	3. Objectives and Components: The cornerstone of NRLM strategy is the creation of Community Based Organizations of the poor, which if capacitated, nurtured and funded initially, will promote and sustain improved livelihoods for the poor. Thus, the NRLM aims at mobilizing all the rural poor households into SHGs and their higher level federations *viz.,*Village Organizations, Cluster/ Block Level Federations and use the institutional platforms so created to promote their livelihoods. The Mission seeks to promote access of the CBOs of the poor to financial and technical services as well as economic support services and enable them to diversify and improve their livelihoods. Towards this end, the Mission intends to promote organic financial and non-financial relations between the SHGs and their federations. In addition, the poor would be facilitated to achieve increased access to their rights, entitlements and public services, diversified risk and better social indicators of empowerment. The NRLM also aims at harnessing the innate capabilities of the poor and seeks to complements them with their capacities (information, knowledge, skills, tools, finance and collectivization) to deal with the rapidly changing external world. Further, the Mission is designed to facilitate shift of the states from the allocation based strategy to a demand-driven strategy, enabling the states in the process to formulate their own poverty reduction plans. Thus, the Mission aims at bringing about fundamental structural changes and reforms in the manner in which rural poverty alleviation programmes are implemented.
	4. NRLM is a process intensive programme and the culmination outcomes of the Mission depend on the quality of processes adopted at all levels. Based on successful models implemented in a few states, the Mission has designed process intensive strategies for implementation of social mobilization, financial inclusion, economic inclusion and other components. There is an ideal process and sequence in which each activity is to be implemented to achieve the intended results. A process intensive approach is particularly required for the development of the sustainable institutions of the poor. Only through a process of intensive capacity building, nurturing and handholding, SHGs and their federations could emerge as self-managed, self-governed and sustainable institutions, capable of accessing and delivering financial and livelihood services to the poor. NRLM has outlined a step-wise process for the states to implement Mission activities. Any deviation from the designed process could affect the Mission outcomes. However, if deviations are identified and corrected early, the Mission could achieve its objectives. Identifying the process deviations through internal reviews and monitoring is not always effective. Therefore, NRLM has provided for a third-party process monitoring to track the process deviations and provide early signals to the Mission management to undertake corrective action. Further, process monitoring would also help the Mission to learn from its own experience and improve upon its effectiveness over time. Thus, a well-designed process monitoring would identify deviations, facilitate mid-course corrections and improve upon the quality and effectiveness of Mission implementation.
	5. Key Features of NRLM: The Key features of NRLM are as under:

Social Inclusion and Institutions of the Poor

* Universal Social Mobilization
* Promotion of Institutions of the poor
* Training, Capacity building and skill building
* Revolving Fund and Capital Subsidy
* Universal Financial Inclusion
* Provision of Interest Subsidy
* Livelihoods
* Infrastructure creation and Marketing support
* Skills and Placement Projects
* Rural Self Employment Training Institutes (RSETIs)
* Innovations

Convergence and partnerships

* Convergence
* Partnerships with NGOs and other CSOs
* Linkages with PRIs

# **2. Objective of the Evaluation Study**

2.1 NRLM is based on a community driven development model (CDD). Any CDD programme requires continuous learning and adaptation in the course of implementation. Not all processes conform to pre-set rules, regulations, procedures and target approaches. Each state has a particular context in which the Mission is being implemented. Within each state, there could be a vast degree of diversity. What works in one state or in one geography may not work in other states/geographies. Evaluation is therefore envisaged to assess the quality of implementation processes in each state and in each phase and identify deviations which could affect the outcomes of the Mission, using both qualitative and quantitative information and taking into account the perceptions of different stakeholders. The main objectives are as follows:

1. To evaluate the financial and physical progress of the schemes under the programme.
2. To study the role of people and peoples organizations in planning, implementation and monitoring of the schemes under the programme.
3. To assess the achievement of the objectives of the programme i.e. to assess the extent of benefits accrued to the target group/area in various components of the programme.
4. To analyze the effectiveness of the administrative and implementing systems to draw lessons for design of future.
5. how and through what processes the intensive/resource block strategy has actually been rolled out (vis-à-vis the intended strategy) including the key processes initiated at SMMU, DMMU, BMMU and the community levels;
6. To study the role of people and people’s organizations in planning, implementation and monitoring of the programme.
7. To evaluate the status of digitization, Aadhaar seeding of beneficiaries, verification processes and progress made by the States
8. To examine the role of Gram Sabhas in identification of eligible beneficiaries
9. Findings of existing critical gaps in the programme;

**3. Approach**

3.1 The selection of institution/agency will be based on its financial status, existing faculty, proven track record and previous experience in the field of evaluation. The selected institution/agency will perform the following functions:

* To develop study schedule/questionnaires in consultation with the subject matter vertical and the Development Monitoring and Evaluation Office (DMEO);
* To conduct the survey at all levels;
* To prepare the software for data entry, validation, compilation, report generation, etc.;
* To prepare the report under the overall supervision and guidance of the DMEO while incorporating necessary corrections/modifications as suggested by it, till the final report is approved by competent authority;
* To submit five pen drives and five copies of the final report along with basic data;
* For this project, the agency/institutions assigned this study should be available for discussion, etc. with the DMEO, as and when required, at short notice.

**4. Monitoring/Supervision of the Fieldwork and the Study**

1. The survey and the data collection work will be supervised by the officers of the DMEO.
2. There will be a Central Monitoring Committee in DMEO to review/facilitate the evaluation work.

**H. Areas of Inquiry - Shyama Prasad Mukherji Rurban Misson (SPMRM)**

**1. Background**

The Government of India has launched a flagship program - Shyama Prasad Mukherjee Rurban Mission (SPMRM) referred as National Rurban Mission (NRuM) on February 21st, 2016. The objective of the National Rurban Mission (NRuM) is development of cluster of villages that preserve and nurture the essence of rural community life with focus on equity and inclusiveness without compromising with the facilities perceived to be essentially urban in nature, thus creating a cluster of Rurban villages.

The mission targets to create 300 such Rurban growth clusters over the next 3 years, across the country. In the first phase of the mission in 2016-17, total 100 clusters have been approved across the country. The scheme in its design has incorporated elements aimed at developing economic activities and skill development along with the provision of urban infrastructure. The clusters will be developed in an integrated manner with convergence of various government schemes in a time bound manner. The SPMRM will provide Critical Gap Funding (CGF) to the clusters to ensure that funding available through various Government schemes is supplemented in achieving the growth aspirations of the cluster. The cost of a cluster will be based on the requirements identified by the Integrated Cluster Action Plan (ICAP), prepared by the States, for the cluster and approved by the Empowered Committee. A maximum of 30% of the project cost will be provided as the Critical Gap Funding (CGF) to supplement the funds mobilized through convergence of various Centrally Sponsored Schemes, Central Sector Schemes and State Schemes. The major objectives of the scheme are as:

1. Bridging the Rural and Urban divide viz: economic, technological and those related to facilities and services;
2. Stimulating local economic development with emphasis on reduction of poverty and unemployment in rural areas;
3. Spreading development in the region;
4. Attracting investment in rural areas.
5. Skill development training linked to economic activities to all the rurban villages.
6. Upgrading school/ higher education facilities.
7. Improvised Sanitation facilities in all Rurban villages.

**2. Objectives of the Evaluation Study**

The objective of the evaluation study of National Rurban Mission (NRuM) is to stimulate local economic development, enhance basic services, and create well planned Rurban cluster.

The outcomes under this Mission are:

1. To assess the achievement of the objectives of the SPMRM, as mentioned in paragraph 1;
2. Assessment of implementation of SPMRM to ascertain the progress made under the scheme vis a vis the physical and financial target & its achievements;
3. To study the role of people and people’s organizations in planning, implementation and monitoring of SPMRM;
4. To evaluate disbursement processes, mode of disbursement, periodicity and timely receipt of benefits;
5. To access the success of convergence of the scheme with other schemes/programmes
6. To evaluate the status of digitization, Aadhaar seeding of beneficiaries, verification processes and progress made by the States;
7. To examine the role of Gram Sabhas in identification of eligible beneficiaries
8. To analyze the effectiveness of the administrative and implementing system to draw the lessons for design for future schemes.
9. **Approach**

The selection of the Institution/Agency will be based on its financial status, existing faculty, proven track record and previous experience in the field of evaluation. The selection Institution/ agency will perform the following instruction:

* To develop study schedule /questionnaires in consultation with the subject matter Division and Development Monitoring and Evaluation Office (DMEO);
* To conduct the survey at all levels;
* To prepare the software for data entry, validation, compilation, report generation, etc.;
* To prepare the report under the overall supervision and guidance of DMEO while incorporating necessary corrections/ modification as suggested by NITI Aayog till the final report is approved by the Competent Authority;
* To submit five compact discs and five copies of the final report along with the basic data.
* For this project, the agency/institutions assigned this study should be available for discussion, etc. with the DMEO, as and when required, at short notice.
1. **Monitoring/ supervision of the framework and the Study**

The survey and the data collection work will be supervised by the officer of the DMEO, NITI Aayog as well as the officer of the concerned subject Vertical of NITI Aayog.

There will be Central Monitoring Committee headed by a very senior official/ expert to review/ facilitate the evaluation work to be done by the Subject Matter Division. This committee will interalia have Advisers/ Consultants of the concerned subject matter divisions and DG (DMEO) as its Member.

1. **Areas of Inquiry- Pradhan Mantri Gram Sadak Yojana (PMGSY)**
	* + 1. **Background**

The Pradhan Mantri Gram Sadak Yojana (PMGSY) was launched in 2000 to provide a single all weather connectivity to unconnected habitations; envisaged connectivity to all unconnected habitations with a population of 500 persons (as per 2001 Census) and above in plain areas and 250 persons and above (Census 2001) in Special Category States’ namely North-East, Sikkim, Himachal Pradesh, Jammu & Kashmir and Uttarakhand, the Desert areas (as identified in Desert Development Programme) and 88 Selected Tribal and Backward districts as identified by the Ministry of Home Affairs/Planning Commission. For Most intensive IAP blocks as identified by Ministry of Home Affairs the unconnected habitations with population 100 and above (as per 2001 census) is eligible to be covered under PMGSY. The unit for this programme is a habitation and not a revenue village. PMGSY was being implemented as a 100 percent funded Centrally Sponsored Scheme., however since 1st April 2015, there has been a change in sharing pattern from 100% Central Share to following Centre: State; 60:40 in Plain Areas and 90:10 in North East and hilly states.

The Ministry of Rural Development and its associated technical arm, the National Rural Roads Development Agency (NRRDA) has been tasked with designing the programme strategy and overseeing actual implementation by States and District bodies.

The programme is implemented by the State Governments. Each State Government has nominated a department as Nodal Department (Rural Development or Public Works Department or Panchayati Raj Department) who is responsible for the implementation of the programme in the State. The Nodal Department has set up State level autonomous agency called State Rural Road Development Agency (SRRDA) with a distinct legal status. These agencies are registered under Societies Registration Act, 1860. The SRRDA get the work executed through Programme Implementation Unit (PIU) at district or tehsil level. The PIU is headed by an officer of the rank of Executive Engineer. He has technical staff and clerical staff on the pattern of public works system.

The main objective of the programme:

a) The primary objective of the PMGSY is to provide connectivity, by way of an all-weather Road (with necessary culverts and cross-drainage structures, which is operable throughout the year), to the eligible unconnected Habitations in the rural areas.

b) The PMGSY will permit the upgradation (to prescribed standards) of the existing roads in those districts where all the eligible habitations of the designated population size (refer Para 1 above) have been provided all-weather road connectivity. However, it must be noted that upgradation is not central to the Programme and cannot exceed 20% of the State’s allocation as long as eligible unconnected habitations in the State still exist. In upgradation works, priority should be given to Through Routes of the Rural Core Network, which carry more traffic.

* + - 1. **Objectives of the Evaluation Study**

The primary objective of Evaluation study of PMGSY is to assess the extent to which the programme has achieved its objectives and to suggest solutions that need to be employed to improve the implementation processes. More specific objectives of the study are:

1. To assess the achievement of the objectives of the PMGSY, i.e providing all weather road connectivity to all eligible and feasible unconnected habitations
2. Assessment of the progress made under the scheme vis a vis the physical and financial target & its achievements;
3. To assess the impact of PMGSY Operational Guidelines for (Construction and inbuilt provision of performance guarantee for 5 years maintenance post construction) on other rural road construction schemes of the State Governments
4. To assess the impact of community participation especially women Self help Group and Panchayati Raj members in decision making regarding road alignment and maintenance of roads.
5. To evaluate the status of digitization and use of IT tools in the scheme;
6. To evaluate the quality assurance mechanism in Tier-I, Tier-II and Tier-III.
7. To evaluate the asset management of roads constructed under PMGSY within 5-years DLP and post 5-years under renewal/maintenance contracts.
8. To analyze the effectiveness of the administrative and implementing system to draw the lessons for design for future schemes.

**3. Approach**

 The selection of the Institution/Agency will be based on its financial status, existing faculty, proven track record and previous experience in the field of evaluation. The selection Institution/ agency will perform the following instruction:

* To develop study schedule /questionnaires in consultation with the subject matter Division and Development Monitoring and Evaluation Office (DMEO);
* To conduct the survey at all levels;
* To prepare the software for data entry, validation, compilation, report generation, etc.;
* To prepare the report under the overall supervision and guidance of DMEO while incorporating necessary corrections/ modification as suggested by NITI Aayog till the final report is approved by the Competent Authority;
* To submit five compact discs and five copies of the final report along with the basic data.
* For this project, the agency/institutions assigned this study should be available for discussion, etc. with the DMEO, as and when required, at short notice.
1. **Monitoring/ supervision of the framework and the Study**

The survey and the data collection work will be supervised by the officer of the DMEO, NITI Aayog as well as the officer of the concerned subject Vertical of NITI Aayog. There will be a Central Monitoring Committee in DMEO to review/facilitate the evaluation work.

1. **Areas of Inquiry- Mahatma Gandhi National Rural Employment Guarantee Scheme (MGNREGA)**

**1. Background**

1.1 The Mahatma Gandhi National Rural Employment Guarantee Act (MGNREGA) notified on September 7, 2005, aims at enhancing livelihood security of households in rural areas of the country by providing at least one hundred days of guaranteed wage employment in a financial year to every household whose adult member’s volunteers to do unskilled manual work. MGNREGS has emerged as a major social safety net, augmenting rural employment. The norm of 33 percent participation of women is an important feature of MGNREGS. The works undertaken through MGNREGS give priority to activities related to water harvesting, groundwater recharge, drought-proofing, and flood protection. The different categories of permissible works are as follows:

Category: A: Public Works Relating to Natural Resources Management: work related to water conservation and water harvesting, watershed management works, micro and minor irrigation works, renovation of traditional water bodies, afforestation, land development works in common land.

Category B: Individual Assets for Vulnerable Sections (Only for Households in Paragraph 5 of Schedule I of MGNREGA):work related to improving productivity of lands through land development, improving livelihoods through horticulture, sericulture, plantation, and farm forestry; development of fallow or waste lands, unskilled wage component in construction of houses sanctioned under the Indira Awaas Yojana or such other state or central government scheme; creating infrastructure for promotion of livestock and fisheries.

Category C: Common Infrastructure for NRLM Compliant Self Help Groups: works for promoting agricultural productivity by creating durable infrastructure required for bio-fertilizers and post-harvest facilities including pucca storage facilities for agricultural produce; and common work-sheds for livelihood activities of self-help groups.

Category D: Rural Infrastructure: rural sanitation related work, maintenance of assets created under the Act, works for disaster preparedness or restoration, road connectivity to unconnected villages, construction of buildings for gram panchayats, cyclone shelters, anganwadi centres, village haats, crematoria at the village or block level, food grain storage structures, play fields etc.

1.2 In Schedule - I of the National Rural Employment Guarantee Act 2005, it is mentioned that

1.2.1 The focus of the scheme shall be on the following works in their order of priority:-

(i) Water conservation and water harvesting;

(ii) Drought proofing (including afforestation and tree plantation);

(iii) Irrigation canals including micro and minor irrigation works;

(iv) Provision of irrigation facility, horticulture plantation and land development facilities on land owned by households belonging to the Scheduled Castes and Scheduled Tribes or to Below Poverty Line families or to beneficiaries of land reforms or to the beneficiaries under the Indira AwasYojana of the Government of India;

(v) Renovation of traditional water bodies including Desilting of tanks;

(vi) Land development;

(vii) Flood control and protection works including drainage in water logged areas;

(viii) Rural connectivity to provide all-weather access; and

(ix) Any other work which may be notified by the Central Government in consultation with the State Government.

1.2.2 Creation of durable assets and strengthening the livelihood resource base of the rural poor shall be an important objective of the Scheme.

1.2.3 The works taken up under the scheme shall be in rural areas.

1.2.4 The scheme shall be subject to appropriate arrangements as may be laid down by the State Government under the rules issued by it for proper maintenance of the public assets created under the scheme.

1.2.5 The cost of material component of projects including the wages of the skilled and semi-skilled workers taken up under the scheme shall not exceed forty percent of the total project costs.

1.2.6 The Scheme shall not permit engaging any contractor for implementation of the projects under it.

1.2.7 As far as practicable, a task funded under the scheme shall be performed by using manual labour and not machines.

1.2.8 Provision of regular inspection and supervision of works taken up under the scheme shall be made to ensure proper quality of work as well as to ensure that the total wages paid for the completion of the work is commensurate with the quality and quantity of work done.

1.3 Panchayati Raj Institutions are principal planning, implementing and monitoring authorities. The Gram Sabha must monitor the execution of projects and conduct social audit of all projects executed within its territorial jurisdiction.

**2. Objectives of the Evaluation Study**

2.1 To assess the achievement of the objectives of MGNREGA, i.e. providing guaranteed wage Employment, creating durable rural assets and empowerment of economically and socially disadvantaged groups.

2.2 To evaluate the physical and financial progress of the scheme.

2.3 To study the role of people and people’s organizations in planning, implementation and monitoring of the scheme.

2.4 To analyse the effectiveness of the administrative and implementing systems to draw lessons for design of future.

2.5 To evaluate disbursement processes, mode of disbursement, periodicity and timely receipt of benefits.

2.6 To assess the success of convergence of the scheme with other schemes/programmes.

2.7 To evaluate the status of digitization, Aadhaar seeding of beneficiaries, verification processes and progress made by the States.

2.8 To examine the role of Gram Sabhas in identification of eligible beneficiaries.

2.9 To evaluate action plan approved by Zila Panchayat for execution of work.

**3. Approach**

The selection of institution/agency will be based on its financial status, existing faculty, proven track record and previous experience in the field of evaluation. The selected institution/agency will perform the following functions:

1. To develop study schedule/questionnaires in consultation with the subject matter vertical and the Development Monitoring and Evaluation Office (DMEO);
2. To conduct the survey at all levels;
3. To prepare the software for data entry, validation, compilation, report generation, etc.;
4. To prepare the report under the overall supervision and guidance of the DMEO while incorporating necessary corrections/modifications as suggested by it, till the final report is approved by competent authority;
5. To submit five pen drives and five copies of the final report along with basic data;
6. For this project, the agency/institutions assigned this study should be available for discussion, etc. with the DMEO, as and when required, at short notice.

**4. Monitoring/Supervision of the Fieldwork and the Study**

* The survey and the data collection work will be supervised by the officers of the DMEO.
* There will be a Central Monitoring Committee in DMEO to review/facilitate the evaluation work.
1. **Indicative list of Externalities and Environmental/Social Safeguards in scheme design**

|  |  |  |  |
| --- | --- | --- | --- |
| **S.No.** | **Scheme/Programme** | **Unintended Consequence/Negative Externality \*** | **Environmental/Social Safeguards in scheme design\*** |
| 1 | **MGNREGA** | 1. Reduced supply of labour for core agricultural activities. 2. Failure to create productive /sustainable /quality assets. | 1. Social Audit mechanism, environment friendly assets, 2. Agriculture and allied works such as wasteland redevelopment, irrigation works, watershed management etc. 3. Activities planned in the lean periods. |
| 2 | **PMGSY** | 1.Agricultural/ Community land used. 2. Clearing forest 3. Increasing soil pollution 4. Change in land use patterns along developed stretches 5. Debris disposal inadequate and haphazard | 1. Preparation of ESMF (Environmental and social management framework)2. Environment friendly (Green technology) approaches in construction 3. Legal and social safeguards followed in construction. |
| 3 | **PMAY-Gramin** | Community land for landless beneficiary - relocation | 1. Social Audit in the scheme 2. Convergence for Swachh Bharat 3. Convergence MNRE - clean cooking fuel |
| 4 | **Shyama Prasad Mukherji Rurban Misson (SPMRM)** | 1. Cluster based agglomerated development leads to higher land prices, congestion, pollution etc. 2. It leads to fragmentation of support services | 1. Focus on Specialised interventions which lack in that particular cluster. 2. Planned development of cluster to counter fragmentation and Urban challenges. |
| 5 | **NRLM** | None | 1. Group based intervention, 2. Social security through credit linkage and livelihood, |
| 6 | **NSAP** | None | 1. Target segment based entitlements |

**L. Guidelines for Evaluation Methodology**

One of the objectives of the study is to evaluate each of the individual centrally sponsored schemes (CSS) implementation during the 14th Finance Commission (14th FC) cycle (April 2015- March 2020). Some of the CSS were launched during the 14th FC period e.g., Smart Cities. Some of the CSS have continued from 12th Five Year plan period, e.g. MGNREGA. Some have been re-launched during the 14th FC period (e.g., AMRUT, Ayushman Bharat) with an expanded or modified mandate. Depending upon the duration of the implementation period, the evaluation has to flexibly adopt the logical framework to evaluate the scheme (Figure 1).

**Logical Framework: Inputs, Activities, Outputs, Outcomes, and Impact**

The evaluation will adopt the logical framework for consistency across all the 10 studies. The logical framework or *logframe* is an analytical tool used to plan, monitor and evaluate projects. It derives its name from the logical linkages to connect a project’s means with its ends. The main components of logical framework are inputs, activities, outputs, outcome and impact, which are described below:

1. **Inputs: The financial, human, material, technological and information resources used for the development intervention.**
2. **Activity:** Actions taken or work performed through which inputs, such as funds, human resources, and other types of resources are mobilised to produce specific outputs.
3. **Outputs:The products and services which result from the completion of activities within a development intervention.**
4. **Outcome: The intended or achieved short-term and medium-term effects of an intervention’s outputs. Outcomes represent changes in development conditions which occur between the completion of outputs and the achievement of impact.**
5. **Impact: Positive and negative long-term effects on identifiable population groups produced by a development intervention, directly or indirectly, intended or unintended. These effects can be economic, socio-cultural, institutional, environmental, technological or of other types.**

The evaluation team will assess all the dimensions of the logical framework. In mature programs whose implementation period is more than 5 years, greater emphasis will be on outcomes and impact, while in more recently launched programs with less than 5 years of implementation period, the evaluation will focus more on activities, outputs and outcomes.

|  |
| --- |
| **Figure 1: Logical Framework: Inputs, Activities, Outputs, Outcomes and Impact** |
|  |

**Cross Sectional Themes**

It is important for the evaluation to assess the relevant cross sectional themes, where such a theme is not the main component of the scheme but can indirectly influence scheme performance in terms its relevance, effectiveness, efficiency, equity and sustainability. The specific cross-sectional themes relevant to a sector have been covered in the evaluation study objectives.

**Mixed Methods and Triangulation**

Given various constraints and complexity of the evaluation of CSS, a flexible mixed methodology, relying on triangulation of existing evidence and primary data to be collected by the evaluation study would be required. Mixed methods approaches are used to increase validity of evaluation findings by using a variety of data collection techniques. Using both qualitative and quantitative data collection, along with meta-analysis of previous evaluation studies and monitoring reports produced by the government (central, state, government agencies, etc.) and by non-government agencies (think tanks, academia, international development agencies), the evaluation study will triangulate the findings to evaluate the scheme using the Relevance, Effectiveness, Efficiency, Equity, Sustainability and Impact framework. During the designing of the evaluation tools—qualitative and quantitative--the evaluation consultant will keep in view the relevance, effectiveness, efficiency, sustainability, equity and impact framework, which is described below:

**Assessments using the core criteria of relevance, effectiveness, efficiency, sustainability, impact (REESI)[[20]](#footnote-20) and equity**

**Relevance.** The relevance assessment addresses the extent to which: (i) the intended outcomes of the scheme were strategically aligned with India’s national priorities (considering both what is included in the scheme and what ought to be included) and did not duplicate other government initiatives; and (ii) the scheme design was appropriate for achieving the intended outcomes, i.e., competent analysis was carried out, lessons were applied, the right financing instrument or modality was chosen, innovation and transformative effects were given attention, and the indicators and targets at various levels were laid down well and lent themselves to measurement.

In assessing for relevance, credit should be given to scheme design elements that are innovative and/or that contribute to transformative effects, in terms of significantly improving the beneficiaries’ well-being, or promoting positive reforms. A scheme’s approach to addressing an identified development constraint should be assessed relative to existing good practice standards.

**Effectiveness.** The effectiveness assessment looks at whether the scheme’s intended outcomes were achieved or were expected to be achieved at the time of observation, and whether any unintended outcomes had inadvertently reduced the value of the scheme. The outcomes are evaluated against the baselines and targets listed in the scheme documents at the outcome level. Outcomes must be available to the intended scheme beneficiaries. For a scheme to be assessed as effective, outcomes should have been achieved or be likely to be achieved and output targets should normally also have been substantially achieved. Scheme-level output-outcome monitoring framework indicators provided as part of the terms of reference will be used for assessment of effectiveness.

Data on outputs and outcomes need to be derived from credible and documented sources. When no data on outcomes are available, it may be possible to review available data on the quality of outputs and capacity of the facilities developed by the scheme, as well as available data on demand conditions, to infer the likely level of usage of the outputs and the attainment of outcomes. Some outputs can serve as leading indicators of outcomes. Lack of any credible evidence can be reason to assume the outcomes were not fully achieved.

Schemes can have unintended adverse effects on people if social and environmental risks are not dealt with. If scheme interventions resulted in environmental degradation or in scheme communities or women being negatively affected (in spite of safeguard measures or gender action plans), the effectiveness assessment will be reduced. If well executed safeguard plans have led to net benefits, for instance if they have improved the livelihoods of affected people or improved the environment, this will improve the effectiveness assessment.

**Efficiency:** The efficiency of a scheme is a measure of how well it used resources to achieve its outcomes. It indicates whether the scheme used resources efficiently for the country and/or on a whole-of-life basis. A quantitative assessment that weighs the scheme’s economic benefits against economic costs is generally needed to assess efficiency. Scheme economic performance indicators, such as the EIRR, net present value, and the benefit−cost ratio, are often used to determine whether the net gains from investing in a particular scheme will be enjoyed by society following scheme completion. Applying the traditional EIRR approach may not always be feasible, for instance for some social sector schemes, or for other schemes where benefits are not easy to quantify comprehensively. In such cases, alternative analytical methods may have to be used: least cost analysis, among others.

Unit cost analysis case be used as a proxy for economic efficiency where benefits cannot be quantified with a high degree of confidence, or where data on benefits are not available. Efficiency can sometimes be analyzed for an assumed level of economic benefits, based on an average unit cost analysis based on industry benchmarks, at the time of appraisal and completion. Analysis can be based on unit costs for comparable activities that could achieve the same or similar benefits in order to assess efficiency on a least unit cost basis. If financial data are lacking, estimates can be prepared for indicators such as average financial unit costs for achieving a defined development outcome. Cost per beneficiary estimations can also be used in sectors such as education and health.

A process efficiency assessment should examine aspects such as the scale of delays and cost overruns and their effects on scheme performance, including the factors that resulted or contributed to these overruns.

**Sustainability:** The sustainability assessment will focus on the likelihood that scheme outcomes and outputs will be maintained over the economic life of the scheme or over a meaningful timeframe. Since evaluation in some schemes is carried out during the first few years of the scheme’s operational life, evaluators must make assumptions about the likely sustainability of operational arrangements, many of which are new, and about probable future operations and maintenance arrangements. They must also look into the wider environmental effects of schemes. The major factors to be considered when assessing sustainability are as follows:

1. *Sustainability and managing risks.* Assessments of sustainability should consider risks such as political, economic, institutional, technical, social, environmental, and financial events that might limit the extent to which the scheme’s achievements continue to be felt. The assessment should also consider the adequacy of risk mitigation measures.
2. *Financial sustainability.* This can be assessed on a qualitative or a quantitative basis depending on the feasibility of assessing the scheme’s income (revenue) and expenditure flows. Financial viability for revenue-generating schemes is based on the estimated financial internal rate of return (FIRR) of these incremental cash flows. Key aspects of the financial sustainability of both revenue and non-revenue generating schemes are: the financial capacity of the agency involved, prospects for the demand for services or products, cost recovery mechanisms, and the availability of resources for O&M of the scheme outputs.
3. *Institutional sustainability.* The assessment of institutional sustainability needs to consider factors such as the ability to ensure adequate levels of qualified human resources, finance, equipment and other inputs, and the suitability of organizational arrangements and processes, governance structures, and institutional incentives. An institutional assessment may include an analysis of how the ownership, functions, structures, and capacity of scheme-related agencies affected scheme-related inputs and service delivery, including the institution’s capacity to assume its identified role or mandate.
4. *Environmental and social sustainability.* The scheme’s likely medium- to long- term effects on natural resource management, pollution, biodiversity, and greenhouse gas emissions should form part of the sustainability assessment, if applicable. Close attention also needs to be paid to the effects of the scheme on social sustainability, for instance how the scheme is accepted by the local communities and stakeholders.

**Impacts:** The development impacts assessment is focused on long-term, far-reaching changes to which the scheme has plausibly contributed. It should answer questions such as: Does the scheme contribute to reaching higher-level development objectives (preferably, overall objective/national priorities)? What is the impact or effect of the intervention in proportion to the overall situation of the target group or those affected? Further, the assessment should also consider possible unintended positive and negative development impacts.

*Special development impacts:* If the scheme aimed to have demonstration effects and/or had innovative features, their impact may be considered. The assessment can also include a discussion of any efforts to scale up and replicate successful features of the scheme that were not previously evident in other schemes in the country or in communities, that have been made during or after scheme implementation. Other elements that would receive positive consideration include successful capacity building activities, and potential for positive institutional or governance impacts.

*Attribution to the scheme:* Development impacts to which the scheme contributes tend to be outside the scheme’s direct control and their achievement is often not solely attributable to the scheme outcomes. Typically, they are dependent on other development efforts. The focus of analysis should be on the contribution of scheme outcomes to the achievement of the impacts.

**Equity:** In addition to the globally accepted REESI framework, it is important to conduct the evaluation through the lens of equity. It assesses the extent to which government services are being made available to and accessed by different social groups. Particularly in schemes designed for universal coverage, the fair inclusion or intended or unintended exclusion of beneficiaries belonging to vulnerable, marginalized, disadvantaged groups and weaker sections of society must be considered. The existence and effectiveness of targeted action for these groups should also be assessed. Further, the schemes should be assessed based on their contribution to the reduction of inequality of opportunity and income.

It should be assessed whether this principle has been integrated into the scheme at the design stage, as well as whether it is playing out in implementation, i.e. whether all sub-groups within the target beneficiary group are getting equitable benefits. This will involve identifying barriers to participation among different groups, and whether these barriers have been sufficiently addressed by the scheme design and implementation. Equity should thus be factored in during data collection, preparation of findings and conclusions and in the recommendations arising from the evaluation.

**Tools for evaluation**

Both qualitative and quantitative tools will be utilized by the consultant to assess the CSS from the relevance, effectiveness, efficiency, sustainability and impact framework. While framing the questionnaires for qualitative and quantitative tools, the audience, questions and information use given at Figure 2 may be considered.

**Qualitative tools**: The consultant will utilize in-depth interviews and focus group discussion.

**In-depth Interview:** It is a personal interview that is carried out with one respondent at a time. This is purely a conversational method and invites opportunities to get details in depth from the respondent. One of the advantages of this method provides a great opportunity to gather precise data about what people believe and what their motivations are. These interviews can be performed face-to-face or on phone and usually can last between half an hour to two hours or even more.

* *Guide for Review of Documentation and Interviews with Policymakers, Managers, and Other Key Stakeholders:* From your perspective, what is the program trying to accomplish, and what resources does it have? What results have been produced to date? What results are likely in the next year or two? Why would the program produce those results? What are the program’s main problems? How long will it take to solve those problems? What kinds of information do you get on the program’s performance and results? What kinds of information do you need? How do you (how would you) use this information? What kinds of program performance information are requested by key stakeholders?
* *Guide for Review of Documentation and Interviews with Operating-Level Managers and Staff:* What are your goals for the project or program? What are the major project activities? Why will those activities achieve those goals? What resources are available to the project? Number of staff? Total budget? Sources of funds? What outputs are being delivered by the project? To whom? What evidence is necessary to determine whether goals are met? What happens if goals are met? What happens if they are not met? How is the project related to local priorities? What data or records are maintained? Costs? Services delivered? Service quality? Outcomes? Something else? How often are these data collected? How is this information used? Does anything change based on these data or records? What major problems are you experiencing? How long will it take to solve those problems? What results have been produced to date? What results are likely in the next two to three years?

**Focus Group:** A focus group is a group interview of approximately six to twelve people who share similar characteristics or common interests. A facilitator guides the group based on a predetermined set of topics. The facilitator creates an environment that encourages participants to share their perceptions and points of view. Focus groups are a qualitative data collection method, meaning that the data is descriptive and cannot be measured numerically. Focus groups are useful for: gathering feedback on activities, projects and services; generating and evaluating data from different groups that use a service or facility, or that an agency wants to target; generating and evaluating data from different groups within a local community or population; and developing topics, themes and questions for further research activities like questionnaires and more detailed interviews. They are good in use in conjunction with other forms of evaluation as they can help ‘triangulate’ findings.

|  |
| --- |
| **Figure 2: Audience, questions, and information use** |
|  |

**Quantitative Tools**

Household/individual level survey: The household survey is important to evaluate the quantity and quality of outputs (services rendered by the government or publicly funded services but provided through private or non-government organizations). Household surveys also give deeper insights into outcomes, although establishing cause-effect relationship between an individual CSS outputs to outcomes may be not that clear. With help of innovative survey designs, triangulation between qualitative and quantitative, along with weight of past evidence, a more robust understanding of umbrella and individual CSS’s contribution to desired sector outcomes can be arrived for policy making purposes.

Household surveys will consist of two parts: household level questions and individual level questions.

To ensure consistency across all the 10 studies, both household and individual level survey questionnaires will consist of standardized questionnaires as well as sector specific variable questionnaires. The standardized questionnaire will be provided around the time of bid award, but will broadly follow the household characteristics of 69 and 71 rounds of the National Sample Survey of India, and individual characteristics of 71 round of the National Sample Survey of India.[[21]](#footnote-21)

**Generalizability of the findings**

The key to quantitative surveys is to find a means to strengthen the generalizability of findings once desired outcome are measured. The key questions to ask to strengthen the generalizability of findings include:

1. To what groups or sites will generalization be desired?
2. What are the key demographic (or other) groups to be represented in the sample?
3. What sample size, with adequate sampling of important subgroups, is needed to make generalizations about the outcomes of the intervention?
4. What aspects of the intervention and context in which it was implemented merit careful measurement to enable generalizability or transferability of findings?
1. $ **Instructions for Applicants**

**Note 1**: Blank spaces contain formats that are to be used by the Applicant after the RFP is issued. (See Appendix-III)

**Note 2**: Footnotes marked “$” in the relevant Clauses of the RFP and Schedules are for guidance of the Applicants. In case of Appendices, the footnotes marked “$” or in other non-numerical characters shall be omitted by the Applicants while submitting their respective Proposals. (See Appendix-III) [↑](#footnote-ref-1)
2. $ No separate annual financial statements should be submitted. [↑](#footnote-ref-2)
3. $ While extending the Proposal Due Date on account of an addendum, the Authority shall have due regard for the time required by Applicants to address the amendments specified therein. In the case of significant amendments, at least 15 (fifteen) days shall be provided between the date of amendment and the Proposal Due Date, and in the case of minor amendments, at least 7 (seven) days shall be provided. [↑](#footnote-ref-3)
4. Ramesh Chand and *et.al.* (2017), Discussion Paper “Changing Structure of Rural Economy of India Implications for Employment and Growth” [↑](#footnote-ref-4)
5. <http://www.niti.gov.in/india-s-commitment-to-the-sdgs> [↑](#footnote-ref-5)
6. NITI Aayog,‘*Strategy for New India@75,*2018 (<http://niti.gov.in/writereaddata/files/Strategy_for_New_India.pdf>) [↑](#footnote-ref-6)
7. Ashish Mathur , 2011,“The Dimensions of Indian Rural Development: Issues and Challenges” International Journal of Contemporary Practices - Vol. 1, Issue. 2(June, 2011)ISSN: 2231-5608 [↑](#footnote-ref-7)
8. CAG Report, 2017, <https://cag.gov.in/sites/default/files/audit_report_files/Chapter_2_Compliance_Audit_of_Implementation_of_NRLM.pdf> [↑](#footnote-ref-8)
9. Planning Commission, GoI, 2008, “A Report on the Success and Failure of SHG’s in India – Impediments and Paradigm of Success”
<http://planningcommission.nic.in/reports/sereport/ser/ser_shg3006.pdf> [↑](#footnote-ref-9)
10. ECG. 2011. Good Practice Standards for Public Sector Operations. Washington, DC:

(<https://www.ecgnet.org/documents/4794/download>) [↑](#footnote-ref-10)
11. This is an indicative structure, which will evolve through the project timeline. [↑](#footnote-ref-11)
12. Separate sub-sections should be provided for each of the cross-sectional themes as outlined in Paragraph 2 of the TOR. This is applicable across sections of the Indicative Report Structure where cross-sectional themes are mentioned. [↑](#footnote-ref-12)
13. This section is applicable only where there is more than one scheme under the Umbrella. [↑](#footnote-ref-13)
14. WHO: A Guide to Identifying and Documenting Best Practices in Family Planning Programmes (<https://www.who.int/reproductivehealth/publications/family_planning/best-practices-fp-programs/en/>) [↑](#footnote-ref-14)
15. Where the Agreement Value specified in Clause 6.1.2 of this Agreement is expected to be less than Rs. 2 crore, the provision for a sole arbitrator shall be retained and where the Agreement Value is likely to be more than Rs. 2 crore, the provision for a Board shall be retained. [↑](#footnote-ref-15)
16. $ In case the Applicant is unable to provide the certification specified in Paragraph 12, it may precede the Paragraph by the words viz. “Except as specified in Schedule ………..... hereto”. The exceptions to the certification or any disclosures relating thereto may be clearly stated in a Schedule to be attached to the Application. The Authority will consider the contents of such Schedule and determine whether or not the exceptions/disclosures are material to the suitability of the Applicant for pre-qualification hereunder. [↑](#footnote-ref-16)
17. $ Please strike out whichever is not applicable [↑](#footnote-ref-17)
18. $ This Appendix-III contains a list of Clauses, Schedules and Appendices that would need to be suitably modified for reflecting bid-specific provisions. This Appendix-III may, therefore, be included in the RFP document to be issued to prospective Applicants [↑](#footnote-ref-18)
19. This is derived from the budget document (<https://www.indiabudget.gov.in/>) as Total = AE 15-16 + AE 16-17 + AE 17-18 + RE 18-19 + BE 19-20 [↑](#footnote-ref-19)
20. ECG. 2011. Good Practice Standards for Public Sector Operations. Washington, DC: <https://www.ecgnet.org/documents/4794/download> [↑](#footnote-ref-20)
21. <http://mospi.nic.in/download-reports?main_cat=NzIy&cat=All&sub_category=All> [↑](#footnote-ref-21)