## Sheet1
Serial No. | Functions |  | Activities | Responsibility | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01
1 | OOMF Framework Development | Current FY | Output Outcome Monitoring Framework (for schemes above INR 500 Crores) presented in the Parliament for FY 2021-22 | OOMF core team & DOE | 2021-02-01: 1st
2 |  |  | OOMF documents (for schemes below INR 500 Crores) to be shared by DMEO team with M/Ds via a D.O. letter from CEO, NITI Aayog | OOMF core team | 2021-02-01: 5th
3 |  |  | OOMF documents (for schemes below INR 500 Crores) finalized by M/Ds and presented as a part of the Detailed Demands for Grants | M/Ds | 2021-02-01: 28th
4 |  |  | Updation of targets and indicators for schemes above INR 500 Crores on the dashboard | DMEO team | 2021-02-01: 28th
5 |  |  | Letter to M/Ds to (i) share their OOMF documents for schemes below INR 500 Crores and presented as a part of the Detailed Demands for Grants and (ii) quarterly targets for all schemes with DMEO team by 30th Mar | OOMF core team | 2021-03-01: 1st
6 |  |  | 2nd Reminder Letter to M/Ds to (i) share their OOMF documents for schemes below INR 500 Crores and presented as a part of the Detailed Demands for Grants and (ii) quarterly targets for all schemes with DMEO team (iii) Update progress for last year by 30th Apr | OOMF core team | 2021-04-01: 1st
7 |  |  | Updation of progress for last year on dashboard by M/Ds | M/Ds | 2021-04-01: 30th
8 |  |  | Updation of targets and indicators for schemes below INR 500 Crores on the dashboard | DMEO team | 2021-05-01: 15th
9 |  |  | Compilation of OOMF notes for previous year (compliance and progress reports) | DMEO team | 2021-06-01: 10th
10 |  |  | OOMF notes to be shared with Ministry/Departments and verticals of NITI Aayog | OOMF core team | 2021-06-01: 15th
11 |  |  | M/D wise OOMF Review meetings under chairmanship of Hon’ble Members of NITI Aayog | DMEO team, NITI verticals and M/Ds | 2021-10-01: 15th
12 |  |  | 2nd round of compliance notes to be shared with M/Ds (for Q1 + Q2 of current year) - may be automated via the DB | DMEO team | 2021-10-01: 30th Oct
13 |  | Next FY | Developing OOMF frameworks for all schemes of all M/Ds | DMEO team | 2021-10-01: From 15th; 2021-11-01: 25th
14 |  |  | Sharing OOMF frameworks with M/Ds via a D.O. letter from CEO, NITI Aayog for their finalization and annual targets by 15th Dec | OOMF core team | 2021-11-01: 30th
15 |  |  | One to one meetings/conversations with Minsitries for the finalization of the indicators and targets | DMEO and M/Ds | 2021-12-01: 15th
16 |  |  | Sending 2nd reminder letter to pending M/Ds for their finalization and annual targets by 30th Dec | OOMF core team | 2021-12-01: 15th
17 |  |  | Compilation of OOMF for next FY (more than 500 Crores consolidated document and M/D wise less than 500 Crore documents) | DMEO team | 2021-12-01: 30th
18 |  |  | Submission of OOMF to DOE for FY 2022 | OOMF core team | 2022-01-01: 10th
19 |  |  | Output outcome monitoring framework 2022-2023 presented in Parliament | OOMF core team & DOE | 2022-02-01: 1st
20 | Dashboard related internal activities | - | AMC approval and related invoice processing | OOMF core team | bar: 2021-12-01 to 2022-01-01
21 | Parternship and Capacity building of M/Ds |  | Training session for DoE officials and FAs on utilization of OOMF Dashboard (involving them in review meetings) |  | 2021-10-01: 15th